TERMS OF REFERENCE

national consultant

| Name of assignment | Drafting of a Decision for the National REDD+ Program – financial context |
| --- | --- |
| Country of the assignment | Viet Nam |
| Project title | UN-REDD Viet Nam Programme |
| Duration of the Assignment | 30 days in the period May – June 2011 |

1. GENERAL INFORMATION

The UNFCCC recognizes Viet Nam as one of the top five most affected countries in the world as a result of climate change. Although not suffering from excessive levels of deforestation typical of some other countries in the region, deforestation is locally significant in Viet Nam, especially in the Central Highlands. Furthermore, natural forests continue to be more fragmented and degraded and its quality is therefore declining. Over two-thirds of Viet Nam’s natural forests are considered poor or regenerating, while rich and closed-canopy forest constitutes only 4.6 percent (in 2004) of the total.

The UN-REDD Viet Nam Programme seeks to establish the sustainable management of forests through capacity building at national and local levels. Firstly, it builds capacity at the national level to permit the Government of Viet Nam to coordinate and manage the process of implementing a National REDD+ Program. Secondly, it will build capacity at local levels through pilots in two districts in Lam Dong province that demonstrate effective approaches to planning and implementing measures to reduce emissions.

The Objective of the UN-REDD Viet Nam Programme is “To assist the Government of Viet Nam in developing an effective REDD regime in Viet Nam and to contribute to reduction of regional displacement of emissions.”  This will contribute to the broader goal of ensuring that “by the end of 2012 Viet Nam is REDD-ready and able to contribute to reducing emissions from deforestation and forest degradation nationally and regionally.”

The National REDD+ Program is one of the key priorities of the Ministry of Agriculture and Rural Development (MARD) and it is considered crucial in meeting the objectives of the National Target Program on the Reduction of Climate Change impacts (NTP-RCC). REDD+ will be pervasive throughout the operations of the Viet Nam Administration of Forestry within the Ministry and it will have important consequences for the other sections of the Ministry. REDD+ has an impact at the national level where the National REDD+ Program will be administered, but also at regional offices of the Ministry where many of the operational tasks will be concentrated. Important elements of the National REDD+ Program involve coordination and collaboration with other government agencies as well as with stakeholders outside of the government.

In order to establish an effective National REDD+ Program the governance structures have to be designed and implemented in such a way that all offices and stakeholders inside and outside of the government are included in an objective, efficient and transparent way. To this order a baseline study has been undertaken which outlines the options for the establishment of the National REDD+ Program; this study is currently in the process of stakeholder consultation to identify the appeal of the various options presented.

The Government of Viet Nam has recently defined the initial governance structure of the National REDD+ Program, through the establishment of the National REDD+ Steering Committee – as the principal policy and governance board for REDD+ – and the Viet Nam REDD+ Office – as the central office for REDD+ implementation.

2. OBJECTIVES

The main objectives of this assignment are as follows:

- To draft the legal text for the establishment of the National REDD+ Program, with particular reference to the institutional setup and structures for financing REDD+, both at central level and in the provinces. The management of the National REDD+ Program has to follow certain principles that meet national standards of governance, but at the same time it has to be responsive to the requirements of the REDD+ mechanism, as defined by the UNFCCC.

- To integrate all work done by other consultants on the UN-REDD Viet Nam Programme as it relates to the definition of the National REDD+ Programme: baseline study, governance design of the National REDD+ Program, design of the National REDD+ Fund.

The assignment will be undertaken jointly with a second National Consultant who specializes in forestry governance of the National REDD+ Program.

The National REDD+ Program will ultimately apply to the entire forest estate of Viet Nam and its National REDD+ Fund will manage all the financial resources available to the Program. The Consultants will liaise closely with the Viet Nam Administration of Forestry and the senior technical staff in the UN-REDD Viet Nam Programme to ensure proper consideration of all requirements of the REDD+ mechanism and the national legal system.

3. MILESTONES & FINAL PRODUCTS

Expected delivery milestones and final products, to be delivered jointly by the Consultants:

|  | Products | Deadline of submission |
| --- | --- | --- |
|  | Interim report, with an outline of the draft text for the establishment of the National REDD+ Program. | After 4 weeks |
|  | Final report with full documentation on: The draft text for the establishment of the National REDD+ Program. Full description of how other reports and comments from stakeholders have been considered in the draft text. | After 8 weeks |

Notes: All reports should be made available in English.

4. SCOPE OF WORK

The National Consultant needs to carry out the tasks as follows:

- Prepare an outline of the draft text for the establishment of the National REDD+ Program, based in principle on reports prepared for the UN-REDD Viet Nam Programme.

- Participate in stakeholder consultations on the National REDD+ Program.

- Prepare a draft text for the establishment of the National REDD+ Program.

- Present the outcomes of this assignment at a workshop, to be organized by the UN-REDD Viet Nam Programme.

5. DURATION OF THE ASSIGMENT, DUTY STATION AND EXPECTED PLACES OF TRAVEL

Duty station: Ha Noi.

Duration of the assignment: 30 working days in the period May – June 2011.

Expected places of travel: Ha Noi.

6. PROVISION OF MONITORING AND PROGRESS CONTROL

The National Consultant will perform the tasks as required under the direct supervision of the UN-REDD Viet Nam Programme, and will be subjected to report on the progress of the assignment whenever required by the Programme. After the signing of the contract, the National Consultant and the Programme will have a meeting to determine and agree on how the work progress should be reported, where detail regulations on progress control, progress reporting and timeline will be developed and agreed between the Programme and the National Consultant.

7. REQUIRED SKILLS AND EXPERIENCE

- Advanced University degree in Forest Economics, Public Administration, or similar.

- At least 5 years professional experience, with special reference to work in financing mechanisms for agriculture, forestry and/or rural development.

- Knowledge of the REDD+ mechanism under the UNFCCC and the Vietnamese proposal for a National REDD+ Program, as detailed in the UN-REDD Joint Programme Document and the proposal submitted to the Forest Carbon Partnership Facility of the World Bank.

- Excellent knowledge of the Vietnamese legal and regulatory context, with special reference to financial management.

- Fluency in spoken and written English.

8. ADMIN SUPPORT AND REFERENCE DOCUMENTS

- Vietnamese legal documents (available from http://www.luatvietnam.vn/):

  - Law on Forest Protection and Development (2004)

  - Decision on the Forest Protection and Development Fund

  - Decision on the Trust Fund for Forest

- Viet Nam R-PP proposal to the FCPF, available from http://www.forestcarbonpartnership.org/fcp/VN

- UN-REDD Joint Programme Document, available from http://www.un-redd.org/UNREDDProgramme/CountryActions/VietNam/tabid/1025/language/en-US/Default.aspx

- Benefit Distribution Study for Viet Nam, available online as above

9. PAYMENT TERM

Remuneration will be based on the UN-EU Cost Norm at the VNM-3 level.

Payments will be made as follows:

- 20% upon receiving and acceptance of detailed work plan

- 50% upon receiving and acceptance of interim report

- 30% upon receiving and acceptance of final report