|  |  |
| --- | --- |
| Agreed next steps for the PGA in Nigeria |  |
| Milestones: | **Specific activities:** | **By whom:** | **By when:** |
| Follow-up after the Calabarworkshop | * Share workshop report with agreements on key governance domains, organizational structure and next steps
* Share preliminary research report
 | Workshop team/ PGA coordinator | 4/2/13 |
| Get baseline governance data | * Indicator training
* Develop indicator set
* Agree on data collection methods and process
* Information/ data collected
* Stakeholder validation of the findings
 | UN-REDD/ FAOResearch team proposes, PGA/ REDD+ committee validates/ adoptsResearch team proposes, PGA/ REDD+ committee validates/ adoptsResearch team/ data collectors overseen by PGA coordinatorPGA/ REDD+ Consultative Network validates, facilitated by PGA coordinator | 18/1/1318/3/1318/3/1318/7/13End of August |
| Develop a communication strategy | * Start discussing the end-users and dissemination of PGA information to ensure this reaches communities in appropriate form/ language
 | PGA/REDD+ Committee (to be presented to the PGA/ REDD+ Consultative Network) | Continuous work until we have the baseline data |
| Recruit a full-time PGA coordinator(as soon as possible) | * Develop ToR
* Recruitment
 | Inputs from UN-Nigeria and UN-REDD, to be validated by the PGA/ REDD+ committeeUNDP Nigeria/ UN-REDD team | ASAP |