|  |  |  |  |
| --- | --- | --- | --- |
| Agreed next steps for the PGA in Nigeria | | |  |
| Milestones: | **Specific activities:** | **By whom:** | **By when:** |
| Follow-up after  the Calabar  workshop | * Share workshop report with agreements on key governance domains, organizational structure and next steps * Share preliminary research report | Workshop team/ PGA coordinator | 4/2/13 |
| Get baseline  governance data | * Indicator training * Develop indicator set * Agree on data collection methods and process * Information/ data collected * Stakeholder validation of the findings | UN-REDD/ FAO  Research team proposes, PGA/ REDD+ committee validates/ adopts  Research team proposes, PGA/ REDD+ committee validates/ adopts  Research team/ data collectors overseen by PGA coordinator  PGA/ REDD+  Consultative Network validates, facilitated by PGA coordinator | 18/1/13  18/3/13  18/3/13  18/7/13  End of August |
| Develop a  communication  strategy | * Start discussing the end-users and dissemination of PGA information to ensure this reaches communities in appropriate form/ language | PGA/REDD+ Committee (to be presented to the PGA/ REDD+ Consultative Network) | Continuous work until we have the baseline data |
| Recruit a full-time  PGA coordinator  (as soon as possible) | * Develop ToR * Recruitment | Inputs from UN-Nigeria and UN-REDD, to be validated by the PGA/ REDD+ committee  UNDP Nigeria/ UN-REDD team | ASAP |