Proposed Revised Indicators for the Programme Monitoring Framework

| Expected Results (Outputs) | Indicators (with baselines & indicative timeframe) | Proposed Revision |
| --- | --- | --- |
| 1.1 National REDD+ Readiness Coordination Mechanism established | - Baseline: interim Taskforce, no approved ToR - By 6/2012 a multi-agency Taskforce is approved - By 6/2012 a draft Taskforce TOR is agreed | Baseline: Initial formal TF meeting expected August 2013 By the end of 2013, the TF has met on at least on 2 occasions and has established rules of procedure and working process By the end of the Programme, the TF has made decisions related to a safeguards system, … The Consultation Group is formed by the end of August 2013 By the end of the Programme, all members of the Consultation Group are satisfied that the TF has taken account of advice from the Consultation Group All Technical Teams are established by the end of September, 2013 By the end of the Programme, all TTs have provided regular technical advice to the TF/CG |
| 1.2 Support to National REDD+ Readiness process | - Baseline: no Secretariat or Advisory Group - By 6/2012 a Taskforce Secretariat is formed - Taskforce Secretariat is able to effectively coordinate and support Taskforce meetings and regular meetings of technical teams - By end 2012 2 capacity building exercises have been carried out with Taskforce, secretariat and government agencies | Baseline: Secretariat established and fully staffed All TF, CG and TT meetings are organized effectively and efficiently By the end of the Programme, members of the TF, CG and TTs are satisfied with the role played by the Secretariat By the end of the Programme, other initiatives (e.g., Cam-REDD, LEAF) are satisfied that the Secretariat has supported the broader REDD+ readiness process in Cambodia |
| 1.3 Stakeholders are engaged in the REDD+ Readiness process | Baseline: Consultation Plan prepared, 4 National Consultation Events - At least 6 consultation events per year - Minutes show that consultations follow the principles in the Roadmap - By 12/2012 a consultation program for the national REDD+ strategy has been developed | Baseline: No effective stakeholder engagement at the beginning of the programme; considerable investment in CG selection during the first 18 months of the programme A survey conducted near the end of the Programme reveals that at least 67% of members of stakeholder groups represented on the CG are satisfied that their views are effectively communicated |
| 1.4 Stakeholders provided with access to information on REDD+ and the National REDD+ Readiness process | Baseline: Khmer awareness-raising materials available, no website - By 09/2012 a REDD+ information and dissemination website has been created - By 09/2012 an awareness raising plan has been developed - By 09/2012 local communication tools have been developed - At least 12 awareness raising events by mid-2013 | Baseline: Information available assumed to be minimal at start of the programme; a survey at the CG selection workshop will establish level of awareness A survey conducted near the end of the Programme reveals that at least 67% of members of stakeholder groups represented on the CG are satisfied that they have access to the necessary information on REDD+ A survey conducted near the end of the Programme reveals that at least 67% of members of stakeholder groups represented on the CG have an adequate understanding of REDD+ |
| 2.1 Development of individual REDD+ strategies and implementation modalities | Baseline: draft REDD+ Strategy in Roadmap - By mid-2013 line agency specific REDD+ strategies have been developed for FA, FiA and GDANCP - By mid-2013 at least four Capacity building activities being carried out for each agency | Baseline: draft REDD+ Strategy in Roadmap By June 2014, draft strategy proposals have been developed for forests under the administration of FA, GDANCP, and FiA A survey conducted near the end of the programme reveals that at least 50% of professional staff of FA, GDANCP, and FiA consider that their agencies have adequate capacities to plan and implement REDD+ actions |
| 2.2 Valuation of co-benefits | Baseline: UNEP-WCMC co-benefits report - By mid-2013 valuation reports are available for four large forested landscapes in the country - By mid-2013 information is available on local opportunity costs of REDD+ versus other livelihood options | Baseline: UNEP-WCMC co-benefits report By September 2014, 50% of professional staff of FA, GDANCP, and FiA have clear understanding on the value of forests under different management regimes By June 2014, 50% of key decision makers and stakeholder groups have a better understanding of the costs of implementing REDD+ activities versus other livelihood options |
| 2.3 Revenue-sharing studies | Baseline: existing pilot projects - By 09/2012 a Benefits Sharing Technical Team is formed - By early 2013 initial assessment of REDD+ fund management options – including legal assessment - By early-2013 an analysis of possible benefit sharing arrangements is complete. - By mid-2013 consultation on different sharing mechanisms is complete. - By mid 2013 – consultation on options completed and plan for fund management developments in place. | Baseline: Benefit distribution process identified in existing pilot projects By the end of 2013, a policy brief on revenue sharing and benefit distribution has been approved by the TF By March 2014, options for revenue sharing and benefit distribution have been produced for broad consultation By the end of the Programme, revised proposals for revenue sharing and benefit distribution have been produced based on results of broad stakeholder consultation |
| 2.6 Safeguards and monitoring of co-benefits | Baseline: No national REDD+ safeguards; Monitoring systems in place in some forested landscapes - By 03/2013 nationally-appropriate safeguards have been prepared - By mid-2013 indicators to monitor co-benefits have been prepared | Baseline: No national REDD+ safeguards; Monitoring systems in place in some forested landscapes By the end of 2013, initial proposals for a nationally appropriate system of safeguards have been produced By June 2014, a revised proposal for a nationally appropriate system of safeguards has been produced, incorporating feedback from broad stakeholder consultation By the end of the Programme, the TF has approved a nationally appropriate system of safeguards |
| 3.1 Development of National REDD+ project guidelines and approval of funding for demonstration sites | Baseline: - By 10/2012 REDD+ Projects Team established - By 12/2012, identification of areas in which sub-national approach should be prioritised - By Mid 2013 - at least two sub-national demonstration sites are under development | Baseline: No REDD+ implementation guidelines exist By the end of 2013, an analysis of options to integrate sub-national approaches within a national REDD+ system has been completed By June 2014, a broad-based consultation process has identified potential options to guide implementation By the end of the Programme, the TF has approved REDD+ implementation guidelines, including sub-national implementation |
| 3.2 Pilot project activities | Baseline: no sales of carbon credits - By end of 2012 2 pilot projects are supported - By mid-2013 at least 2 projects are making sales on the voluntary carbon market | Baseline: Several NGO-driven demonstration projects are under implementation By the end of 2013, at least 5 Policy briefs have been produced and reviewed, or are under review by TTs By the end of the Programme, the TF has approved at least 6 Policy Briefs, methodologies, or other implementation tools developed through UN-REDD Programme funding |
| 4.1 Establishment National MRV/REL Technical Team and build appropriate national capacity | Baseline: no MRV/REL Technical Team, 1 training course held on MRV/REL - By 7/2011 a MRV/REL Technical Team is established. - By 7/2011 MRV/REL advisor is in place - By mid-2013 at least six training courses on MRV/REL have been held |  |
| 4.2 Develop Cambodia Monitoring system plan | Baseline: principles for a Monitoring system plan in Section 6 of the Roadmap - By 03/2013 a national monitoring system is designed |  |
| 4.3 Review of forest cover assessments to provide REDD+ activity data and design the satellite forest monitoring system | Baseline: current forest cover assessments - By end of 2011 the 2010 forest cover assessment is complete - By mid-2013 forest cover data sets have been reanalysed |  |
| 4.4 Design of a National Forest Inventory to develop emission and removal factors for REDD+ related activities | Baseline: principles for a Monitoring system plan in Section 6 of the Roadmap - By end-2012 existing forest carbon stock data has been collected and harmonized - By end of 2012 a national forest inventory system is developed - By 09/2012 a central database is created - By end of 2012 pilot field data collection has been completed |  |
| 4.5 Support the development of a REDD+ related GHG Reporting System | Baseline: only the Department of Climate Change have capacity for GHG reporting - By end of 2012, FA, GDANCP and FiA understand current GHG reporting requirements under the UNFCCC - By mid-2013 capacity for GHG reporting has been established |  |
| 4.6 Support the development of Cambodia RL/REL framework | Baseline: draft report on the Assessment of Land-use, Forest Policy and Governance - By 09/2012 information on drivers is collated - By mid-2013a national RL/REL framework has been developed |  |

# Text boxes

Document 5