|  | Back to Office Report Submitted by Tina Hageberg Title Programme officer (UNDP/UN-REDD) Date submitted 25/1/13 |
| --- | --- |
| 1. Practice area : Environment and Energy & Democratic Governance |
| 2. Mission period (incl. of travel days) From : 14 January to : 19 January 2013 |
| 3. Type of mission : Consultative workshop for the PGA process in Calabar, Nigeria | 4. Clients PGA stakeholders at federal and CRS level, government counterparts in Nigeria |
| 5. Purpose of mission Attend and contribute to the workshop, meet and discuss with national counterparts and agree on way forward (scope, roles of different stakeholders, and next steps) | 6. Documents, materials, resources Workshoph agenda is available here. Workshop report is currently being drafted, but will shortly be available using the same hyperlink |
| 7. Mission members Tina Hageberg and Josep Garí (UNDP/ UN-REDD) Emelyne Cheney and Rabe Mani also attended from FAO’s end* | 8. Costs UNDP/UN-REDD (PGA budget) * covered by FAO |
| 9. Brief summary of the mission This two days workshop is a result of the preparatory work for the PGA in Nigeria until now, building on the initial workshop in May 2011, a Calabar PGA workshop in June 2012 (organized by the Cross River State), and preparatory research being conducted late 2012 to feed into this workshop. In addtion, on the third day, a training on indicator development and data collection methods was held with a smaller number of the workshop participants thought to contribute in the further work related to the development of indicators and data and information collection of the PGA. Workshop participants were CSO and community representatives, government staff ( both from the federal and state level), academia and media. The objectives of this workshop were to: a) raise awareness and ensure the intereset of a larger stakeholder group for the PGA (beyond the intital group that has been working on this until now), b) discuss and agree on the scope of the PGA (i.e. prioritize governance domains), c) agree on immediate next steps and d) to have an organizational structure for the further process with clarity on roles and responsbilities. 9 a Results achieved (key outputs) Key outputs after workshop: Agreement on governance domains that will be prioritized in the PGA in Nigeria An organizational structure of the PGA in Nigeria in place, with clarity on the different roles and responsibilities of the different groups A road map for the next 8 months agreed by the workshop participants, and endorsed by government counterparts at both federal and state level (Cross River State) Draft indicator set (first version, to be further refined) |
| 10. Key counterparts Federal Ministry of Environment, CRS Forestry Commission, NGO community at CRS and federal level, staff from the University of |
| 11. Follow up action matrix |
| Action to be taken | By whom | Expected completion date |
| See agreed next steps on page 2. Most immediate action to be taken is to recruit a full-time PGA coordinator to follow up on the road map. | As highlighted in the plan/ next steps below | As highlighted in the plan/ next steps below |
| 12. Distribution list UNDP UN-REDD team (including regional advisers), OGC all staff and relevant regional governance assessment colleagues. Note that these BTORs will also be posted on the UN-REDD workspace here and thus accessible to all UN workspace users. |

| Agreed next steps for the PGA in Nigeria |  |
| --- | --- |
| Milestones: | Specific activities: | By whom: | By when: |
| Follow-up after the Calabar workshop | Share workshop report with agreements on key governance domains, organizational structure and next steps Share preliminary research report | Workshop team/ PGA coordinator | 4/2/13 |
| Get baseline governance data | Indicator training Develop indicator set Agree on data collection methods and process Information/ data collected Stakeholder validation of the findings | UN-REDD/ FAO Research team proposes, PGA/ REDD+ committee validates/ adopts Research team proposes, PGA/ REDD+ committee validates/ adopts Research team/ data collectors overseen by PGA coordinator PGA/ REDD+ Consultative Network validates, facilitated by PGA coordinator | 18/1/13 18/3/13 18/3/13 18/7/13 End of August |
| Develop a communication strategy | Start discussing the end-users and dissemination of PGA information to ensure this reaches communities in appropriate form/ language | PGA/REDD+ Committee (to be presented to the PGA/ REDD+ Consultative Network) | Continuous work until we have the baseline data |
| Recruit a full-time PGA coordinator (as soon as possible) | Develop ToR Recruitment | Inputs from UN-Nigeria and UN-REDD, to be validated by the PGA/ REDD+ committee UNDP Nigeria/ UN-REDD team | ASAP |