Readiness Preparation Proposal (R-PP) for Country: Bhutan Date of submission or revision: July 2013 #### Version 6 Forest Carbon Partnership Facility (FCPF) The United Nations Collaborative Programme on Reducing Emissions from Deforestation and Forest Degradation in Developing Countries (UN-REDD)

Disclaimer: The World Bank and the UN-REDD Programme do not guarantee the accuracy of the data included in the Readiness Preparation Proposals (R-PPs) submitted by REDD Country Participants and accepts no responsibility whatsoever for any consequence of their use. The boundaries, colors, denominations, and other information shown on any map in the R-PPs do not imply on the part of the World Bank any judgment on the legal status of any territory or the endorsement or acceptance of such boundaries.

Note:  This version is for use by:

1)  FCPF REDD-plus Country Participants submitting revised or new R-PPs to the FCPF FMT for PC 12 meeting in Colombia, June 27 – 29, 2012 or afterwards.

2) UN-REDD countries submitting National Programmes, as agreed.

General Information

# Contact Information

Please provide the details for the national REDD-plus focal points (lead official, and day-to-day contact) submitting the R-PP in the table below.

| Name |  |
| --- | --- |
| Title |  |
| Organization |  |
| Address |  |
| Telephone |  |
| Fax |  |
| Email |  |
| Website |  |

# R-PP Development Team

Please list the names and organizations of the authors and contributors to the R-PP (insert as many rows as necessary in the table below).

| Name | Organization |
| --- | --- |
| Jigme Tenzin | WMD/DoFPS |
| Sigyel Delma | WMD/DoFPS |
| Kinley Tshering | FRMD/DoFPS |
| Kezang Yangden | FRMD/DoFPS |
| Nedup Tshering | Independent consultant |

# Summary of the R-PP

| Dates of R-PP preparation (beginning to submission): | March 2013 – July 2013 |
| --- | --- |
| Expected duration of R-PP implementation (month/year to month/year): | March 2014 – February 2018 |
| Total budget estimate: |  |
| Anticipated sources of funding: | from FCPF: $3,800,000 from UN-REDD: $ 200,000 National government contribution: $ other source: other source: |
| Expected government signer of R-PP grant request (name, title, affiliation): |  |
| Expected key results from the R-PP implementation process: | Outcome 1) Outcome 2) Outcome 3) Outcome 4) |

# Executive Summary

Bhutan is a small mountainous landlocked country located in the Eastern Himalayas. It has a geographical area of 38,394 square km (NSB 2013) and a population of 0.734 million (NSB 2013). The country is characterized by fragile mountainous ecosystems with elevations ranging from about 100 masl in the foothills to over 7500 masl in the north; within a distance of170 km from the northern to the southern border. The most dominant land cover is forest, making up 70.46% of the land area, while shrubs account for 10.43%, and cultivated agricultural land and meadows account for 2.93% and 4.10%, respectively. Snow cover constitutes 7.44% while bare areas constitute 3.20%. Degraded areas, water bodies, built up areas, marshy areas and non-built up areas constitute less than 1% each.

The overall mandate of the 11th Five Year Plan (2013-2018) places a strong emphasis on self-sufficiency and self-reliance through inclusive green socio-economic development through improvement of rural livelihoods and poverty reduction with particular emphasis on addressing multi-dimensional poverty, income inequalities, malnutrition and growing urban poverty. The11th Five Year Plan of Department of Forests and Park Services places a strong emphasis on strengthening forest governance and management through participatory and science based approach to deliver effective services.

In the 11th FYP, all programs has a component of good governance and management of forest strengthened through science based and participatory approach to deliver effective service which will be carried out through participatory by mainstreaming REDD+ into the plans. By end of the 11th FYP, the status of readiness of REDD+ can be achieved through the four pillars of GNH policy of the RGOB i.e.) Promotion of equitable and sustainable socio-economic development, ii) Preservation and promotion of cultural values, iii) Conservation of the natural environment, and iv) Good governance.

Bhutan’s total forest area has expanded slowly over the past 20+ years, as shown by FRA 2010.  Of the total area, 12.7% (413,000ha) is classified as primary forest, a figure that has remained constant. Bhutan has 3,000 ha of planted forest.

Although the net area of forests is increasing, there are areas of local deforestation.  However, most of the relevant drivers are processes leading to forest degradations.  The key processes, acting at landscape scale, are:

- Tshamdro and livestock (livestock grazing in forests)

- Tseri or slash-and-burn agriculture (now banned, but still practiced)

- Forest fire

- Leaf litter collection or sokshing

- Firewood collection

- Timber harvesting

- Poaching and illegal logging

The process leading to the formulation of the R-PP began in 2010 when an initial National REDD+ Seminar was held.  This was a platform to raise awareness of all relevant stakeholders. As a follow up to the seminar, the DoFPS hired a consultant to carry out a REDD+ feasibility study. During the feasibility study, the consultant held a series of consultations with various stakeholders which helped in enhancing knowledge on REDD+ concepts.

In 2011, Bhutan joined the UN-REDD Programme and Watershed Management Division, under the Department of Forests and Park Services, Ministry of Agriculture and Forests was designated as the focal point for REDD+. Since then the WMD began selection of stakeholders and sharing of information process. The aim of the stakeholders’ participation was to determine and identify key stakeholders from sectors that contribute directly or indirectly to drivers of deforestation and forest degradation, as well as those whose support will be needed; to implement actions that are needed to address the problems. The result of this objective evolved into development of REDD+ Technical Working Group, who advised the WMD focal point in selection of the stakeholders as well as the methods of dissemination of information to the grassroots.

Subsequently, numerous stakeholder consultation meetings have been held, together with awareness raising workshops, a National REDD+ Workshop, and a large number of media programmes to raise awareness among all stakeholders.

This intensive process of awareness raising and consultation has results in a number of potential strategy options being identified. The proposed key strategy options and activities will address the direct and indirect causes of deforestation and degradation and to promote conservation, sustainable management of forests, and enhancement of forest carbon stocks, and are consistent with the country’s Eleventh Five-Year Plan (2013-2018).

An estimate of the potential costs and benefits for the emerging REDD+ strategy are extremely speculative at this stage as no details have yet been prepared for pilot sites where interventions will be tested and potential reductions in carbon dioxide emissions assessed. Pilot activities which will be supported during the readiness phase will help to identify optimal REDD+ intervention strategies.  Such pilots include:

Community Forests: There are now almost300 CFs in Bhutan covering 32,200 ha reaching 13,000 households. The CFs will be an easy pilot to ensure multiple benefits for local livelihoods, conservation and biodiversity. As the CFs are mostly relatively small in area it would be an option to aggregate a number of CFs in a Dzongkhag to reach more household and at the same time build a better economy of scales and learn from the set-up with geogs and Dzongkhags involved in the institutional set-up.

Protected Areas: As more than half of Bhutanese territory is under protected area status there is ample scope for trialing REDD+ in a National Park or other protected area. Revenues could be used for community support and park management enhancement.

Forest Management Units (FMUs): There is good scope for improvement of forest management towards standards that were initially aimed at in the FMU plan, leading to SFM and better stock enhancement. Improvement of the management of the FMUs would also be instrumental in improving the present apparent imbalance between timber supply and demand in the long run, although on a shorter term this might imply decrease of production volume and an increased imbalance between demand and supply of timber and fire wood.

Landscape and Market Approaches: The Bhutanese mountainous landscape offers a good opportunity to follow a landscape approach, making use of the natural ecosystem boundaries and structure.

Regarding financial management and benefit distribution, Bhutan has a long-standing and very successful trust fund, the Bhutan Trust Fund (BTF).  One option for management of REDD+ finance would therefore be to establish a REDD+ sub-fund under the BTF.  Alternatively, a new REDD+ fund could be established.  These and other options will be examined during R-PP implementation.

Bhutan has some experience with benefit sharing under PES schemes.  A PES Feasibility Study was undertaken by FAO in 2009.  The study identified certain positive conditions for implementation of PES in Bhutan.  For example, there is political will and enabling laws and policies which include specific references to PES as a mechanism for benefit-sharing and more decentralized investment in NRM. The Feasibility Study recommended piloting PES for three different ecosystem services in three locations in the country.  The Wang Watershed was proposed as a pilot of payment for hydropower services; the headwaters of the water system of Mongar were proposed as a pilot of payment for drinking water services, and the Phobjikha valley was proposed as a pilot for ecotourism services.  The drinking water pilot at Mongar began implementation at the beginning of 2011, while arrangements for the ecotourism pilot in the Phobjikha Valley are well advanced.

RELs/RLs will be developed in such a way that ensures GHG emissions and removals are directly comparable to the emissions and removals in the national forest monitoring system component, using the same metrics to ensure consistency between RELs/RLs and the national forest monitoring system (see Component 4). Key features of the development of Bhutan’s RELs/RLs will be:

- Methodological consistency: to ensure comparability of all future RELs/RLs;

- Transparency: to ensure that all relevant stakeholders, including those in the international community, have full access to the process and information used in the development of RELs/RLs.

The first step towards the development of Bhutan’s national forest monitoring system will be the determination of transparent and effective institutional arrangements for 1) the production and sharing of land use monitoring and forest carbon stocks data, 2) compilation of the national GHG inventory for the LULUCF sector, and 3) compilation and reporting of the National Communication to the UNFCCC. Transparent and accountable institutional arrangements will be essential to ensure the effective functioning of the system; the Government of Bhutan will therefore aim to formalize these arrangements through a legal act to ensure long-term accountability and sustainability of the national forest monitoring system.

In order to specify in detail the steps that Bhutan will take to develop and implement its national forest monitoring system, the Forest Department will lead on the formulation of a National Forest Monitoring System Action Plan (NFMS-AP) document. This document will set out the actions that the country will undertake, in the context of the provision of adequate and predictable support, including financial resources and technical and technological support, to implement its national forest monitoring system for REDD+ activities.

One method which will be used to share forest monitoring data and information at the national and international level will be a web-GIS portal, through which any internet user will be able to view forest information through an GIS mapping interface, including viewing of forest areas and types, deforestation statistics, forest governance structures, etc.

Regarding safeguards and monitoring of co-benefits, the aim is to have a unified monitoring system that covers changes in forest composition and carbon stocks as well as co-benefits and social and environmental impacts to ensure compliance with safeguards. Data on changes and improvements to livelihoods and other co-benefits resulting from REDD+ interventions will be collected by relevant government agencies and, where appropriate and feasible, local communities and the private sector. Once evaluated, results will be posted on the web-GIS forest monitoring portal. Preliminary potential indicators that may be considered to identify to use and assess REDD+ co-benefits have been identified.

SESA will be carried out during the Readiness phase which will include stakeholder analysis, description of the initial social and environmental situation of the forestry sector in Bhutan, analysis of the possible impacts of different REDD+ strategy option scenarios, analysis of impacts of different REDD+ alternatives, and development of an Environmental and Social Management Plan (ESMP). Tasks to be conducted during the Readiness phase will include 1) scope of assessments and baseline analysis; 2) measures for impact mitigation and efficiency improvement. The results from SESA analysis will be used to suggest measures for negative impact mitigation and efficiency improvement for positive impacts in REDD+ strategy options; the suggestions will include the revision of REDD+ strategic options; the revision of rules and regulations together with institutional management; terms/conditions of REDD+ project implementation and stakeholder participation, 3) monitoring framework: and 4) reporting: the results and conclusions from SESA will be subject to broad consultation and validation and the report disseminated to all relevant stakeholders.

# Acronyms used in the R-PP

# Many missing!

| AAA | Adaptation Action Areas |
| --- | --- |
| ACM | Anti Corruption Measures |
| BAP | Biodiversity Action Plan |
| BDS | Benefit Distribution System |
| CBD | Convention on Bio-Diversity |
| CC | Climate Change |
| CF | Community Forestry |
| CITES | Convention on International Trade in Endangered Species |
| Common Approach | The Common Approach provides an overarching framework for the World Bank and development agencies to be Delivery Partners to provide R-PP Formulation and/or Preparation grants to FCPF REDD Country Participants. |
| COP | Conference of the Parties |
| CORRB | Council for Renewable Natural Resources Research of Bhutan |
| DEC | Dzongkhag (District) Environment Commission |
| DNA | Designated National Authority |
| DOFPS | Department of Forests & Park Services |
| ESMF | Environmental and Social Management Framework |
| FAO | Food and Agriculture Organization |
| FCPF | Forest Carbon Partnership Facility |
| FMU | Forests Management Unit |
| FYP | Five Year Plan |
| GCCA | Global Climate Change Alliance |
| GDP | Gross Domestic Products |
| GHG | Greenhouse Gas |
| GLOF | Glacial Lake Outburst Flood |
| ICIMOD | International Centre for Integrated Mountain Development |
| INC | Initial National Communication to the UNFCCC |
| IPCC | Intergovernmental Panel on Climate Change |
| IPNM | Integrated Plant and Nutrient Management |
| M &E | Monitoring and Evaluation |
| masl | Meters above sea level |
| MoAF | Ministry of Agriculture and Forests |
| MRV | Measurement, Reporting and Verification System |
| MRV | Measurement, Reporting and Verification |
| MSTCCC | Multi Sectoral Technical Committee on Climate Change |
| NAPA | National Adaptation Program of Action |
| NCCC | National Committee on Climate Change |
| NEC | National Environment Commission |
| NFI | National Forest Inventory |
| NFMS | National Forest Monitoring System |
| NGO/CSO | Non-Governmental Organization |
| NPM | National Park Management |
| NWFP | Non-wood Forest Products |
| PLAMS | Planning and Monitoring System |
| QA/QC | Quality Assurance and Quality Control |
| REDD | Reducing Emissions from Avoided Deforestation and Forest Degradation |
| REDD+ | Policy approaches and positive incentives for issues relating to reducing emissions from deforestation, reducing emissions from forest degradation, conservation of forest carbon stocks, sustainable management of forests and enhancement of forest carbon stocks |
| REL/RL | Forest Reference Emission Level / Forest Reference Level |
| RGoB | Royal Government of Bhutan |
| RNR | Renewable Natural Resource |
| SAPA | Sectoral Adaptation Plan of Action |
| SESA | Strategic Environmental and Social Assessment. |
| SFM | Sustainable Forest Management |
| SLM | Soil and Land Management |
| SLMS | Satellite Land Monitoring System |
| SNC | Second National Communication to the UNFCCC |
| ToR | Terms of Reference |
| UNCBD | United Nations Convention on Biological Diversity |
| UNCCD | United Nations Convention to Combat Desertification |
| UNFCCC | United Nations Framework Convention on Climate Change |
| UN-REDD | UN-REDD Programme |
| WMD | Watershed Management Division |

# Glossary of Bhutanese terms

Dzongkhag		District or province

Gewog			Sub-District

Chiwog			Local area

Gup			Geog Head

# Component 1: Organize and Consult

## 1a. National Readiness Management Arrangements

# Rationale

Bhutan is a small mountainous landlocked country located in the Eastern Himalayas. It has a geographical area of 38,394 square km (NSB 2013) and a population of 0.734 million (NSB 2013). The country is characterized by fragile mountainous ecosystems with elevations ranging from about 100 masl in the foothills to over 7500 masl in the north; within a distance of170 km from the northern to the southern border. The most dominant land cover is forest, making up 70.46% of the land area, while shrubs account for 10.43%, and cultivated agricultural land and meadows account for 2.93% and 4.10%, respectively. Snow cover constitutes 7.44% while bare areas constitute 3.20%. Degraded areas, water bodies, built up areas, marshy areas and non-built up areas constitute less than 1% each.

Environmental conservation constitutes an important part of Bhutan’s national spatial planning strategic framework and has always enjoyed a high priority on the country’s development agenda. Conservation of the environment has been robustly pursued even as Bhutan, a least developed country, is compelled to make short term sacrifices to serve the long term interests of not just the country alone but the region and world at large. It is this unwavering commitment to environmental conservation and sustainability that has brought widespread global recognition for Bhutan’s efforts to protect its environment and natural resources. The strong emphasis on protecting and conserving the environment is reflected in the 11th Five Year Plan, as well as in the last 10 plans. Indeed, the environment sector will require more attention than before in view of the accelerated pace of economic and development activities accompanied by increased expansion of infrastructure development, urbanization, industrialization, population expansion and consumption patterns that are likely to put an even greater burden and stress on the natural environment.

# National Policies and Legislation for Environmentally Sustainable Development

In the current state, Bhutan`s protection and conservation of the environment and the safeguarding of forest and wildlife is ensured under the Constitution of the Kingdom of Bhutan Article 5. The Constitution directs every Bhutanese citizen to protect environments and natural resources. The constitution under Article 5, section 2(d) mandates Bhutan to maintain 60% forests cover all the time. Over the years, set of strong laws and policies have evolved to ensure the protection, management and sustainable use of GRFs. These legislations are essentially geared towards contributing towards the development philosophy of Gross National Happiness (GNH). The constitution of Kingdom of Bhutan as mentioned earlier enshrines environmental conservation as constitutional mandates and Bhutan 2020, the country`s vision document to maximize the GNH, serve as principal policy instruments.  To harmonize these two documents several laws and policies exit related to GRFs conservation in the country.

The policies and legislations are translated and implemented by the Government through the Five year plans. The current five year plan (10th FYP (2008-2013) will end in June, 2013. The 11FYP, which is currently in draft form, will begin implementation in July, 2013 after being endorsed by the Government.

The overall mandate of the draft 11th Five Year Plan (2013-2018) places a strong emphasis on self-sufficiency and self-reliance through inclusive green socio-economic development through improvement of rural livelihoods and poverty reduction with particular emphasis on addressing multi-dimensional poverty, income inequalities, malnutrition and growing urban poverty. The Department of Forests & Park Services has proposed three programs in the 11th Five Year Plan which are:

- Sustainable Management of Government Reserve Forests (GRF)

- Sustainable management of forest landscapes and conservation of biodiversity

- Scientific information system for effective service delivery and resource management

The 1st program of the DoFPS is geared towards sustainably managing Bhutan’s forest resources to meet the long term needs of the society through a wide range of social, economic and environmental goods and services as required by the National Forest Policy of 2011. Production forests will be brought under sustainable management to ensure sustainable supply of timber and other forest products.  Forest Management Code of Bhutan, 2004 provides codes of best practices for management planning and implementation of these areas.  The Forest Resources Potential Assessment carried out by the Department will help identify potential production areas and define specific criteria to delineate them as forest management units or working schemes. At the local level, community forests will be increased to empower rural communities and accrue socio-economic benefits at local level from forests. While Forest Management Units (FMUs) & Working Schemes (WS) cater to the demand of timber for domestic and commercial purpose, the community forest and Non wood forest produce management groups also help in uplifting the living standards of the rural people through sale of forest produce and non-wood forest produce from their managed area.

The 2nd program has been designed to balance the conservation and livelihood needs of the communities living inside PAs and critical watershed landscapes. The activities are oriented to support communities by introducing the basic developmental needs in their far flung rural areas so that Department can garner their support for the conservation initiatives. This would in the long run benefit the communities themselves but they need to be convinced with the promising initiatives. These initiatives will be backed by surveys and studies as planned.

Protected areas in Bhutan have been considered as water towers for our big hydro power projects and the source for the clean drinking water. The watershed areas need to be protected in order to have continuous and maintained volume of water flow as this is the only cheap natural resource that generates the huge revenue for the country.

The 3rd program is geared towards information management for effective service delivery. Forest resources utilization is foreseen to increase in the 11th FYP period and consequently present the evident risk of unsustainable and over exploitation of these resources. To adequately address this risk, participatory and science based approaches and interventions will be formulated and implemented. An effective and efficient service delivery mechanism is also absolutely necessary to avoid such risks and importantly, facilitate equitable and fair allocation of resources. The program will look into providing congenial working conditions to field offices by keeping provisions for adequate infrastructure, mobility services and opportunities for capacity development. The department also identifies the lack of adequate reliable data in the current scenario as a setback in formulating programs to improve resource management. In the 11th FYP, under this program, emphasis will also be given to improving the existing system of information management which entails collection, compilation,

# Table 1a-1: Plan Target baseline (source: Draft 11th FYP of DOFPS 2013)

| Result (Outcome) | Indicator | Unit | Baseline | 11th Plan Target |
| --- | --- | --- | --- | --- |
| Program 1: Sustainable management of Government Reserve Forests |  |  |  |  |
| Improved management of GRF for sustainable production of economic goods and services to reduce poverty | Forest area under sustainable management increased | Ha | 184610.67 | 218541.96 |
|  | Areas under afforestation and reforestation increased | Ha | 24404 | 26658 |
|  | Proportion of Nature Based Tourists increased through Nature Recreation and Community Based Ecotourism | % | 19 | 35 |
|  | Proportion of Wood recovery increased by using upgraded technology in forest based enterprises | % | 59-64 | 70-75 |
|  | Income from sale of forest products from CF & NWFP groups increased | Nu. Per household(annually) | 2000 | 4000 |
| Program 2: Sustainable management of forest landscapes and conservation of biodiversity |  |  |  |  |
| Sustainable management of forest landscapes and biodiversity conservation enhanced to improve ecosystem services, natural habitats and maintain species persistence | Landscapes brought under Integrated Water Resource Management Plan | No | 2 | 11 |
|  | Conservation plans for Endangered and Endemic Species developed | No | 1 | 5 |
|  | Forest Areas of Natural, Historical or Cultural significance identified and established as Heritage Sites/Reserves | No | 9 | 56 |
|  | Human Wildlife Conflict incidences reduced | No | 162 cases in a year | 50 cases in a year |
|  | Protected areas managed based on functional zones to integrate conservation and development” | Nos | 3 | 10 |
| Program 3: Scientific information system for effective service delivery and resource management |  |  |  |  |
| Service delivery enhanced through establishment of improved infrastructure and information management system | Participation of local communities and institutions in forest management and conservation increased | % | 28 | 50 |
|  | Experimental or observatory plots in different ecological zones established | Number | 0 | 10 |
|  | Forest Protection & service delivery improved | Rating | Medium | High |
|  | Forest information system strengthened | No | 1 | 3 |

REDD+ activities cut across all three programs of the DoFPS but REDD+ is explicitly mentioned in program 1 under output 7, which is titled “REDD+ Readiness activities initiated”. The Department expects to be ready for implementing the REDD+ activities by the end of the 11th FYP in 2018.

The Department of Forests and Park Services will be focusing on key strategies based on the National Forest Policy, 2011 for implementing the 11th Five Year Plan. Some of the key strategies/goals would be:

- Strengthening the rights, responsibilities and capacities of local communities to regulate access and sustainable use of forest resources through decentralization and devolution of management authority from central government to local communities and promote good governance

- Manage forests based on the principles of good governance to ensure transparency, accountability, participation, empowerment and equity and benefit sharing

- Carry out research to generate knowledge, information and technology to support policy implementation and development including integration of climate change issues through dedicated research programme

- Capacity building of all stakeholders for successful implementation of activities

The implementation of the 11FYP will be carried out in coherence with the National Forest Policy of 2012. The Department has developed various strategies, road maps and documents for carrying out the planned activities/programs. The implementation of the activities are to be carried out by the field divisions(Territorial Divisions, Parks, Dzongkhag Forestry Sector) in collaboration with other relevant stakeholders. It is the responsibility of the respective head of the agencies to implement the activities. Since most of the activities are co-ordinate by the central level, it is the responsibilities of the central agencies to see all the activities in the field are going on well technically and on time.  Monitoring and evaluation of the field works are to be carried out quarterly/as and when needed. Technical backstopping the field offices are to be provided by the functional divisions. The concerned division shall closely liaise with other relevant stakeholders information sharing are to be encouraged.

# Bhutan and International Conventions

Bhutan is a party to the United Nations Convention on Biological Diversity (UNCBD), United Nations Framework Convention on Climate Change (UNFCC), United Nations Convention to Combat Desertification (UNCCD), and United Nations Convention on International Trade in Endangered Species of Wild Flora and Fauna (CITES). Bhutan committed to remain carbon neutral at the UNFCCC’s 15th Conference of the Parties (COP 15) in Copenhagen. Being a party to these international conventions, national policies and other legal instruments are steered towards addressing Bhutan’s international commitments.

Bhutan’s Second National Communication (SNC) Report is the country’s most recent official communication to the UNFCCC and provides a comprehensive report of actions taken by Bhutan as required under the UNFCCC, including an assessment of national circumstances related to climate change and the implementation of climate change-related policies, vulnerability to climate change, capacity building and technology needs. The SNC also includes a national greenhouse gas (GHG) inventory which details the gains and losses of GHGs from all sectors of the economy. Bhutan’s National Adaptation Program of Action (NAPA 2012) is a report of prioritized adaptation activities/actions that are needed to address the impacts of climate change. The activities focuses mainly on landslide management and flood prevention, reducing disaster risks through intervention and providing emergency medical services to vulnerable communities and enhancing the national capacity for weather and seasonal forecasting in Bhutan.

# Strategies and Programs for  Sustainable resources management

# Protected Areas

In 1966, the country’s first protected area was established. It was the Royal Manas National Park and is situated in central south part of Bhutan. The concept of a national protected areas system was introduced in 1974 when eight additional protected areas were declared in the northern and southern parts of the country. This was followed by addition of another five more protected areas in 1983. In the same year, three protected areas in the north were consolidated to form JigmeDorji Wildlife Sanctuary covering the entire northern part of the country. Today, Bhutan has ten protected area and biological corridors with an area of 19,676.57km2.

# Table 1a-2: Protected area and Biological Corridors

|  | Area in km2 | Percentage |
| --- | --- | --- |
| Total Protected areas System | 16,396 | 43 |
| Total Area Biological Corridors | 3,307 | 9 |
| Royal Botanical Park | 47 | 0.1 |
| Total PAs and BCs | 19,704 | 51 |

# Forest Management Units

Scientific management of forests in Bhutan started in 1965 with preparation of first management plan. The management division was first established in 1971. In 1974 a new method of management plan was formulated, and subsequently the Division was then changed to Forest Resources Development Division in March 2000. Recently the Division was renamed as Forest Resources Management Division (FRMD) keeping in with current priorities and functions. Scientific management of forests is progressively being achieved through identification and establishment of Forest Management Units (FMUs) and managing them under a prescription of written management plan.

The Forest Management Units(FMUs) are for implementing long-term sustainable forest management plans over10 years, which can be extended. However,it has been observed, that implementation of these forest management plans is often not sustainable as the annual allowable cut (AAC)is regularly surpassed and the standing stock impoverished by uncontrolled timber extraction and grazing damage. This often results in limited regeneration and insufficient standing timber stocks to continue sustainable extraction, in turn resulting in forest clearing (deforestation) and forest degradation.  There are currently 17 FMUs in Bhutan, covering an area in excess of 250,000ha.

# Community Forests

The Forest and Nature Conservation Act, 1995, recognized community forests and the subsequent Community Forest Rules established procedures for their creation and management. Under the community forest rules a group of at least ten households willing to establish, control and manage a forest area as a community forest in accordance with these rules can form a community forest management group (CFMG). The CFMG is authorized under the rules to control the management of the community forest in accordance with the management plan prepared by the CFMG and approved by the dzongkhag administration on the recommendation of the Divisional Forest Officer (DFO). The management plan needs to contain maps of the boundary and various compartments, management objectives, descriptions of forest types and species, an assessment of the forest condition and an inventory of the forest areas. It is often difficult for local people to provide such information for a management plan. Rules provide for no royalty for the bonafide use of forest products from the community forest by the CFMG members.

Since the decentralization of forestry activities in 1990s, under the guidelines on Decentralization of Forestry Activities to Dzongkhags (1993), community forestry is administered in a decentralized fashion, representing a significant shift in the focus of power for major decision making from government to local communities.  CFs are rapidly growing in number, with now almost there are 510 CFs with 224,491 households and area of 57,825 hectares.

CF is expected to be seen as a practical expression of decentralization and an approach for improving the governance of natural resources at the local level. One of the underlying faiths of Community Forestry is that forest resources will be managed sustainably andhuman well-being will be enhanced, and in the long term, it is expected to contribute to the philosophy of Gross National Happiness.

# National Climate Change and REDD+ Framework

The National Environment Commission (NEC) is the national focal point for climate change. The NEC also acts as the Designated National Authority (DNA) for the Clean Development Mechanism (CDM) of the Kyoto Protocol. The NEC does not have a department dedicated to climate change, nor staff assigned on a full-time basis to climate change issues. The Initial National Communication (INC)to the UNFCCC (2000) was prepared by the NEC, which then formed the National Climate Change Committee (NCCC), a technical level task force.

Recently, the National Climate Change Committee as a technical task force has developed the Sectoral Adaptation Plan for Action (SAPA) that will serves as the strategic plan for climate change adaptation mainstreamed into the Vision 2020, the RNR 11th FYP and coincides with the objectives of the Bhutan National Adaptation Programme of Action (NAPA 2012). SAPA is prepared through extensive stakeholder consultations in order to integrate climate adaptation options into sectoral programs and sub-programs of the MoAF.

This Sector Adaptation Plan of Action (SAPA) focuses on coping and dealing with the consequences of Climate Change, such as how much the temperature will affect the glaciers, how much rainfall patterns will be affected, and how much such changes will affect livelihoods and the natural ecosystems that sustain these livelihoods.

The purpose of SAPA is:

- To implement RNR adaptation plans that are vibrant for responding to changing and uncertain climatic conditions;

- To inform and facilitate RNR Sectoral programs working towards the integrated approaches among various programs and sub-programs; and

- To create awareness among the communities in understanding the changing futures climatic conditions and engage them effectively in the process of developing adaptation activities

Two government agencies are pivotal for the implementation of REDD+ activities in Bhutan. The Watershed Management Division (WMD) of the Department of Forests and Park Services (DoFPS) of the Ministry of Agriculture and Forests (MoA), have the mandate within the Renewable Natural Resources (RNR ) sector on climate change related issues. WMD is the focal agency for Bhutan for the UN-REDD Programme. The National Environment Commission (NEC) is the focal agency for Bhutan for the UNFCCC and responsible for the national communications and the adaptation and mitigation National Action Plans. The WMD has already established a REDD+ Technical Working Group and is in the process of establishing a  REDD+ Task force. The REDD+ TWG will assist the the WMD in preparing and developing a  Readiness Preparation Proposal for Bhutan and also guide the REDD+ Secretariat in preparing for implementation of REDD+ program. Technical experts from these agencies will have to feed members of delegations to UNFCCC COPs information on REDD+ issues and the status of implementation in Bhutan.

A multi-sectoral Technical Committee on Climate Change (MSTCCC) is represented from several government agencies, NGOs and Associations (NAPA 2012). The MSTCCC is a group of members represented from different agencies and meet whenever needed as and when required to tackle climate change issues.  For example, the MSTCCC was responsible in assisting the national while developing the NAPA 2012, Sectoral Adaptation Plan of Action (SAPA) and SNC.(seeFigure 1a-1).

Chair (National Environment Commission)

Member Secretary (NEC)

Members of MSTCCC are representatives from

- National Environment Commission

- Ministry of Foreign Affairs

- Ministry of Works & Human Settlement

- Department of Energy

- Department of Forests and Park Services

- Department of Disaster Management

- Department of Geology and Mines

- Ministry of Foreign Affairs

- Watershed Management Division

- Tarayana Foundation (NGO)

- RSPN (NGO)

- Ministry of Information & Communication

- Gross National Happiness Commission

- Association of Business Industries

- Department of Agriculture

- Department of Livestock

Figure 1a-2. Multi-Sectoral Technical Committee on Climate Change

Ministry of Agriculture & Forests

# Existing Institutional Arrangements relevant to REDD+ Readiness

The existing institutions for REDD+ and their roles and responsibilities are listed below.

Gross National Happiness Commission: GNHC is the central government body for coordinating and spearheading policy formulation, and ensures that all policies are processed in line with the Protocol for Policy Formulation. It also directs and coordinates the formulation of all policies, plans and programmes in the country and ensures that GNH is mainstreamed into the planning, policy making and implementation process by evaluating their relevance to the GNH framework. GNHC also reviews sectoral policies and plans and finalizes plans for government approval. The sectoral plans are submitted to the GNHC to ensure coherence of policies to promote performance and growth, and is compiled by GHNC as a National Planning Document which is in the form of five year plans..

Ministry of Agriculture and Forests (MoAF): The Ministry of Agriculture was established in 1985, bringing together agriculture, livestock and forestry sub-sectors (known as renewable natural resources (RNR) sector). It plays a significant (dominant) role in the economic development of the country through enhancement of food self-sufficiency, raising farm income and pursuing sustainable management of natural resources. The RNR sector (agriculture, livestock & forestry) provide livelihood to c. 66.6 percent of the population (NSB, 2007).  The ministry constitutes of four main departments namely Department of Agriculture, Department of Forests & Park Services, Department of Livestock and Department of Agriculture marketing and Cooperatives. Apart from the above four departments, there are two non-departmental organizations under the Ministry namely BAFRA ( Bhutan Agriculture and Food Regulatory Authority and National Biodiversity Center ( NBC).

. DOFPS is the main custodian of the Government Reserve Forests (GRFs) of the country and is the main agency responsible for developing and implementing strategies and policies for conservation and sustainable management of GRFs. It is also entrusted with the responsibility of managing and allocating resources for the forestry sector. DoFPS implements its various GRF-related programs through its functional division and field division offices located around the country. There are six functional divisions under DoFPS, which contribute to the conservation and sustainable management of GRFs in the country. Watershed Management Division (WMD) is one of the six functional  divisions under the DoFPS and is responsible for carrying all watershed plans and activities within the country.

The mandate of WMD are given below:

- Plan, coordinate, monitor and report nation-wide watershed management activities

- Coordinate RNR sectoral roles and responsibilities related to environment, climate change including enhancement of information and research to support policy implementation and development

- Pursue innovative financial and institutional mechanisms for participatory and integrated watershed management, including options for payment of ecosystem services (PES), and develop appropriate modalities.

Recently, WMD has been designated as the REDD+ Secretariat and will be responsible for screening all REDD+ related projects for which they will function as the Competent Authority and is also responsible for periodic environmental monitoring for compliance and final environmental monitoring.

National Environment Commission (NEC): The NEC was established in 1989 by His Majesty the fourth king as a national environmental committee under the Planning Commission (PC). In 1992, it was delinked from the PC and became an autonomous government body. It was further empowered in 1998 with responsibility as a high-level policy decision making body on matters related to environmentally sustainable development and the development of measures to integrate environmental management into the overall development process. It has the overall responsibility for formulation and implementation of environmental laws. Currently it is the national focal agency for UNCBD and UNFCCC. Through close collaboration with the legal office, it is empowered to develop, revise and amend environmental laws and regulations. It also prepares the country’ s documents to facilitate the ratification of international treaties and conventions.

# Non-Governmental Organization (NGO) Institutional Arrangement

Bhutan Trust Fund for Environmental Conservation (BTFEC): BTFEC was established in May 1996. The trust fund was legally incorporated in Bhutan under Royal Charter. Today, it is an effective conservation grant-makingorganisation autonomous of the government. The trust fund is governed by the Royal Charter of 1996 and a high-level Management Board that was fully Bhutanised in May 2001.

The BTFEC is represented in the REDD+ TWG as part of the technical advisory group to the REDD+ Secretariat.

Royal Society for Protection of Nature (RSPN): In 1987, the Royal Society for Protection of Nature was established as a citizen based non-profit, non-governmental environment organization to support environment conservation in Bhutan. RSPN works on environmental education and advocacy, conservation and sustainable livelihoods, research and emerging issues like climate change, solid waste and water. Regular advocacy programs on emerging environmental problems are also carried out with the help of local volunteers, stakeholder organisations, partners and members.

The RSPN is represented in the REDD+ TWG as part of the technical advisor body to the REDD+ Secretariat.

# REDD+ Readiness Institutional arrangements in Bhutan

# Institutional arrangements for management of REDD+ readiness in Bhutan are show in Figure 1a-3.

The recently-established TWG will be upgraded to a REDD+ Taskforce.  Members of the Taskforce will be:

- Social Forestry and Extension Division, Department of Forests and Park Services

- Forest Resources Management Division, Department of Forests and Park Services

- Wild Life Conservations Division, Department of Forests and Park Services

- Nature Recreation & Ecotourism Division, Department of Forests and Park Services,

- Ministry of Finance,

- Gross National Happiness Commission,

- Department of Livestock

- Royal Society for Protection of Nature (NGO)

- Bhutan Trust Fund for Environmental Conservation (NGO)

- Natural Resources Development Corporation Limited

- National Environment Commission

- College of Natural Resources, Royal University of Bhutan

The two NGO representatives were identified through a self-selection process, designed and managed by the NGO community.

The REDD+ Taskforce oversees the work of three Technical Working Groups.  The three groups are:

- TWG on NFMS and RELs/RLs

- TWG on Safeguards, Governance and Benefit Distribution

- TWG on Strategy Options

# ToR for the Taskforce and the three TWGs are found in Annex 1a-x.

National REDD+ Taskforce

R-PP Executive Board

TWG Strategy Options

TWG NFMS & RELs

TWG Safeguards, Governance & BD

MSTCCC Chaired by NEC)

WMD/REDD+ Office as Secretariat

R-PP Implementation (and other related initiatives)

DG, DoFPS

MoAF

# Figure 1a-3: Institutional arrangements for REDD+ readiness

The Watershed Management Division of the DOFPS will serve as Secretariat to the Taskforce, pending the establishment of a longer-term REDD+ Office. The Chief Forest Officer of WMD will head the REDD+ Secretariat. The main tasks of the WMD, and subsequently the REDD+ Office, will include:

- Manage the facilitation and management of all REDD+ readiness activities;

- Plan and implement the R-PP;

- Coordinate and lead capacity building efforts through workshops, seminars and other media such as local radio, television for REDD+ readiness;

- Coordinate and participate in international REDD+ dialogues and provide information and material for Bhutan to the Chairman of the National Environment Commission during the negotiation at the International forum such as COPs

- Document all progress made for REDD+ implementation in collaboration with the TWG and MSTCCC members to be submitted to the DOFPS

- Disseminate all information on REDD+ readiness.

The Chair of the REDD+ Taskforce (self-selected among its members) will report to the DG of DoFPS.  The DG will be responsible for reporting both to the MoAF and to the MSTCCC.

REDD+ readiness in Bhutan will be supported by a number of internationally-funded initiatives chief among which is the FCPF.  Implementation of the R-PP, and coordination with other initiatives, will be the responsibility of the WMD, and subsequently the REDD+ Office.  An R-PP Executive Board will be established to oversee implementation of the R-PP and to facilitate coordination with other initiatives.  Members of the R-PP Executive Board will include representatives of key governmental and non-governmental stakeholders, and of relevant Development Partners.

# Consultations and Grievance Recourse Mechanisms

Broad stakeholder consultations will be inbuilt in the national REDD+ planning and implementation process .A feasibility team will conduct and record consultations with relevant stakeholders including local-level organizations, communities, forest user committees or water-user committees, schools/clubs and other stakeholders as part of the assessment. During implementation, the site supervision team will consult regularly with the impacted people/communities as well as local stakeholders for their observations and feedback. A monitoring team from Dzongkhag or from WMD, MOAF or NGOs will periodically consult with these stakeholders during implementation.

For the grievances, the REDD+ implementation staff at the local level will keep a feedback register and inform local stakeholders that they may register their complaints, comments and/or suggestions related to REDD+ implementation. The REDD+ implementation staff members will review the feedbacks and take appropriate action. Complaints may also be registered at the gewog/Dzongkhag government offices. The gewog will take up these complaints with the REDD+ implementation team and forward the complaints to Dzongkhag.

The complainant(s) will have the option of filing the case with the Dzongkhag administration or even to court. All stakeholders will be fully and freely informed of their rights and the grievance process prior to the implementation of activities.

# Social Grievance Redress Mechanism:

Bhutan has an existing robust grievance redress system. Any issue on grievances are verified at the gewog level by the gup (gewog leader). The most serious grievance issues are put up to Ministry of Home and Cultural Affairs by the Dzongkhag, which can subsequently be forwarded to His Majesty’s Secretariat for Compensation.  Informal traditional dispute mechanisms, based primarily on negotiations between aggrieved parties and through community meetings to reach consensus on a satisfactory resolution, are therefore already practiced in Bhutan. These traditional dispute practices appear to function well and are generally accepted by all community members as a satisfactory means for resolving disputes and grievances. The implementation of REDD+  make use of these existing systems for addressing grievances. However, to make the grievance redress process more systematic, but still working within traditional community norms and practices, aggrieved parties will follow following steps:

- Any complaining parties will submit a formal complaint to the Tshogpa of the Chiwog for consideration;

- If it cannot be resolved within the jurisdiction of the Tshogpa of the Chiwog, the grievance case will be submitted to the GT. The GT will review the grievance case and call a public hearing;

- Where the complainant does not agree with the recommendation of the public hearing, he or she can file the case with the Dzongkhag Administration for review and intervention. The Dzongkhag Administration will review the case and make recommendations to resolve the case;

- The complainant can always file his or her case in court at any time, where the case will be reviewed and settled.

Any appeals to the above-mentioned committees will be recorded in a register, identifying the name of the aggrieved party, date of grievance registered, nature of the grievance, and measures suggested to address the grievance, including escalating resolution of the grievance to MoAF or RGoB for recourse through traditional judicial practices, and date of grievance redress.

[Please include each component's standard box like this one in your submission]

Standard 1a the R-PP text needs to meet for this component:

National Readiness Management Arrangements:

The cross-cutting nature of the design and workings of the national readiness management arrangements on REDD-plus, in terms of including relevant stakeholders and key government agencies in addition to the forestry department, commitment of other sectors in planning and implementation of REDD-plus readiness. Capacity building activities are included in the work plan for each component where significant external technical expertise has been used in the R-PP development process.

| Table 1a: Summary of National Readiness Management Arrangements Activities and Budget (and hypothetical example) |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Main Activity | Sub-Activity | Estimated Cost (in thousands US$) |  |  |  |  |
|  |  | 2014 | 2015 | 2016 | 2017 | Total |
| REDD-plus Working Group management | Meetings (e.g., travel for stakeholders on WG) |  |  |  | $ | $ |
|  | Dissemination of reports |  |  | $ | $ | $ |
| Hire 2 staff for working Group | Hire information specialist | $ | $ | $ | $ | $ |
|  | Hire economist | $ | $ | $ | $ | $ |
|  |  | $ | $ | $ | $ | $ |
|  |  | $ | $ | $ | $ | $ |
| Total |  | $ | $ | $ | $ | $ |
| Domestic Government |  | $ | $ | $ | $ | $ |
| FCPF |  | $ | $ | $ | $ | $ |
| UN-REDD Programme (if applicable) |  | $ | $ | $ | $ | $ |
| Other Development Partner 1 (name) |  | $ | $ | $ | $ | $ |
| Other Development Partner 2 (name) |  | $ | $ | $ | $ | $ |
| Other Development Partner 3 (name) |  | $ | $ | $ | $ | $ |

## 1b. Information Sharing and Early Dialogue with Key Stakeholder Groups

# Introduction

The Constitution of the Kingdom of Bhutan states that 60% forest cover is to be maintained for all times to come, and to realize this goal the partnership between government and people is crucial. Accordingly, the RGoB has been carrying out awareness raising among the general public on the importance of conserving and sustainably managing natural resources for many years.

Considering that local people’s participation is key to sustainable management of natural resources, the Royal Government of Bhutan has framed various enabling policies and pieces of legislation to ensure public participation from initial decision making to implementation. Article 5 of the Constitution of the Kingdom of Bhutan states that every Bhutanese citizen is a trustee of the Kingdom’s natural resources and environment.  This highlights that the responsibility to protect and conserve the environment is vested upon each and every individual. The Forests and Nature Conservation Act of Bhutan of 1995 recognizes the traditional and cultural rights of local people to forest use and thereby establishes their legitimate access to forest resources. This provides a strong legal framework to pursue people-centric forest management programmes. Accordingly, the Forest and Nature Conservation Rules 2003 (revised in 2006) has a dedicated chapter on Bhutan’s Social and Community Forestry Programme to guide implementation of this programme in a participatory manner.

The RGoB has always accorded high priority to sharing information and public consultation before starting any new programmes. These are clearly reflected in the programmes undertaken so far in the previous Five Year Development Plans. These policy decisions and programmes were supported and implemented through the recruitment of extension officers (agriculture, livestock and forestry) at district and block (local) levels and delegation of the responsibilities to them as per the Decentralization Policy of the Government (1994). These existing institutions and mechanisms will help ensure that all the stakeholders and communities effectively participate in decision making, planning and implementation of REDD+ activities.

For further strengthening of peoples’ participation in natural resource management, the 11th FYP of the DoFPS, MoAF has proposed a separate programme on people’s participation and good governance, with a strong emphasis on participation of local communities and institutions in forest management and conservation. The DoFPS will be focusing on key strategies based on the National Forest Policy (2011) for implementing the 11th FYP through:

- Strengthening the rights, responsibilities and capacities of local communities to regulate access and sustainable use of forest resources through decentralization and devolution of management authority from central government to local communities and the promotion of good governance;

- Forest management based on the principles of good governance to ensure transparency, accountability, participation, empowerment, equity and benefit sharing.

# Stakeholder Mapping

A preliminary stakeholder mapping exercise has been undertaken to identify stakeholder groups with an interest in REDD+, and the relationships among the groups.   Table 1a-1 provides a listing of stakeholders by type and geographic influence.

# Table 1a-1: REDD+ Readiness Stakeholder mapping

| Level | Government institutions and agencies | NGOs | Private Sector/ Corporation | Knowledge Institutions | Development Partners |
| --- | --- | --- | --- | --- | --- |
| National | - Gross National Happiness Commission - National Environment Commission - Ministry of Finance - National Land Commission - Ministry of Agriculture and Forests - Department of Forests and Park Services - Watershed Management Division - Social Forestry & Extension Division - Forest Resource Management Division - Wildlife Conservation Division - Nature Recreation & Ecotourism Division - Forest Protection & Enforcement Division - Department of Agriculture - Department of Livestock - Ministry of Home & Cultural Affairs - Department of Local Government - Ministry of Foreign Affairs - Tourism Council of Bhutan - Ministry of Economic Affairs - Department of Geology and Mines | - Royal Society for Protection of Nature - WWF –US - Tarayana Foundation - Bhutan Trust Fund for Environmental Conservation - Association of Bhutanese Tour Operator | - Natural Resource Development Corporation Limited - Druk Green Power Corporation - Mining sector - Tour Operators - Saw millers and furniture units | - Council for RNR Research of Bhutan - Ugen Wangchuk Institute for Conservation and Environment - College of Natural Resources - Sherubtse College | Multilateral - UNDP - FAO - UNEP - UN REDD Bilateral - NORAD - JICA - IFC/WB - ADB |
| Regional | - Territorial Forest Division - National Parks - Wildlife Sanctuaries | Same as National level institute | Same as National level institute | Same as National level institute | Same as National level institute |
| Dzongkhag | - Dzongkhag Administration - Gewog Administration - Chiwog level - Village level | Same as National level institute | Same as National level institute | Same as National level institute | Same as National level institute |

Figure 1a-1 indicates shows and interest influence diagram for major stakeholders at the national level.

High Influence, Low Interest

Low Influence, Low Interest

High Influence, High Interest

Low Influence, High Interest

Local communities

Herders

NGOs

WMD

NEC

GNHC

NRDC

Media

Dzongkhag administration

Geog administration

Academia

# Figure 1a-1: Interest-influence diagram for key REDD+ stakeholders in Bhutan

# Table 1a-2 shows the roel and mandates for key governmental stakeholders.

# Table 1a-2: Current and potential roles of government ministries in REDD+ readiness

| Ministry | Current REDD+ relevant roles | Potential role in REDD+ Readiness |
| --- | --- | --- |
| Gross National Happiness Commission | All REDD+ projects will be approved as per GNHC criteria | - -Coordinate and evaluate REDD+ programs |
| National Land Commission | Carrying out land demarcation | Land Reform-responsible for land demarcation during REDD+ implementation |
| National Environment Commission | - Developing Environmental legislations and policy - Monitoring environmental impacts - Represents Bhutan at a political level in UNFCCC negotiation - Chairperson of the Climate Change Committee | - Continue to conduct technical climate Continue to conduct technical climate change policy analysis and make - Continue to conduct technical climate change policy analysis and make recommendations to MOFA for UNFCCC negotiations |
| Ministry of Agriculture and Forests | - - Represents Bhutan at a political level in UNFCCC negotiation - Agricultural land management - Drafts agricultural laws/regulations - Needs to meet agricultural production targets - Genetic resources management - Development of livestock program including improvement of breeds and feed resources - Management of Government Reserve Forests including Protected area network, forest management units and areas outside FMUs - Community forests - Watershed Management - Wildlife conservation and habitat management - Management plans for FMU for timber harvesting Non-wood forest products development | - Lead the National REDD Task Force - Coordinate REDD Readiness - Coordinate REDD Strategy and lead Strategy development - -Drafting REDD relevant laws - Draft agricultural laws relevant to REDD -Representation in the National REDD+ Technical Working Group - Identification of REDD+ plans and programs - Coordinating all REDD+ activities - Implementation of REDD+ activities and programs - Monitoring and evaluation of REDD+ activities and plans - |
| Ministry of Economic Affairs | - Development of Mines - Development of Hydropower projects | Involve in REDD+ with national development plans/planning process |
| Ministry of Foreign Affairs | Represents Bhutan at government level in UNFCCC negotiations | - Represent Bhutan at Government level in UNFCCC negotiations |
| Ministry of Home and Culture Affairs) | - Responsible for law enforcement -Administration at Dzongkhag level - Conflict and Grievance | - Represent REDD+ committee at Dzongkhag level for communities |
| Ministry of Finance | -Auditing donor aid -Budget control/Allotment | - Representation in REDD+ Technical Working Group -Managing Budget for REDD+ readiness activities |

# Environmental Consultation and Awareness Raising Activities

The MoAF, with the support from the RGoB and donors, has carried out various environmental awareness raising activities through the celebration of events including World Environment Day, Social Forestry Day and World Earth Day. During celebration of such events, messages on the importance of conservation and sustainable management of natural resources are circulated through various newspapers as well as online on the websites of the MoAF and the DoFPS. Further, awareness raising campaigns have been rigorously pursued through the media to reach out to a broad audience. Radio and television have also been used for awareness raising. For example, a radio and television program hosted by the Bhutan Broadcasting Service (BBS), in collaboration with Ministry of Agriculture since 2010, is “Sanam Rigpa” – which literally means “enhancing knowledge on integrated natural resources management” (farming, livestock and forestry). A summary of the themes discussed in the interactive live show over the past year are given in Table 1b-3.

# Table 1b-3: Summary of themes discussed in BBS many missing

| Sl.no | Themes discussed | Agency |
| --- | --- | --- |
|  | Forest Fire management | DoFPS |
|  | Organic farming | DoA |

# REDD+ Awareness Raising Activities and Programs

With its large area under forest cover, low rate deforestation and forest degradation, political commitment to environmental conservation, more than 50% of its land area under protection and its commitment to carbon neutrality, Bhutan provides a conducive environment for implementing REDD+. The Government acknowledges the potential of REDD+ to deliver significant benefits to local communities living in and around the forests for conserving and sustainably managing their resources. For resource managers, REDD+ could be a platform to enhance their capacity to manage their forests, improve their knowledge base and promote sustainable forest management. However, the risks associated with the implementation of REDD+ activities to local communities needs to identified, reduced and mitigated jointly in collaboration with all relevant stakeholders. The process requires considerable awareness raising efforts and capacity building of staff and local communities in identifying risk and benefits of REDD+ and to develop appropriate measures to mitigate the risks. Therefore, the RGoB considers the awareness raising programs as the first step in implementing REDD+ activities.

In 2011, Bhutan joined the UN-REDD Programme and Watershed Management Division, under the Department of Forests and Park Services, Ministry of Agriculture and Forests was designatedas the focal point for REDD+. Since then the WMD began selection of stakeholders and sharing of information process. The aim of the stakeholders’ participation was to determine and identify key stakeholders from sectors that contribute directly or indirectly to drivers of deforestation and forest degradation, as well as those whose support will be needed; to implement actions that are needed to address the problems. The result of this objective evolved into development of REDD+ Technical Working Group, who advised the WMD focal point in selection of the stakeholders as well as the methods of dissemination of information to the grassroots.

A summary of the stakeholders meetings and its outcome are:

- The local communities were positive of such initiatives i.e. REDD+ activities, and it would improve their livelihood and health of the forests.

- It was a general concern that there may be increase of human wildlife conflict in some areas

- There were some concerns that the REDD+ activities may stop development activities within forested areas.

- Increased aesthetic and recreational value leading to development of more nature based tourism sector that will uplift livelihood of the local communities

- With the introduction of REDD+ activities the stakeholders felt that the Benefit distribution mechanism would improve or complement the existing community forest mechanism of income generation by the local communities.

The stakeholder consultation meeting had more XXXX people including women and youth from XXX Dzongkhag/Gewogs who learned new subjects and issues about REDD+ activities:

- Climate change and its Impacts to the local ecosystem

- Role of forests in climate change and its benefits

- REDD+ (Reducing Emission from deforestation and forest degradation including conservation, enhancement of carbon stock, sustainable management of forests)

- Local communities and how REDD+ activities will enhance the rural community livelihood

- Challenges, risks and benefits from REDD+ activities

# Initial National REDD+ Seminar

REDD+ was formally introduced to Bhutan through a two-day seminar in Thimphu in June, 2010. The seminar was also used as a platform to raise awareness of all relevant stakeholders. As a follow up to the seminar, the DoFPS hired a consultant to carry out a REDD+ feasibility study. During the feasibility study, the consultant held a series of consultations with various stakeholders which helped in enhancing knowledge on REDD+ concepts.

# Awareness raising workshops

Bhutan joining the UN-REDD Programme in 2011 also proved to be an important step towards preparing the country to implement REDD+. With financial support from UN-REDD, the Ministry implemented awareness workshops at national and sub-national levels, targeting a diverse range of government organizations, civil society organizations and local communities living in and around forest areas. The summary of workshops on REDD+ carried out are given in the Table 1b-4.

Table 1b-4: Awareness workshops carried out so far on REDD+ between 2010 and 2012 at National level

| Workshops | Target Audience | Date | Number of Participants | Objectives of the workshop |
| --- | --- | --- | --- | --- |
| Awareness Raising Seminar on REDD+ | National Stakeholders involved in Natural Resources management | June 2010 |  | - Familiarize with the basic concepts & different forms of REDD in international perspectives and negotiations - Sensitize key issues on various aspects - Inform policy makers of socio-economic and equitable sharing of benefits |
| National Workshop on REDD+ Strategy Development in Bhutan | Multi-sector REDD+ stakeholders | April 2012 | 68 | - To bring all the stakeholders together and provide opportunity for the participantsto familiarize themselves with the concept of the REDD+ mechanism andeducate them on the process of REDD+ strategy development; - To institutionalize the REDD+ Advisory committee and Technical working group and finalize their mandates; - To share and identify the processes for the development of a National REDD+ Strategy |
| REDD+ Environmental Safeguard and Multiple Benefits workshop | National REDD+ stakeholders and probable implementers ( District Officers) | October 2012 |  | - Build national awareness of, and capacity on REDD+ safeguards and multiple benefits |
| National Forest Monitoring System Workshop | National REDD+ stakeholders, technical NFI, remote sensing/GIS and GHG inventory staff, | December 2012 | 40 | - To enhance knowledge among Bhutanese REDD+ stakeholders on: 1) REDD+ activities and the negotiation process under the UNFCCC; 2) UNFCCC guidance on national forest monitoring systems for REDD+; 3) IPCC Guidance and Guidelines - Determine next steps for capacity building activities and support to the implementation of forest monitoring and measurement systems |

In addition to the above workshops, DoFPS took the opportunity to clarify and explain REDD+ and its associated risks and benefits in many forums, including:

- Annual Forestry Conference, December, 2011

The conference was attended by all levels of staff under the DoFPS, organized to debate proposed plans and programs of the DoFPS. REDD+ was presented to participants as one of these new programs. The Conference was also attended by representatives from the NGOs and other relevant autonomous agencies.

- Annual Livestock Conference, 2012

Similarly, the Annual Livestock Conference was attended by staffs of Department of Livestock to discuss new plans and programs. DoFPS was given a chance to present on the plans and programs relevant to the Livestock Department, including REDD+.

- Annual Agriculture Conference, 2012

The Agriculture Conference was another platform the DoFPS used to raise awareness of REDD+ to the participants, consisting of agriculture staff from all over the country. During the presentation, support was sought for jointly preparing for REDD+ implementation.

REDD+ was also touched upon in many of the workshops on climate change and its impacts organized by different agencies and NGOs.

# R-PP Early Information Sharing and Dialogue Activities

The series of awareness programs on REDD+ at national level and sub-national level has helped in reaching the message on REDD+ to most important stakeholders. The formulation of R-PP also started with initial consultation with REDD+ Technical Working Group members comprising of representatives from the DoA, DoL, DoFPS, CNR (RUB), MoF (DPA), GNHC, NRDCL, RSPN (NGO), BTFEC and NEC.  DoFPS has already organized three TWG meetings so far to discuss on the R-PP and REDD+. The members of the TWG also have the responsibility to discuss and inform their parent organizations on the R-PP and REDD+ and to inform any issues because of REDD+. The TWG has met  four times, and the meetings so far have served as a useful platform to discuss key issues, as well as helping to build awareness on the REDD+ among a range of stakeholders.

The DoFPS has also printed reports of all the national workshops held so far (Table 1b-2 and circulated to the relevant stakeholders to enhance their knowledge and understanding on REDD+ and its process.

One of the workshop reports consists of potential risk and benefits identified by the stakeholders at the National Workshops.

Priority risks identified were:

- Restricted access to forest resources by rural forest-dependent communities

- Increased human and wildlife conflict

- Reduced development opportunities

Priority benefits identified were:

- Increased watershed protection for hydropower generation

- Contribution to Bhutan’s constitutional mandate to protect 60% of forests

- Increased aesthetic and recreational value of the Bhutanese landscape

Apart from the National level workshops, DoFPS also initiated awareness workshops at district level (Table 1b-5) so as to involve local people represented by their local leaders. The participants consisted of Gup and Mangmi (Gewog Leader), GAO ( Gewog Administration Officer), Tshogpa (village leader) and Renewable Natural Resources Extension Agents (Agriculture, Forest and Livestock). The workshop was carried out in 14 out of the total of 20 districts in the country. The Gewog leaders and representatives of government agencies were entrusted to carry out similar workshops at their village level involving the local people.

# Table 1b-5…REDD+ Awareness raising at district level

| Sl. No | District | Month date | No. of participants | Region |
| --- | --- | --- | --- | --- |
| 1 | Chhukha | 29th April 2013 | 122 |  |
| 2 | Dagana | 6th May 2013 | 108 |  |
| 3 | Gasa |  |  |  |
| 4 | Haa |  |  |  |
| 5 | Mongar |  |  |  |
| 6 | Paro |  |  |  |
| 7 | Punakha |  |  |  |
| 8 | Thimphu |  |  |  |
| 9 | Trashigang |  |  |  |
| 10 11 | Trash Yangtse |  |  |  |
| 12 | Trongsa |  |  |  |
| 13 | Tsirang | 8th May 2013 | 138 |  |
| 14 | Wangdue |  |  |  |

During the above workshop, several key themes were discussed in relation to REDD+ including climate change, Payment for Environmental Services (PES), REDD+, R-PP etc.

Recognizing the potential for REDD+ in Bhutan, the stakeholder workshops held across the country have provided substantial approach to REDD+ and preparation of this R-PP has already significantly contributed to building greater awareness and capacity across a range of stakeholder groups and forest sector institutions. Again, a continuation of this approach to capacity building and greater awareness across all stakeholder groups from national to community level will be needed for Bhutan to reach ‘readiness’ in 2014.

# Key discussion topics

- Climate change

- Causes of Climate change

- Impacts of Climate change

- Role of forests in climate change

- REDD+ ( Reducing Emission from deforestation and forest degradation including conservation , enhancement of carbon stock, sustainable management of forests)

- Local communities and REDD+

- Challenges, risks and benefits from REDD+

While the participants welcomed the idea of REDD+ as a global initiative to compensate for the rural communities involved in conservation of forest and its allied resources, there were several issues and concerns.  These were:

- Restriction on use of natural resources

- Benefit distribution mechanism

- Human Wildlife Conflict

- More Awareness programmes

# Restriction on use of natural resources

While the participants acknowledged that conservation polices have helped in maintaining the environment intact which helped in providing various goods and services to the people, introduction of new restrictions would directly impinge on their livelihood since there is limited alternatives to enhance their well being.

# Benefit distribution mechanism

Concerns were raised about the flow of benefits to the communities living in and around forest areas. A need was felt for a transparent and equitable benefit distribution for the revenue generated from REDD+. Some suggested that benefits from REDD+ should be distributed based on the forest cover percentage of different districts.

# Human Wildlife Conflict

The participants also raised the concern of human wildlife conflict issue. They were of the view that REDD+ might lead increase in incidences of conflicts thereby causing damage to their crops in the agriculture field. The participants also questioned whether the funds coming from the REDD+ can be used for compensating the damages caused.

# More Awareness programmes

The participants in all the regions expressed that the awareness programmes were a powerful tool to engage wide range of stakeholders towards sustainable management of forest resources. Therefore, such awareness programmes should be taken to community or village level and discuss the REDD+ process in details. They expressed that any new program has to be discussed with local communities so as to avoid future implications as ultimately it is the local governments who will be implementing the programme.

# Methods and tools used during the awareness and consultation on REDD+

During the REDD+ awareness at National and district level, DoFPS used following methods and tools for information sharing and early dialogue:

- Consultative meetings

- Interviews

- Focus group discussions

- Poster presentation

- Workshops

- Video Presentation

# Awareness programs in the Readiness Phase

During the initial discussion on REDD+ with the local communities and other stakeholders, it was felt that detailed consultation on the REDD+ on the following issues was necessary:

- Process

- Readiness Phase

- Benefits and risks

- Benefit Distribution system

- Institutional arrangement

In order to address the above issues, various levels of consultation will be carried out with different stakeholders. Due to involvement of different level of stakeholders starting from the communities in and around the forests till highest government agency, different communication and information materials will be needed to ensure that all level of stakeholders have adequate understanding and knowledge on REDD+ and related issues. Proper understanding of REDD+ and issues by the stakeholders will not only enhance their participation but also ensure that they are involved in the decision making process. Therefore, the following activities will be undertaken:

- Updating and mapping of relevant stakeholders and ensure participation of the relevant stakeholders in the consultative meetings

- Organize consultative meetings with different stakeholders on the REDD+ Readiness Phase at National Level, Regional level and District level

- Organize awareness workshops in schools and institutions

# Communication and information materials to be developed

For effective communication of messages on REDD+, following products would be developed:

- Updated WMD website to include REDD+

- Posters, manuals, brochures in English and Dzongkha

- Publish awareness messages in print media, radio and television

- Photo competition

- Art competition

- A REDD+ logo

# Please provide the following information:

- Pre-consultation activities to date and additional activities planned under this component, to contribute to the development of the R-PP in less than five pages

- Provide a brief summary activity and budget and funding in Table 1b (detailed budget data and funding table go in Component 5);

- If necessary, attach a work program or draft input to ToR for activities to be undertaken in Annex 1b.

| Table 1b-6: Summary of Information Sharing and Early Dialogue with Key Stakeholder Groups Activities and Budget |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Main Activity | Sub-Activity | Estimated Cost (in thousands) |  |  |  |  |
|  |  | 2014 | 2015 | 2016 | 2017 | Total |
| Preparation of information sharing and consultation process | Developing awareness program materials | $ | $ | $ | $ | $ |
|  | Capacity Building of local communities and TOT | $ | $ | $ | $ | $ |
| Communication media | Developing websites | $ | $ | $ | $ | $ |
|  | Media campaign process | $ | $ | $ | $ | $ |
| Workshops and seminars |  | $ | $ | $ | $ | $ |
|  |  | $ | $ | $ | $ | $ |
| Total |  | $ | $ | $ | $ | $ |
| Government |  | $ | $ | $ | $ | $ |
| FCPF |  | $ | $ | $ | $ | $ |
| UN-REDD Programme (if applicable) |  | $ | $ | $ | $ | $ |
| Other Development Partner 1 (name) |  | $ | $ | $ | $ | $ |
| Other Development Partner 2 (name) |  | $ | $ | $ | $ | $ |
| Other Development Partner 3 (name) |  | $ | $ | $ | $ | $ |

## 1c. Consultation and Participation Process

Introduction

Recognizing the multiple benefits of forests and its potential to enhance the socio-economic development, the Royal government has always emphasized the importance of forest conservation and sustainable management of our forest resources for the benefit of our people. Over the years, with the enactment of series of acts and policies, the Department of Forests & Park Services (DoFPS), has institutionalized the process and system of sustained supply of forest resources from designated forest areas like forest management units and working schemes across the country. However, the Department of Forests & Park Services faces many challenges that put at risks the principles of sustainability of forest resources.

With close to 79% of the population, dependent on subsistence agriculture, forestry plays a major part in the overall productivity of the farming systems and its contribution in enhancing the economic development of the rural population. Considering that local people’s participation is key to sustainable management of natural resources, the Royal Government of Bhutan has framed various enabling policies and pieces of legislation to ensure public participation from initial decision making to implementation. Article 5 of the Constitution of the Kingdom of Bhutan states that every Bhutanese citizen is a trustee of the Kingdom’s natural resources and environment.  This highlights that the responsibility to protect and conserve the environment is vested upon each and every individual.

For further strengthening of peoples’ participation in natural resource management, the 11th FYP of the DoFPS, MoAF has developed a programme on people’s participation and along good governance, with a strong emphasis on participation of local communities and institutions in forest management and conservation. The Ministry of Agriculture and Forests (MOAF) will therefore, institutionalize active participation and engagement of relevant stakeholders in REDD+ readiness. The utilization of participatory processes within Bhutan will make it possible to ensure transparency in decision-making, improve the empowerment of stakeholders, involve them in making decisions, and implementation, monitoring and evaluation of REDD+ activities.

Consultation and Participation Process

Since 2010, Bhutan has gained experience in conducting the early information sharing and dialogue for the formulation phase, understood the importance of participatory processes in relation to REDD+ and other forestry activities. During the implementation of Readiness phase MOAF will undergo extensive consultations with relevant stakeholders on the various components of the R-PP by building on the early information and social mobilization campaign and dialogue conducted.

MOAF will provide realistic understanding of REDD+ to all stakeholders before implementing the activities. The consultation and participation process will be developed in steps, so that there is adequate time for understanding, consolidated and shared amongst the stakeholders. The main focus of consultation and participation would be:

- To share experiences of civil society organizations, local forest-dependent communities, private sector and other relevant stakeholders to improve in local decision-making when developing plans for REDD+ activities.

- To involve all sectors of the governmental organization will be encouraged while developing cross sectoral framework for REDD+ activities

- To conduct a consultation with all the relevant Dzongkhag and gewogs to provide a clear understanding on issues of REDD+ activities and its benefit to the local communities

Goals and Objectives:

The overall goals of the consultation and participatory of the stakeholders within the REDD+ Dzongkhags and gewogs  area would be:

- To increase awareness through wholesome participation of the stakeholders when implementing and decision making on REDD+ plans and activities and how benefits can be distribution to the local communities.

Key Stakeholders to Target for the Consultation and Participation

The Dzongkhgas and Gewogs will share information and exchange dialogues with the government and NGOs to formulate REDD+ activities. Furthermore, consultations on the social and environmental impacts and risks associated with different options and design of the environmental management framework will be developed depending on area and location wise. During the implementation of Readiness phase, the stakeholder analysis will be built upon exercise described in Component 1b. Lessons will be identified and appropriate steps taken to address concerns of stakeholders. This would include:

- Participatory mechanisms and structures will be identified at the initial stage of information sharing to enhance the active engagement and inclusion of stakeholders most especially the forest-dependent communities and institutions such FMUs and Dzongkhag forests.

- Several awareness programme at the Dzongkhag level will be done to mainstream REDD+ within the 11th FYP activities

- The government sectors and NGOs will ensure that mitigation measures of REDD+ are identified, implemented and monitored

- To provide information to enable Dzongkhags and local institutions to understand their role in facilitating REDD+ readiness through good governance

- National Land Commission will be engaged to provide approval for any land use change and ownership change

- The private sector and local community will be informed particularly for any agro-industries, Non-wood forest products, energy, mining and small entrepreneurship development

- The local NGOs and associations will be involved in community development and conservation.

- Women and youth of the local communities will be also be involved in the decision making process which will further processed to the Dzongkhag administration for all REDD+ activities

Key Issues to Address during Consultation and Participation

The Government acknowledges the potential of REDD+ to deliver significant benefits to local communities living in and around the forests for conserving and sustainably managing their resources. For resource managers, REDD+ could be a platform to enhance their capacity to manage their forests, improve their knowledge base and promote sustainable forest management. However, the risks associated with the implementation of REDD+ activities to local communities needs to identified, reduced and mitigated jointly in collaboration with all relevant stakeholders.

Based on the REDD+ strategy options that identifies issues affecting land use, benefit sharing and forestry, the following issues will be key discussion topics:

- Main causes and drivers of deforestation and forest degradation as identified for the 11th FYP planning process will be included along with the REDD+ options

- Economic, social and environmental impacts of REDD+ and mitigation of risks

- Equitable distribution of income will be shared from the existing community forest experiences where no community forest plans are not implemented as part of REDD+ option strategy

- Setting up effective grievance and feedback redress mechanisms

Table 1c-1: Participation of key stakeholders in REDD+ activities

| Activities | Central Government | Dzongkhag | Gewog | Local Communities | NGOs | Private sector |
| --- | --- | --- | --- | --- | --- | --- |
| MRV and Monitoring | Yes | Yes | Yes | Yes | Yes | Yes |
| REDD+ forest Governance | Yes | Yes | Yes | Yes | Yes | Yes |
| Multiple Benefit system | Yes | Yes | Yes | Yes | Yes | Yes |
| Transparent, equitable and accountable management | Yes | Yes | Yes | Yes | Yes | Yes |
| Grievance Mechanism | Yes | Yes | Yes | Yes | Yes | Yes |
| Safeguards – Environmental and Social Impacts | Yes | Yes | Yes | Yes | Yes | Yes |
| Carbon Inventory and socio-economic | Yes | Yes | Yes | Yes | Yes | Yes |

Awareness programs on REDD+ at national level and sub-national level would be organized to provide information on the importance of REDD+ to all stakeholders. The members of the TWG will be responsible to discuss and inform their parent organizations on the R-PP and REDD+ and to inform any issues on REDD+ which is being implemented at Dzongkhag and Gewog level.

Consultation Process

Step 1. Awareness raising and capacity building

The main role of the Department of Forest and Park Services and TWG multi-sectoral coordination and cooperation for the planning and implementation of REDD+ activities will endorses plans related to REDD+ and forestry and climate change. In addition, it provides advice, oversees and monitors the planning process and the implementation of activities on REDD+.

A REDD+ Technical Working Group (TWG) under the leadership of the Director General (Forests), will ensures the institutional representation of different stakeholders during the process and the members are well represented from the grass-root level to NGOs and government. To ensure the effectiveness and efficiency of the REDD+ implementation process, the TWG will be expected to proactively provide innovative ideas, monitor program activities, and prepare a comprehensive REDD+ Strategy through consultative meetings, workshops and distribution of pamphlets including websites.

Awareness and Capacity Building: The forestry research program was formally started in 1987. The national forestry program is coordinated by national forestry research nodal centre, based in Research and Development centre at Yusipang, and implementation across the country by other research and development centers spread strategically at different agro-ecological zones.  Currently there are five research and development centers and five sub-centres which cater research and development needs in renewable natural resources (RNR) sector. The forestry researches are clubbed into four research programs namely

- Nature conservation research,

- Sustainable forest management research,

- Watershed research and

- Socio-economics forestry resources related research.

The forestry research priorities are set in research and planning meeting held every three years with all concerns stakeholders. The RDC Yusipang strategically maintains close relationship with regional and international universities and institutions for better research input and as well as output. Additionally educational institutes such as Ugyen Wangchuck Institute Conservation of Environmental based in Bumthang, conducts certificate training courses to foresters as well as conducts basic research in forestry (UWICE) and College of Natural Resources (CNR) under Royal University of Bhutan (RUB) conducts research as well as training of forestry students up to Bachelor of Science in Forestry. The RDCs also trains farmers and individuals on management of forestry resources in the country.  A recently established Rural Development Training Centre at Zhemgang imparts training on basic management of forestry resources to farmers and interested individuals on regular basis.

Further with the established of the CSO/NGOs, the NGOs will be involved in all REDD+ readiness capacity building as part of the REDD+ readiness.

Step 2. Pilot project

Bhutan is proposing to implement a demonstration pilot activity during the readiness phase. The selection of pilot projects or program under the REDD+ will be taken into consideration of different geographical conditions and traditional practices. Bhutan has different climatic zones starting from sub-tropical to cold temperature zones and the pilot programs will be based on criteria that are required by the FCPF. The activities will be designed to be able to establish monitoring mechanisms, how to provide information to the stakeholders and how to prepare activities for REDD+ program.

Step 3. Ready for REDD+

The third step of the consultation process will be to evaluate the results from these pilot projects and programs to enable readiness for REDD+. The process will be in the following methods:

Step 1. Awareness and capacity Building

Step 2. Pilot and testing activities

Step 3. Ready for REDD+

Year 1

Year 2 and 3

Year 4

Consultation meetings, workshops and capacity building training programs and stakeholders awareness program

Implementation of pilot projects and program

Final Evaluation

Consultation groups formed

REL and MRV

BDS

ACM

Final Consultation

Well-trained stakeholders

Training Materials

Consultation and participation process during the Readiness Phase

| Table 1c: Summary of Consultation and Participation Activities and Budget |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Main Activity | Sub-Activity | Estimated Cost (in thousands) |  |  |  |  |
|  |  | 2014 | 2015 | 2016 | 2017 | Total |
| Consultation Meeting at National Level | MRV and monitoring | 10 | 20 | 20 | 20 | 70 |
|  | Benefit distribution systems | 10 | 20 | 20 | 20 | 70 |
|  | Grievance Mechanism meeting | 10 | 20 | 20 | 20 | 70 |
|  | Climate change task force meeting | 10 | 20 | 20 | 20 | 70 |
| Consultation Meeting at Dzongkhag Level | Stakeholders meeting | 55 | 55 | 55 | 55 | 220 |
| Capacity building at Dzongkhag and Community level | Stakeholders capacity building at 20 Dzongkhags | 450 | 600 | 600 | 0 | 1650 |
| Identification pilot programmes | Piloting of community forest | 10 | 30 | 20 | 10 | 70 |
|  | Nature reserve park | 10 | 30 | 20 | 10 | 70 |
|  | Forest Management Units | 10 | 30 | 20 | 10 | 70 |
| Total |  | 575 | 825 | 795 | 165 | 2360 |
| Government |  | 50 | 82 | 79 | 20 | 231 |
| FCPF |  | 525 | 743 | 716 | 145 | 2129 |
| UN-REDD Programme (if applicable) |  | $ | $ | $ | $ | $ |
| Other Development Partner 1 (name) |  | $ | $ | $ | $ | $ |
| Other Development Partner 2 (name) |  | $ | $ | $ | $ | $ |
| Other Development Partner 3 (name) |  | $ | $ | $ | $ | $ |

# Component 2: Prepare the REDD-plus Strategy

## 2a. Assessment of Land Use, Land Use Change Drivers, Forest Law, Policy and Governance

# Introduction

This Sub-Component assesses land use, land use change drivers and forest law, policy and governance in Bhutan. This assessment will help to identify 1) key drivers of deforestation and forest degradation, and activities related to conservation, sustainable management of forests, and enhancement of forest carbon stocks; and 2) shortcomings in current land use, forest law, policy and governance structures that contribute to drivers of deforestation and forest degradation.

Bhutan is situated on the southern slopes of the Eastern Himalayas with an area of 38,394 km2. It is divided into four broad geographical zones with an altitudinal gradient from less than 150m on the southern border with India to 7500 meters in the north (see Figure 2a-1).

# Figure 2a-1: Topographic diversity of Bhutan

The country’s climate is as varied as its topography and, like most of Asia, is affected by monsoons. The climate is humid and subtropical in the foothills, temperate in the inner Himalayan valleys of the Southern and Central regions, and cold in the North, with year-round snow on the main Himalayan summits. Annual precipitation ranges widely in various parts of the country from 40mm-7800mm. Rainfall, in particular, can differ within relatively short distances due to rain shadow effects. Based on the agro-climatic condition determined by altitude, temperature and rainfall distribution, the country is classified into six major agro-ecological zones, as shown in Table 2a-1.

# Table 2a-1: Agro-ecological zones of Bhutan

| Agro-ecological zone | Altitude m. | Temperature 0C |  |  | Rainfall (mm) |
| --- | --- | --- | --- | --- | --- |
|  |  | Max | Min | Mean |  |
| Alpine | >3500 | 12.0 | -1.0 | 5.5 | <650 |
| Cool temperate | 2500-3500 | 22.0 | 1.0 | 10 | 650-850 |
| Warm Temperate | 1800-2500 | 26.0 | 1.0 | 13 | 650-850 |
| Dry Sub-tropical | 1200-1800 | 29.0 | 3.0 | 17 | 850-1200 |
| Humid Sub-tropical | 600-1200 | 33.0 | 5.0 | 20 | 1200-1500 |
| Wet Sub-Tropical | 150-600 | 35.0 | 12.0 | 24 | 2500-5500 |

The combination of topographical and climatic diversity contributes to Bhutan’s wide array of ecosystems and immense biodiversity.  Bhutan ranks in the top ten percent of countries with the highest species density on earth, and it has the highest fraction of land in protected areas as well as the highest proportion of forest cover of any Asian nation.

The protected areas system, which is made up of five national parks, four wildlife sanctuaries, and a strict nature reserve, covers altogether an area of 19,677km2 (exclusive of botanical park with 47km2) or 39.6% of the country’s total area. This puts Bhutan at the top of the list of countries in the world with the highest proportion of area under protected areas. An additional 9.5% of the country is set aside as biological corridors bringing the total under some form of protection to 51.4% of country. Currently there are 10 PAs of which 7 are operational and the rest will be brought under operation by 2013.  There are also 13 conservation areas of which 2 are under effective management and the rest under some form of interventions.  The network of protected areas is shown in Figure 2a-2, below.

# Figure 2a-2: Protected area network of Bhutan

The forests of Bhutan can be divided into the Alpine Zone, above 4000m, where there is no forest cover; the Temperate Zone, between 2000 to 4000m, including major conifer/broadleaf forests; and the Subtropical Zone, 150 to 2000m, characterised by tropical/subtropical vegetation.

Forest types include the following:

- Fir forests at 2,700 to 3,800m, requiring relatively high precipitation. Hemlock (Tsuga dumosa) and birch (Betula alnoides) also may be present. Toward the tree line, at 3,600-3,800m, fir becomes stunted and grades into juniper (Juniperus recurva) and rhododendron (Rhododendron spp.) scrub. Total area 345,302 ha.

- Mixed conifer forest, which occupies the largest portion of the sub-alpine region, between 2,000 and 2,700m. These forests may be dominated by spruce (Picea spinulosa), hemlock, larch (Larix spp.) or mixtures of these species. Hemlock tends to be found on wetter slopes than spruce and is generally bearded with lichens and mosses. Total area 486,827 ha.

- Blue pine (Pinus wallichiana) forest, found in temperate regions between 1,800 and 3,000m in Haa, Paro and Thimphu valleys in the west and Bumthang and Gyetsa valleys in central Bhutan. Sometimes it is mixed with oak (Quercus spp.) and rhododendron. Total area 128,593 ha.

- Chir pine (Pinus roxburghii) forest, a low-altitude (900-1,800m) forest type occurring in the deep, dry valleys of the Puna Tsang Chhu, Kuri Chhu and Kulong/Dangmechhu river systems, essentially under subtropical conditions. A long dry season is characteristic of these areas. Chir pine forests are heavily influenced by human activities, including tapping for resin, felling for timber and burning to produce fresh grazing for livestock or new lemongrass (Cymbopogon flexuosus) growth. Total area 100,899 ha.

- Broadleaf mixed with conifer in extensive areas where the gradation is very gradual. These are generally oak mixed with blue pine, or upper hill forest mixed with spruce or hemlock. Total area 135,789 ha.

- Upland hardwood forests on temperate hillsides, 2,000 to 2,900m, including evergreen oak forest and cool broad-leaved forest. Total area 450,000 ha.

- Lowland hardwood forests include forests in subtropical hills, and tropical forests in hills below 700m 1,000 to 2,000m.  The former are very rich and mixed with a wide variety of subtropical and temperate genera.  The latter are broadly classified as semi-evergreen, vary from almost totally deciduous on exposed dry slopes to almost totally evergreen in moist valleys. These are multi-storeyed, with particularly rich species diversity. Total area 440,000 ha.

### Forest scrub, which includes alpine and temperate scrub occurring naturally between the limits of the tree line and barren rocks. The dwarf juniper (Juniperus squamata), Rhododenron setosum and R. lepidotum and sometimes even dwarf oaks and willows are common species in the forest scrub. On the drier and higher ridges, however, xerophytic scrub like Caragana spp., Chesneya spp. and Ephedra spp. are much more common. Temperate scrub consists of dense bamboo or other xerophytic, spiny shrubs, which grow in cleared temperate forests that are not converted for agriculture or pasture.  Total area 325,730 ha

The relative frequency of each forest type is shown in Figure 2a-3. below.

# Figure 2a-3: Frequency of different forest types in Bhutan

# Trends in Forest Resources

Bhutan’s total forest area has expanded slowly over the past 20+ years, as shown in Table 2a-2, below, from FRA 2010.  Of the total area, 12.7% (413,000ha) is classified as primary forest, a figure that has remained constant. Bhutan has 3,000 ha of planted forest.   Trends in land use cover over the past 40 years are shown in Figure 2a-4.

# Table 2a-2: Trends in forest and other land cover types, 1990-2010 (area in ha x 103)

| Broad National Classes | 1990 | 2000 | 2005 | 2010 |
| --- | --- | --- | --- | --- |
| Forests | 3035 | 3141 | 3195 | 3249 |
| Scrub/Shrub/Grassland/Pasture | 566 | 609 | 611 | 613 |
| Agriculture | 318 | 199 | 186 | 173 |
| Others | 781 | 751 | 708 | 665 |
| Total | 4700 | 4700 | 4700 | 4700 |

# Figure 2a-4: Change in Land use over last four decades based on LUPP (1997)

# FRA 2010 also reports on estimates of forest carbon in Bhutan, as shown in Table 2a-3, below.

# Table 2a-3: Estimates of forest carbon for Bhutan (FRA 2010)

| FRA 2010 categories | Carbon (million metric tonnes) |  |  |  |
| --- | --- | --- | --- | --- |
|  | Forest |  |  |  |
|  | 1990 | 2000 | 2005 | 2010 |
| Carbon in above-ground biomass | 216 | 228 | 236 | 245 |
| Carbon in below-ground biomass | 80 | 85 | 88 | 91 |
| Carbon in dead wood | n.a | n.a | n.a | n.a |
| Carbon in litter | 49 | 55 | 58 | 60 |
| Carbon in soils | 212 | 218 | 223 | 226 |
| TOTAL | 557 | 586 | 605 | 622 |

# Legal Framework

Article 5 (Environment) of the Constitution of Bhutan states:

1. Every Bhutanese is a trustee of the Kingdom’s natural resources and environment for the benefit of the present and future generations and it is the fundamental duty of every citizen to contribute to the protection of the natural environment, conservation of the rich biodiversity of Bhutan and prevention of all forms of ecological degradation including noise, visual and physical pollution through the adoption and support of environment friendly practices and policies.

2. The Royal Government shall:

(a) Protect, conserve and improve the pristine environment and safeguard the biodiversity of the country;

(b) Prevent pollution and ecological degradation;

(c) Secure ecologically balanced sustainable development while promoting justifiable economic and social development; and

(d) Ensure a safe and healthy environment.

3. The Government shall ensure that, in order to conserve the country’s natural resources and to prevent degradation of the ecosystem, a minimum of sixty percent of Bhutan’s total land shall be maintained under forest cover for all time.

4. Parliament may enact environmental legislation to ensure sustainable use of natural resources and maintain intergenerational equity and reaffirm the sovereign rights of the State over its own biological resources.

In support of Article 5 of the Constitution, the Royal Government of Bhutan has established stringent laws, policies, regulations and rules for the protection and conservation of forest areas including biodiversity.  The most important of these are:

# National Forest Policy, 2011

The National Forest Policy, 2011 consists of a long term goal, major policy objectives and specific statements to enable various aspects of forest production, use and management. It has five guiding principles i.e., equity and justice in terms of access, poverty alleviation through integrated approach, deregulation and devolution, integration of science and indigenous knowledge and allowing import of logs and swan timber.

# Bhutan Forest Act (1969)

The Forest Act, 1969 was the first legislation that substantially changed natural resource property rights and provided substantial power to forest officials to protect, manage and control access to the forests. At the same time it appropriated many areas used as village and community forests as government property. The act stipulates that at least 60% of the country should remain forested at all time. It established centralized control over the utilization of forest resources and provided first legal framework for regulating forest resources in the country and consolidates numerous directives relating to forest rights, forest products and royalties. The act also provided, for the first time, strong penalties for forest offences.

# Land Act, 1979

This act was enacted as per the office order from the Hon’ble Home Minister in 1979. It provided legal perspective on rights of possession of lands and other land matters. The Act describes the rights of Thram holder over his owned land, Tsamdo and Sokshing, uses of Sokshing, rights over trees growing in a registered land; forming legal restrictions over forest management in these areas (RGOB, 1979).

# Forest and Nature Conservation Act (FNCA, 1995)

In 1995, the National Assembly repealed the Forest Act, 1969 and expanded its content to enact a new act, the “Forest and Nature Conservation Act, 1995” addressing changed social and economic needs of society. An important objective of the new act is to ensure an adequate supply of basic forest products to meet the needs of the population with due recognition of the multiple responsibilities for forest resources and their sustainable management and use. The basic principle of using the law to protect forests from local people has been maintained.

The new act recognizes community forests and deals in detail regarding their creation, utilization and management. The new act also provides a legal perspective on protection of flora and fauna and categorizes their status. It lists twenty-four wild animals and seven plants as totally protected species. The new act provides special legal protection to forests from fires.

# Forest and Nature Conservation Rules (2000, revised 2003)

The first set of rules was promulgated by the Council of Cabinet Ministers to exercise powers and duties reflected in the Forest and Nature Conservation Act (1995). Under the FNCR (2003) it is a legal requirement for a forest management plan to be prepared for FMUs. It defines administrative responsibility for preparation of forest management plans and its strict implementation in accordance with the approved plan. These rules also further emphasize community based natural resource management and PAs management.

# Forest and Nature Conservation Rules (FNCR, 2006)

Forest and Nature Conservation Rules implements the provisions of the FNCA 1995.The Rules issued administrative responsibility to the DoFPS for the preparation of Forest Management Plans and establishment of the National Level Forest Management Committee and the FMU Level Forest Management Committee. In addition, the Rules declare all forests to be the Government Reserved Forest (GRF) and provide for the allotment of land, land rights and user’s rights in GRF and issuance of social forestry rules to encourage forest crops on registered private land, excluding those categories of registered private land outside the 25 acre ceiling. The Rules further enable the establishment of community forests on GRF, use of forest resources, regulation of transport, import and export of forest produce. Provisions also include regulation of activity within PAs, soil and water conservation, offences and penalties.

# The Middle Path (National Environment Strategy, 1998)

The strategy identified several needed reforms that are relevant to REDD+, including:

- The conservation of protected areas must not be left to the forestry sector alone. Other sectors benefiting from well-preserved, up-stream catchments should contribute to the continued protection of watersheds, especially within the hydropower sector.

- Forestry conservation and use must be organised according to a “bottom-up” approach so that public participation is maximised.

- Although preventing forest degradation through strict enforcement of rules and regulations is important, educating the people about the importance of forest conservation also is needed.

- In all cases where either conservation or exploitation of forests is concerned, it is necessary to conduct an initial environmental examination and, if needed, a thorough Environmental Impact Assessment. Private and public-sector industries must be made to pay adequate compensation when violations occur.

The strategy also noted that enacting these reforms would require the active participation of many economic sectors, especially forestry, agriculture and industry.

# Environment Assessment Act (2000)

The Act responded to one of the reforms identified in the National Environment Strategy described above.  It establishes that all strategic plans, policies, programs and projects which may have an impact on the environment require environmental assessment.  Clearance is granted if:

- The effects of the project on the environment are foreseeable and acceptable;

- The applicant is capable of carrying out the terms of the environmental clearance;

- The project, alone or in connection with other programs or activities, contributes to the sustainable development of the Kingdom and the conservation of its natural and cultural heritage;

- Adequate attention has been paid to the interests of concerned people; and,

- The project is consistent with the environmental commitments of the Kingdom.

Other relevant acts, policies, and regulations include:

- Regulation for Environmental Clearance of Projects (2002)

- Timber Pricing and Marketing Policy (1999)

- RNR Sector Goals (2001)

- The Water Act of Bhutan (2011)

- Mines and Minerals Management Act (1995)

# Institutions

# Government organizations

The Department of Forestry was established in 1952 to oversee conservation and exploitation of the country's significant forestry resources. As part of the Ministry of Agriculture and Forests, the current Department of Forests and Parks Services includes in its mandate:

- Ensuring the maintenance of a minimum of 60% of the country’s geographical area under forest cover for all times to come as mandated by the Constitution of Bhutan;

- Conservation, protection, sustainable management and utilization of state forests, forest soil, water resources and biodiversity through insightful application of good science and science based management prescriptions;

- Facilitate development of forest based industries to contribute to local and national economics, and to create employment opportunities;

- Facilitate the empowerment of rural communities for the stewardship and management of local forest resources and NWFPs for income generation and livelihood enhancement and contribute to poverty reduction through enactment of enabling policies, legislations, strategies, plans and programs;

- Ensuring transparent and enhanced delivery of forestry services to the public through appropriate development of forestry administration, organization, capacity and facilities;

- Ensuring Bhutan’s commitments to international and regional conventions, treaties and non-legally binding instruments through participation, facilitating and enactment of enabling policies, legislations, strategies, plans, and programs;

The Watershed Management Division is one of the six functional divisions under Department of Forests and Park Services with primary responsibility of managing watersheds throughout the Country. It is also the agency with the mandate for REDD+.

# State enterprises

Following a period of unsustainable harvesting in the 1970s, the Logging Division of the Department of Forestry was upgraded to a Corporation known as Bhutan Logging Corporation (BLC), in 1984.  In 1996, BLC was upgraded to Forestry Development Corporation Limited (FDCL) and entrusted with commercial mandates.

In November 2007, FDCL was restructured as Natural Resources Development Corporation Limited (NRDCL) as per the Executive Order of the Prime Minister vide letter No PM/01/07/571 dated 7th November 2007 with mandate to manage sand, stone and other natural resources in addition to timber.  NRDCL is owned by Druk Holding and Investments (DHI), which is a 100% Government owned Investment Company and is governed by the Articles of Incorporation under the revised Companies Act of the Kingdom of Bhutan 2000.

# Non-governmental organizations

The main NGOs working on forest-related issues in Bhutan are:

Royal Society for the Protection of Nature (RSPN):  Established in 1987, RSPN has promoted environmental education and advocacy, conservation and sustainable livelihoods, research and emerging issues like climate change, water and solid waste. RSPN is active in the conservation of endangered species such as the black-necked crane (Grus nigricollis) , and through its  Environmental Education and Advocacy Program, RSPN in collaboration with Ministry of Education, has  established school based nature club in all the schools across the country to create environmental awareness in the school and surrounding communities

Worldwide Fund for Nature (WWF): WWF began working in Bhutan in the 1970s, and works closely with communities in and around protected areas through various educational and participatory initiatives in an effort to raise awareness, as well as promoting sustainable livelihood alternatives like eco-tourism.  WWF aims to work closely with the government and with local communities to reduce human induced pressures and threats on the environment. A particular focus of WWF’s work is the conservation and management of the natural biodiversity of Bhutan Biological Conservation Complex (B2C2: all protected areas, including buffer zones and the connecting biological corridors).

Tarayana Foundation: The Tarayana Foundation was established in 2003 by Her Majesty the Queen, Ashi Dorji Wangmo Wangchuck, to help bridge local needs of disadvantaged remote communities with larger national initiatives.  It is a non-profit organization working to uplift and enhance the lives of vulnerable individuals and     communities in Bhutan, focusing on small communities in the remote areas that lag behind on many socio-economic development indices. The Foundation helps these communities achieve self-sufficiency through small and targeted interventions through the process of true local empowerment.

# Universities

A Forest School was first established in 1971.  Now part of the Royal University of Bhutan, the College of Natural Resources, located at Lobesa, Punakha, offers a 2-year Diploma in Forestry and a 4-year BSC in Forestry (starting in academic year 2014).

# Major Causes of Deforestation and Forest Degradation

As noted above, the net area of forests is increasing in Bhutan, though there may be areas of local deforestation.  Thus, most of the relevant drivers are processes leading to forest degradations.  The key processes, acting at landscape scale, are discussed that are thought to be drivers of forest degradation and/or forest cover change are:

# Tshamdro and livestock

Livestock traditionally in Bhutan has to graze and find its fodder to a large extent in the forest in a country with such extensive forest cover. The traditional land tenure of grazing land is named tshamdro, with a great variety ranging from high-altitude pasture land to sub-tropical broadleaf forests. In general tshamdro will induce a certain negative impact on forest quality by the intensive browsing of tree seedlings, soil trampling and compaction and lobbing of tree branches by herders as fodder for their herds. To lesser extent will tshamdro use and grazing result in net forest cover decrease, although in limited areas serious overgrazing of forest areas has resulted in severe land forest and ultimately land degradation, especially in these areas where winter grazing by yaks and summer grazing by cattle coincides, e.g. Sheytemi in Radhi, Trashigang. The figures for 2007, as reported by Dr. Pema Choephel 2009, indicate a total tshamdro area of 406,513 ha, roughly 1% of the total land area of Bhutan. The new Land Act of 2007 revoked all traditional tshamdro rights and envisaged a new lease system for grazing land to replace the old tshamdro grazing right. As of now, no new system has been introduced so that a status quo is continuing, with continuation of the old grazing practices in many forest areas. Overall livestock numbers are slightly decreasing in recent years, with the number of cattle heads decreasing (DoL 2009) from 312,063 in 2006 to 307013 in 2009 and yak numbers decreasing from 52,911 in 2006 to 38,690 in 2009, see Table 2a-4 and Figure 2a-5. The decrease in livestock population is partly the result of the policy to replace unproductive local cattle with improved breeds, aiming at enhanced dairy production and reduced pressure on the forest. The reduction in the yak population is more outspoken and is most likely the result of less interest of the younger generation to continue the cumbersome life of a semi-nomad and the attraction of other income sources. The focus on dairy production is combined with dairy group formation, introduction of improved breeds as jersey and improvement of the fodder base by fodder promotion and improved pasture development in a move towards stall feeding. These changes from the traditional herding of local cattle in the forest, to a more sedentary livestock management will help to decrease pressure on the forest and enhance resilience and forest regeneration.

# Table 2a-4: Area of Tshamdro by dzongkhag

| Dzongkhag | Tshamdro (ha) | Dzongkhag | Tshamdro (ha) |
| --- | --- | --- | --- |
| Tsirang | 662 | Punakha | 17,569 |
| Pemagatshel | 3,162 | Gasa | 13,893 |
| Samdrup Jongkhar | 8,764 | Zhemgang | 18,775 |
| Sarpang | 365 | Samtse | 15,775 |
| Trashi Yangtse | 1,665 | Haa | 60,778 |
| Mongar | 7,142 | Bumthang | 26,671 |
| Dagana | 9,235 | Chhukha | 21,014 |
| Lhuentse | 9,108 | Wangdue | 50,719 |
| Trongsa | 21,687 | Thimphu | 77,317 |
| Paro | 1,767 | Trashigang | 40,445 |
| TOTAL |  |  | 406,513 |

# Figure 2a-5: Livestock population 2006-2006 (data from DoL)

# Tseri or slash-and-burn agriculture

Traditional slash-and-burn agriculture (tseri) has for centuries been practiced in Bhutan by farming communities. Tseri is still being practiced, but after the regulations of 2002 and the new Land Act of 2007, the practice is becoming less common as a result of the Government ban, and combined effect of labor shortage, wildlife pressure, alternative income options, promotion of sustainable land management alternatives and rural-urban migration trends. The decrease in tseri areas is resulting in an increase of forest cover; as many of the former tseri patches will ultimately, through forest succession stages return to forest cover.  Thus, currently and in the future, tseri is not a major driver of deforestation or of forest degradation.

# Forest fire

Most of the forest fires are anthropogenic in nature usually from agricultural debris burning and intentional burning to promote growth of new fodder grass. Fire management and suppression is hampered by limited accessibility in the harsh Bhutanese terrains, lack of adequate fire fighters and equipment.

Data for the last seventeen years (1993-2010), reveal 805 cases of wildfires, affecting 123,000ha of forest.  The data (see Table 2a-5) reveal no clear trend, but show a more cyclic character with years of very limited forest area affected (1,084 ha in 2003-2004) to more severe damage as in 1992-1993 (29,182 ha). The fire season in Bhutan is mainly in the winter period with very limited rainfall and very dry forest floor conditions, combined with often strong valley winds. The climate change scenarios predict more climate extremes in the years ahead, which could have serious implications for the severity and number of forest fires. Active forest fire prevention and initiatives as forest fire volunteer groups are needed to control the impact of forest fires. The impact on forest cover is seen as limited, but in years with larger forest areas affected, the impact on forest quality must be tangible, with loss in soil and water protection function and loss of valuable timber and firewood.

# Table 2a-5: Forest fires and area affected, 1992-2008

| Season | Area affected (ha) | Number |
| --- | --- | --- |
| 1992-93 | 29,182 | 84 |
| 1993-94 | 2,241 | 36 |
| 1994-95 | 19,628 | 56 |
| 1995-96 | 10,812 | 62 |
| 1996-97 | 9,853 | 48 |
| 1997-98 | 6,487 | 72 |
| 1998-99 | 13,536 | 112 |
| 1999-2000 | 13,455 | 104 |
| 2000-01 | 9,326 | 81 |
| 2001-02 | 5,858 | 64 |
| 2002-03 | 2,170 | 46 |
| 2003-04 | 1,084 | 40 |
| 2004-05 | 3,186 | 67 |
| 2005-06 | 7,832 | 37 |
| 2006-07 | 22,512 | 47 |
| 2007-08 | 2,567 | 10 |

# Leaf litter collection or sokshing

The practice of collecting leaf litter from the forest floor is regulated though a right of use granted for the practice to households. Sokshing is important to ensure sustained yields from agriculture and forms an important input of essentials nutrients to the top soil of dry- and wetland. Leaf litter is collected from both conifer forest (needles and litter) and broadleaf, especially oak forest (leaves and litter). The area of sokshing is limited with about 8,500 ha registered according to the records of the National Land Commission. The continuous removal of leaves, needles and litter results in serious impact on the nutrient availability of the sokshing forest with often stunted growth and limited regeneration. Soil fertility will decrease over time and the often bare forest floor is much more exposed to erosion processes. Sokshing will not affect forest cover extent, but will have a clear negative impact on forest quality, and is thus a potential driver of forest degradation.

# Infrastructure development

The rapid economic development of the last decades has resulted in an accelerated development of infrastructure as roads, transmission lines and urbanization. The growth of the farm road network over the last decade has been substantial and, apart from providing access to remote communities, has also had negative effects on the forest because of the corridors felled in previously untouched forests and the significant increase of landslides, erosion and other slope instability along the road alignments. The new roads in forest will give easy access to previously remote forest stands and encroachment, from collecting of NTFPs to illegal timber and firewood collection is common. For the construction of transmission lines and towers forest corridors have to be cleared, but the long-term impact is regarded as less destructive as the transmission alignments are not easily accessible and will not lead to further encroachment. Enlargement of settlements and urbanization with many new town plans being developed, means loss of a certain forest area. Encroachment into the surrounding the forest and related forest degradation are common. On the other side of the spectrum of urbanization is migration from rural areas, leading to less dependence on the forest where people have left, so the overall impact on forest cover and quality is complex to assess.

# Firewood

Firewood (or fuelwood) consumption in Bhutan is very high. The recent Integrated Energy Development Master Plan (IEDMP) of the Department of Energy, 2010, gives a comprehensive overview of residential, government and industrial demand for fuelwood, together with firewood demand projected, considering several growth scenarios. For instance, the country consumed 724 597 tonnes of fuelwood during 2005, which accounted for 56.8% of the total primary energy supply and represent 90% of the energy used in the residential sector. Fuelwood represents 231 739 TOE (ton-equivalent of oil) while electricity production stood at 216107 TOE in 2005. The per capita firewood consumption in the residential sector is about 0.78 ton per annum, accounting for 68% of the total firewood consumption in the country. The IEDMP states that “Dependence of the residential sector on firewood is alarming, but with strategic planning, this dependency can be reduced to minimum by 2020.” The report also indicates that: “Heavy dependence of the residential sector on firewood would be a cause of concern in the years to come.

Experience shows that because of electrification, firewood consumption reduces by about 30%–35%.  The electrification effort, to have complete coverage by 2013 to all households, will reduce domestic demand of firewood, but especially in rural areas the communities will continue to collect the free resource firewood represents. The IEDMP further reports that: ”With the sustainable yield for timber and firewood estimated at 1 565 540 tonnes/year, biomass would continue to remain an important source of energy for Bhutan.” Looking ahead at projected demand for firewood the IEDMP explores 4 scenarios of economic growth and energy efficiency improvement: BAU-business as usual, EE-increased energy efficiency, HIG-high economic growth, HIGEE-high economic growth coupled with higher energy efficiency. It is striking to note that under all scenarios the firewood demand is projected to increase, which will further put pressure on the forest ecosystem and on the forest management to be able the substantial demand. The net impact on forest cover is most likely a continued pressure on the forest through firewood collection with limited negative effect on total forest cover and more pronounced effect on regeneration and forest quality, with a trend to more open forest. The projected increase in firewood demand is worrying and requires focused policy development to be able to meet future demand sustainable, coupled with and increased focus on energy efficiency and the development of alternative and renewable sources.

# Timber

Timber is categorized as commercial logs or rural construction timber and substantial amounts are needed to cater to the market demand. The Bhutanese construction technique requires considerable amounts of timber and the rapid economic development has been accompanied by a frenzied construction. Timber is supplied mainly from Forest Management Units (FMUs), managed by NRDCL and from forests designated for the subsidized rural timber allotment, in line with the King’s call for affordability, accessibility and availability.

If we compare the actual removal with the potential production in FMUs it is clear that the market supply has problems to meet the increased demand. The annual allowable cut for FMUs, under operation, planned for and potential, is estimated for at approximately 160,000m3. According to the same author the potential AAC inside and outside of FMUs combined amounts to 791,155m3. This implies that the market demand has been such that the AAC as estimated for Bhutan has been surpassed for a number of years and that the timber supply therefore cannot be considered to be sustainable. This is in line with the comments of the management of NRDCL during the consultations, stating that they feared that within a number of years they will not be able to meet the market demand. Although the FMUs have a scientific based plan for sustainable management for 10-year plan periods, it appears that the implementation of the plans is not able to sustain continued yields from the FMU areas. NRDCL management mentioned that they see considerable loss of stock in their FMUs due to rural timber extraction and damage to the regeneration potential because of cattle grazing. This is combined with a sub-optimal management of the FMUs, not in sync with the initial well formulated management plans, aimed at sustainability of the stock.

# Poaching and illegal logging

Poaching or taking of forest resources (both floral and faunal) as deemed illegal in the Forest and Nature Conservation Rules, 2006 is today identified as the greatest threat to the survival and continuous existence of these resources. Incidences of poaching of wildlife, timber and other Non Wood Forest Produces (NWFPs) are reported from different parts of the country.

While “black marketing” of timber is mainly fuelled by the short supply of timber in the market attributed to the booming construction activities in the country, poaching of wildlife and NWFPs are often driven by various factors like high medicinal value of plant/wildlife parts, lucrative market for certain forest produces, human wildlife conflicts, ignorance and greed, etc.

A breakdown of illegal activities related to forest resources is shown in Figure 2a-6.  About 70 percent of the poaching offences relate to poaching of musk deer due to the high market price. The remote and harsh environment in which such species live makes law enforcement difficult and expensive.  Similarly, while many of the illegal logging offences are by local stakeholders cutting trees without the necessary permit, the more serious illegal logging activities occur in remote areas close to the border with India, which allows illegal logging gangs to escape detection and capture easily.

# Figure 2a-6: Breakdown of different illegal activities related to forest resources

# Analysis of Past Efforts to Combat Deforestation and Forest Degradation

The main strategy of the RGoB to avoid deforestation and forest degradation has been the establishment of an extremely extensive system of protected areas, as described above.  Forest cover in the 19,677km2 of protected area averages 72%.  This means that about 14,167km2 of forests lie within protected areas, corresponding to about 43% of all forests in the country.  Effective measures to avoid deforestation and forest degradation is therefore closely linked to protected area management effectiveness,

For those forests outside protected areas, the approach mainly consists of developing and implementing regulations to prevent forest loss and degradation.  This includes:

- The Royal Government of Bhutan decided to phase out tseri in the early 1980s. In 1986, the National Assembly passed a resolution that tseri land left fallow for 12 years or more would automatically revert to government forest.  Subsequently, the National Assembly, at its 72nd session in 1993 passed a resolution banning tseri cultivation and offering incentives to households formerly dependent on tseri to adopt settled agriculture.

- The Department of Livestock, under the theme, “Livestock for Green Enterprise Development and Poverty Alleviation”, adopted 12 resolutions to achieve in the 11th FYP.  Among the activities identified in these resolutions was the promotion of stall feeding, both to mitigate human-wildlife conflicts and to reduce impacts on forests.

- Community forestry is another strategy that has been adopted.  Community forestry in Bhutan was introduced in its current form relatively recently, in 2000.  The Forest and Nature Conservation Rules (2003) state that:

“Any area of the Government Reserved Forest that is suitable for management by a Community Forest Management Group may be designated as community forest”; and

“All individuals and households with traditional claim to forest produce from the proposed community forestry area have the opportunity to join the Community Forestry Management Group”

The CFs in Bhutan now comprise of over 510 CFMGs and 224,491 households, with a total area of 57,825 hectares, corresponding to nearly 2% of the country.

- Delineation and regulation of Forest Management Units.  Forest areas outside protected areas are divided into (a) critical, fragile, and depleted forest areas for conservation and protection and (b) operable areas for production. Forest Management Units (FMU) are units within the operable areas for which forest management plans (FMP) are prepared and implemented over a 10-year period for the purpose of sustainable management of forests and production of forest products.  There are currently 17 FMUs in Bhutan, covering 5.4% of the area of the country (250,000 ha).  Figure 2a-7 shows the location of FMUs in relation to the protected area system and biological corridors.

Figure 2a-7: FMUs, outlined in red, protected areas in various colours, and biological corridors outlined in blue

# Forest Governance in REDD+

It has been widely acknowledged that REDD+ will be more sustainability implemented by putting in place effective, transparent, and accountable governance systems that would contribute to yield positive results, impacts and outcomes. For Bhutan, the key governance issues related to REDD+ that will be reviewed during the readiness phase includes but not limited to:

- Forest Land Tenure and Ownership- looking at the issues of customary rights, user access rights and land tenure in general; and addressing the extent to which customary claims are recognized in law and what are the implications of REDD for local tenure arrangements?);

- Role of local level institutions in dealing with effective forest governance;

- Participation of local stakeholders in decision making process;

- Benefits sharing mechanism  that are equitable and transparent.

Bhutan has a sound legal policy framework to continue and strengthen measures to conserve and sustainably manage forest and to address threats.  However, there are still capacity gaps in ensuring full and effective implementation of these policies and legislation. A forest governance assessment framework for REDD+ implementation has not yet been undertaken. It is proposed that it will be conducted in the Readiness Phase using existing tools, such as UN-REDD’s Participatory Governance Assessment methodology.  The Objectives of the assessment would be to:

- Identify REDD+ governance challenges and risks

- Provide robust evidence base to recommend responses for overcoming them

- Facilitate sustainability of long-term policy reform through ownership

- Provide a framework for a participatory process at the country level for sharing information on how (governance) safeguards are promoted, addressed and respected

The governance assessment will include other sectors that directly or indirectly impact forests. It is important to analyze the policies and the state of governance in these sectors to examine the extent to which these sectors could adjust their policies and programs to reflect and integrate REDD+ activities and objectives for reducing forest emissions.

Criteria to be considered as checklist during implementation for adjustment as appropriate:

# 1) Assessment and analysis

- Check to see whether the summary of the work conducted during the R-PP formulation and implementation phases for this component present a complete, comprehensive and accurate (to the extent possible) analysis of recent historical land use trends and assessment of relevant land tenure, natural resource rights, forest law, policy and governance issues?

# 2) Prioritization of direct and indirect drivers

- Check to see how the analysis used to prioritize key direct and indirect drivers was used to address programs and policies included in the REDD+ strategy?

# 3) Links between drivers and REDD+ activities

- Check to see what evidence demonstrates that systematic links between key drivers and REDD+ activities were identified?

# 4) Actions plans to address natural resource rights, land tenure, governance

- Do action plans to make progress in the short-, medium- and long-term towards addressing relevant land tenure, natural resource rights and governance issues in priority regions related to specific REDD+ programs, outline further steps and identify required resources?

# 5) Implications for forest law and policy

- Does the assessment identify implications for forest law and policy in the long-term?

| Table 2a-6: Summary of Assessment of Land Use, Land Use Change Drivers, Forest Law, Policy and Governance Activities and Budget (Follow-up Activities Needed) |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Main Activity | Sub-Activity | Estimated Cost (in thousands) |  |  |  |  |
|  |  | 2011 | 2012 | 2013 | 2014 | Total |
|  |  | $ | $ | $ | $ | $ |
|  |  | $ | $ | $ | $ | $ |
|  |  | $ | $ | $ | $ | $ |
|  |  | $ | $ | $ | $ | $ |
|  |  | $ | $ | $ | $ | $ |
|  |  | $ | $ | $ | $ | $ |
| Total |  | $ | $ | $ | $ | $ |
| Government |  | $ | $ | $ | $ | $ |
| FCPF |  | $ | $ | $ | $ | $ |
| UN-REDD Programme (if applicable) |  | $ | $ | $ | $ | $ |
| Other Development Partner 1 (name) |  | $ | $ | $ | $ | $ |
| Other Development Partner 2 (name) |  | $ | $ | $ | $ | $ |
| Other Development Partner 3 (name) |  | $ | $ | $ | $ | $ |

## 2b. REDD-plus Strategy Options

# Introduction

This Sub-component proposes a preliminary set of strategies, to reduce deforestation and forest degradation, and enhance and conserve carbon stocks, thereby directly address the key drivers of deforestation and degradation identified in Sub-component 2a. However, it is recognised that not all the answers are known with regards to the best strategy options for REDD+. Thus, during R-PP implementation a process of consultation will continue to identify the best options, using a process of refining and testing the strategy options.

# Proposed REDD+ Strategy Options

A number of potential strategy options were identified through analysis of existing policies, legal frameworks and plans, as well as stakeholder consultations. This process began with a national workshop on REDD+, held in June, 2010.  One of the conclusions of the workshop was that a study of the feasibility of REDD+ actions in Bhutan should be commissioned by WMD.  The study was undertaken by SNV.  The results of the study were subsequently used as inputs to a  follow-up national workshop on REDD+, held in April, 2012. The proposed key strategy options and activities to address the direct and indirect causes of deforestation and degradation and to promote conservation, sustainable management of forests, and enhancement of forest carbon stocks are provided in Table 2b-1. These strategy options are consistent with the country’s Eleventh Five-Year Plan (2013-2018). The Five-Year Plan lays out the strategy for managing natural resources and the environment to achieve sustainability.

# Evaluation of Strategy Options

An estimate of the potential costs and benefits for the emerging REDD+ strategy are extremely speculative at this stage as no details have yet been prepared for pilot sites where interventions will be tested and potential reductions in carbon dioxide emissions assessed. The WMD-commissioned feasibility study undertaken by SNV applied a cost-benefit analysis (CBA) to assess priority options. A full monetary CBA is not yet possible as the financial details of the funding mechanism are still unclear and evolving. A more qualitative CBA however gives some insights in the balance of the analysis towards beneficial or less attractive. The qualitative CBA was positive as the REDD+ would be a catalyst to build the knowledgebase on the forest ecosystem, which is a necessity beyond the carbon market, and will serve many more objectives.  The quantitative CBA was less clear, but if geared towards multiple benefits and linking the funds to the communities, tends to give a green light for REDD+, under the premise that piloting should prove the actual benefits.

The conclusions of the study indicated that pilot activities which should be supported during the readiness phase in order to identify optimal REDD+ intervention strategies.  Such pilots include:

# Community Forests

CFs are a good trial platform as they already offer an organized and established community with a certified CF management plan and committee. CFs are rapidly growing in number, with now almost300 CFs in Bhutan covering 32,200 ha reaching 13,000 households. Community involvement is guaranteed and the CFs are known for being rather conservative in their extraction from their CF stock, leading to good increment rates and related carbon stock enhancement. The CFs will be an easy pilot to ensure multiple benefits for local livelihoods, conservation and biodiversity. As the CFs are mostly relatively small in area it would be an option to aggregate a number of CFs in a Dzongkhag to reach more household and at the same time build a better economy of scales and learn from the set-up with geogs and Dzongkhags involved in the institutional set-up. Plan Vivo would be a possible partner/ standard, having applied the aggregation approach in different countries. Good lessons could be learned from CF trials going on in Nepal (ref. Karkyand Skutsch, 2010 and Banskota, K., Karky, B.S, and Skutsch, M. (eds.), 2007).

# A National Park

As more than half of Bhutanese territory is under protected area status there is ample scope for trialing REDD+ in a National Park or other protected area. Revenues could be used for community support and park management enhancement.

# Forest Management Units (FMUs)

The FMUs are in principal designed to have a long-term sustainable management plan for 10 years, which can be extended. In practice, implementation is often not sustainable as the annual allowable cut is regularly surpassed and the standing stock impoverished by uncontrolled rural timber allotment extraction and grazing damage, resulting in limited regeneration and leaving often insufficient stock to continue sustainable extraction and with clear forest opening and degradation as effect. There is thus good scope for improvement of forest management towards standards that were initially aimed at in the FMU plan, leading to SFM and better stock enhancement. Improvement of the management of the FMUs would also be instrumental in improving the present apparent imbalance between timber supply and demand in the long run, although on a shorter term this might imply decrease of production volume and an increased imbalance between demand and supply of timber and fire wood.

# Landscape and Market Approaches

The Bhutanese landscapes, with its mountainous watersheds, offer a good opportunity to follow a landscape approach, making use of the natural ecosystem boundaries and structure. In such an approach certain landscape elements as forests with a distinct function and management, as community forests, protected area forests or FMUs, are chosen as pilot areas, but seen as part of a larger system as upslope and downslope relations and upstream and downstream interactions reflect the nested setting of these landscape elements. The benefits of a chosen forest system are thus not only limited to the global carbon sequestration effect and potential climate mitigation, but have leverage through multiple benefits for the broader landscape and the communities making use of the natural resources it contains.

Table 2b-1a shows strategy options and preliminary indications of priority options to address emissions from deforestation and forest degradation.  Given the low historical and current deforestation rates in Bhutan, none of the strategy options to address deforestation are considered as priority options.  Instead, strategies to reduce emissions from forest degradation are prioritized.

Table 2b-1b shows strategy options and preliminary indications of priority options to promote conservation, sustainable management of forests, and enhancement of forest carbon stocks. The priority options relate to conservation and sustainable management of forests.

# REDD Strategy preparation process

# Studies

The development of analytical studies will provide a scientific foundation for the national REDD+ Strategy. Studies will help fill the knowledge gaps about land use, the forestry sector, and the drivers of deforestation and forest degradation. Research will collect relevant information to facilitate the identification of the magnitude of the potential impacts of REDD+ in the country.

Therefore, the following studies will be commissioned in the Readiness phase:

- Risk analysis: A risk analysis framework that summarizes major types of risks, and how significant they are for the major REDD+ strategy activities.

- Feasibility assessments (socioeconomic, political and institutional): More detailed, regional feasibility studies that build on the national feasibility study undertaken by SNV will be undertaken of the proposed options.

# Table 2b-1a: Strategy options to address deforestation and forest degradation

| Eligible REDD+ activity | Direct Causes | Strategy Options | Activities | Comment |
| --- | --- | --- | --- | --- |
| Deforestation | Hydro-power | Ensure policy coordination to minimize negative environmental impacts, including GHG emissions | - Inter-ministry communication and coordination - Incorporation of hydropower plans into National Circumstances | Already occurring – minimal further investment required |
|  | Infrastructure development | As above | As above | As above |
|  | Forest fire | Increased awareness; and improved capacity to manage fire risk | - Awareness raising campaigns for general public - Strengthen fire detection capability Strengthen existing fire control procedures - Develop incentives for forest fire protection | Priority strategy option |
| Degradation | Forest fire2 | As above | As above | As above |
|  | Livestock grazing | Promotion of stall-feeding of livestock | - Awareness raising campaign for farmers - Provision of incentives to promote stall feeding - Enforcement of regulations | Priority strategy option |
|  | Timber harvesting | Improved enforcement of regulations | - Review of existing regulations, and modification if indicated - Strengthen monitoring capacity - Strengthen enforcement capacity | Priority strategy option |
|  | Fuelwood harvesting | Increased regulation over fuelwood collection | - Review of existing processes and rules governing fuelwood, and modification if indicated - Strengthen monitoring capacity - Strengthen enforcement capacity | Priority strategy option |
|  | Illegal logging | Increased capacities for enforcement and prosecution | - Capacity building for field forestry officers - Capacity building for law enforcement officers - Capacity building for the judiciary - Promotion of public knowledge and awareness | Priority strategy option |

# Table 2b-1b: Strategy options to promote conservation, sustainable management of forests and enhancement of forest carbon stocks

| Eligible REDD+ Activity | Current gaps/weaknesses | Strategy Options | Activities | Comment |
| --- | --- | --- | --- | --- |
| Conservation | Weak local community support | Strengthen community engagement and support | - Establish or strengthen co-management structures - Design and implement benefit sharing mechanisms - Raise awareness | Priority strategy option |
|  | Inadequate law enforcement | Strengthen law enforcement | - Capacity building for field forestry officers - Capacity building for law enforcement officers - Capacity building for the judiciary - Promotion of public knowledge and awareness | Priority strategy option |
|  | Inappropriate or inadequate zoning | Review and adjust zoning | - Review current zoning arrangements - Undertake participatory re-zoning where required - Raise awareness | Priority strategy option |
|  | Staffing shortages | Increase staffing levels | - Promote natural resource management/forestry among students - Recruit additional staff - Improve staff incentive system - Strengthen engagement with local stakeholders | Priority strategy option |
| Sustainable management of forests | Regeneration failure | Research on regeneration | - Undertake additional research - Ensure dissemination of improved techniques - Build capacity to apply improved techniques | Priority strategy option |
|  | Non-compliance with timber harvesting regulations | Strengthened enforcement | - Capacity building for field forestry officers - Promotion of public knowledge and awareness | Priority strategy option |
|  | Weak capacities for management of community forests | Capacity development for CFMGs |  | Priority strategy option |
| Enhancement of forest carbon stocks | Inadequate budget particularly for after care (maintenance) | Allocation of sufficient fund | - Propose fund with clear justification | Priority strategy option |
|  | Biotic interference including grazing pressure | Adequate protection till planted saplings are well established | - Focus plantations in larger areas & recruit plantation guards/ caretakers till plantations are established | Priority strategy option |
|  | Low survival rate on bare areas | Research on suitable species and plantation techniques | - Select the right species and techniques for plantation on harsh sites - Training of forest staff on different plantation techniques | Priority strategy option |

- Economic valuation to assess the value of the forest at the national level: this study will analyze values in terms of both direct and indirect values, including ecosystem services; and the contribution of forests to livelihoods.

These studies, and particularly the results of the studies will be communicated to key stakeholders through a consultation process in the next stage of the REDD+ preparation process.

# Consultation

A number of different consultation processes will be implemented to identify and develop REDD+ strategic options, and to allow broad stakeholder review of draft sections of the strategy as it is produced.

These consultations will will include national and Dzongkhag multi-sectoral and multi-stakeholder consultations, including the participation of representatives from the private sector, non-governmental organizations, academia, government officials, local people and local communities.

Consultations are anticipated on core issues of the National REDD+ Strategy, including, but not limited to:

- Institutional arrangements to plan, implement and monitor REDD+ activities e.g. government or other institutions authorized to participate in domestic and/or international transactions based on GHG emissions reductions following reductions in deforestation and/or forest degradation.

- Financing mechanisms for REDD+ activities and transactions.

- Benefit sharing arrangements, especially design elements that will ensure fair and equitable, efficient, effective and transparent operation of the system; revenue allocation measures, payment structure and conflict resolution/grievance mechanisms.

- National registry for REDD+ activities and transactions.

- Capacity building needs for improving technical background knowledge and skills e.g. financial management, accounting, facilitation, negotiation, moderation, planning, monitoring and evaluation skills.

- Regulatory framework e.g. interpretation and use of existing legislation and development of specific legislation to ensure clarity concerning REDD+ implementation.

Criteria to be considered as checklist during implementation for adjustment as appropriate: Presentation and prioritization of REDD+ strategy options

1. Check to see whether REDD+ strategy options are prioritized based on comprehensive assessment of direct and indirect drivers of deforestation (or informed by other factors, as appropriate), and via a transparent and participatory process?

# Feasibility assessment

2. Check to see whether REDD+ strategy options are assessed for their social and environmental feasibility, risks and opportunities, and analysis of costs and benefits?

# Consistency with other policies

3. Check to see whether major inconsistencies between the priority REDD+ strategy options and policies or programs in other sectors (e.g., transport, agriculture) have been identified?

# Integration with relevant strategies and policies

4. Is an agreed timeline and process is in place to resolve inconsistencies and integrate REDD+ strategy options with relevant development policies?

# Table 2b-2: Summary of REDD-plus Strategy Activities and Budget (or Results Framework)

| Output (major activity) |  | Organizations involved | Activities or Sub-activities | Budget allocation in thousand (estimated cost in thousands) |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | 2011 | 2012 | 2013 | 2014 | Total |
| Outcome 1: |  |  |  |  |  |  |  |  |
| Output 1.1 |  |  | 1.1.1 main activity | $ | $ | $ | $ | $ |
|  |  |  | Sub activity 1 | $ | $ | $ | $ | $ |
|  |  |  | Sub activity 2 | $ | $ | $ | $ | $ |
| Output 1.2 |  |  | 1.2.1 Main activity | $ | $ | $ | $ | $ |
|  |  |  | Sub activity 1 | $ | $ | $ | $ | $ |
|  |  |  |  | $ | $ | $ | $ | $ |
| Total |  |  |  | $ | $ | $ | $ | $ |
| Government |  |  |  | $ | $ | $ | $ | $ |
| FCPF |  |  |  | $ | $ | $ | $ | $ |
| UN-REDD Programme (if applicable) |  |  |  | $ | $ | $ | $ | $ |
| Other Development Partner 1 (name) |  |  |  | $ | $ | $ | $ | $ |
| Other Development Partner 2 (name) |  |  |  |  |  |  |  |  |
| Other Development Partner 3 (name) |  |  |  |  |  |  |  |  |

## 2c. REDD-plus Implementation Framework

# Introduction

The REDD+ implementation framework provides comprehensive guidance for the design and implementation of the appropriate institutional, financial, legal and governance arrangements to effectively and efficiently implement REDD+ in Bhutan in accordance with international guidance. Its principles include the basic requisites of REDD+ to ensure credibility and transparent, efficient and effective decision making, implementation and monitoring of REDD+ activities. It should set out the appropriate institutional, financial, regulatory and technical capacities to enable Bhutan to operationalize and implement its provisional REDD+ strategy options to minimize the conversion of forest land into other uses, thus reducing emissions, and equally to introduce actions that will enhance conservation, sustainable management and carbon stock enhancement. In addition, it needs to ensure that REDD+ implementation delivers real (measurable, reportable and verifiable) reductions of emissions from deforestation and forest degradation, in accordance with international guidance (relevant UNFCCC decisions and IPCC guidance and guidelines) and adheres to national development priorities.

Implementation of REDD+ is a multi-sector and multi-stakeholder endeavor and comprises actions at the national and sub-national levels. In Bhutan, three main instruments will be used for REDD+ implementation: institutions, fiscal measures and regulatory framework. In addition, information management will be undertaken to form the basis of the implementation framework. Each of these instruments will be designed to ensure effective implementation.

Specifically, key issues unique to REDD+ implementation that must be resolved during the readiness phase are: institutional arrangements, financial management, benefit sharing system, establishment and operation of carbon registry and information and knowledge management. Stakeholder participation and consultation, including capacity building, are the primary means through which to make well-informed decisions. Stakeholder consultations have been undertaken on the following REDD+ issues to prepare for implementation:

- Institutional arrangements to plan, implement and monitor REDD+ activities e.g. government or other institutions authorized to participate in domestic and/or international transactions based on GHG emissions reductions following the implementation of REDD+ activities;

- Capacity building to improve the knowledge and skills of relevant stakeholders on issues relating to REDD+ implementation e.g. financial management, accounting, facilitation, negotiation, moderation, planning, monitoring and evaluation skills;

- Financing mechanisms for REDD+ activities and transactions e.g. anticipated co-financing which could potentially include potential donor or partner agencies, type of support, and amount of contribution for the R-PP implementation;

- Benefit sharing arrangements e.g. how international REDD+ finance will be shared domestically with diverse stakeholders; benefit sharing schemes based on fair and equitable, efficient, effective and transparent principles; revenue allocation mechanisms; payment structure and conflict resolution mechanisms;

- Registry of REDD+ activities e.g. development of criteria to specify REDD+ project proposals, appropriate protocol standards, establishment of a national registry of projects;

- Regulatory framework e.g. interpretation and use of existing legislation and development of specific legislation to ensure clarity concerning REDD+ implementation.

Importantly, how institutions will actually lead and coordinate across sectors and stakeholder groups, how benefits will be shared fairly and how various interests will be satisfied and/or mediated are key challenges for the success of REDD+ implementation in Bhutan. The process to make required decision jointly during the readiness preparation phase will be the key to ensure effectiveness, efficiency transparency. Like many other countries in the region, building technical understanding among stakeholders on key issues unique to REDD+ implementation in Bhutan will be necessary before initiating activities on the ground.

# Regulatory Framework

REDD+ readiness requires a regulatory framework that ensures consistency with key principles, i.e. transparency, efficiency and effectiveness, to implement REDD+ strategy options. Generally, regulations relevant to implementation of REDD+ strategic options for tackling the drivers for deforestation and forest degradation in Bhutan are now in place through existing forest laws and policies under which the relevant agencies are currently employed. In addition, legal support to ensure that the rights of local people to utilize and manage forest resources is also recognized through several laws, including:

- The Land Act of 1978, which provides for tenure rights over agricultural land and for legal status to grazing land (tshamdo) and forests maintained for leaf manure (sokshing).

- The Forest and Nature Conservation Act of 1995, which recognizes community forests and establishes procedures for their creation and management. The Act also establishes the right of local stakeholders to procure a firewood permit (free of charge).  The Private Forest Rules and Community Forest Rules were developed under the Actin order to encourage local people to grow firewood and construction timber for their own use and as a source of cash income

However, there are important new issues that may require special provisions for the regulation of REDD+, which will need to be developed, consulted upon and issued by the government during the readiness phase.

In Bhutan, the MoAF has ultimate responsibility for forest lands but within the MOAF there are different functional divisions responsible for different aspects of forest and forestland management.

The Department of Forests and Park Services is responsible for forest conservation, ensuring the 60% forest cover figure established by the Constitution is maintained, and empowerment of rural communities for the stewardship and management of local forest resources and NWFPs for income generation and livelihood enhancement.  Six functional divisions within the Department are:

- Forest Protection and Enforcement Division, responsible for forest protection, sustainable management & utilization of land & forest resources

- Forest Resources Management Division, responsible for identifying potential FMUs,  carrying out forest resources inventories, technical backstopping of FMU plan implementation, and preparation of maps and providing quality data related to GIS

- Social Forestry Extension Division, responsible for backstopping the Dzongkhag forestry sectors in effective and efficient implementation of the decentralized forestry activities and enhancing participatory sustainable forest management

- Wildlife Conservation Division, responsible for planning and implementing conservation programs

- Watershed Management Division; responsible for implementing watershed management programmes, functioning as the sector's focal point for environment, climate change, rangeland and wetlands, and therefore responsible for REDD+

- Nature Recreation and Ecotourism Division, responsible for all nature recreational and eco-tourism activities both within and outside the protected areas, and for ,environmental education and awareness to encourage and increase the public support towards conservation.

In addition, the following agencies of the MOAF have mandates that are relevant to REDD+:

Council for Renewable Natural Resources Research of Bhutan (CoRRB) is the apex body responsible for coordination and monitoring of research done by the various agencies under the Ministry of Agriculture and Forests (MoAF).

The RNR Information and Communication Services (ICS) supports village-level activities where the need for information is great. Its role is to support extension and farmer training by producing information materials as well as to publish the RNR Newsletter, design and develop communication materials, and  coordinate with external media for press releases of RNR activities;

The Policy and Planning Division is responsible for providing policy and planning services and for monitoring and evaluation of the various programmes and projects. It is responsible for liaison with donor agencies for mobilising funds and with the other ministries in the government for clearing programmes and projects

Since REDD+ payments will be performance based, regulation(s) for REDD+ will need to safeguard against the risk of REDD+ activities being implemented that will not be able to achieve the expected levels of emission reductions and expected benefits. Such failures could lead to conflicts between stakeholders involved. Thus benefit sharing should also include the sharing of risk and liabilities. To mitigate this risk, a regulatory framework to govern REDD+ transactions and an institutional regime will be formulated and widely consulted upon. This will provide clarity related to key REDD+ issues including clear REDD+ related terminologies in Bhutanese, clear delegation of responsibility for approving all REDD+ activities, the principles for a benefit sharing system and a financial management and distribution mechanism.

In addition, national guidelines will be formulated and widely consulted upon on the process for developing and implementing REDD+ activities, including which organizations, groups and individuals are eligible to implement REDD+ activities and methodologies that should be followed to do so (these guidelines will be at the core of Bhutan’s National REDD+ Strategy).

Legalization of the institutional arrangements outlined in Component 1a as well as roles and responsibilities among government agencies and other involved stakeholders, is also necessary for REDD+ readiness and implementation. This will help ensure transparency and accountability among involved stakeholders. The formulation and implementation of a REDD+ regulatory framework will require a comprehensive legal analysis of existing legislature to ensure overlap and/or conflicts between new and existing laws are avoided and ensure efficiency of REDD+ implementation. It will also require a phased approach to ensure sufficient time is dedicated to broad multi-stakeholder consultations.

# Institutional Arrangements

As indicated in the institutional arrangement in Component 1a, existing institutions and the establishment of new institutions at national government levels to implement the R-PP will be undertaken in a step-wise manner subject to national circumstances to fulfill key functions for REDD+ readiness and implementation. During the REDD+ readiness, the following key steps will be undertaken:

- Establish three technical working groups, dealing with Forest Monitoring, Safeguards, Benefit Distribution and Stakeholder Engagement, and Policies and Measures for REDD+

- Develop a National REDD+ Strategy to guide REDD+ implementation;

- Establish a REDD+ Office to serve as the national implementing government agency; and to fulfill the function of a  REDD+ Information Center to provide transparent and accurate data and information on REDD+ implementation and to work with the Multi-Sectoral Climate Change Task Force;

- Appoint the Protected Area Regional Offices to serve as hubs for Dzongkhag-level REDD+ implementation.

# The institutional arrangements for REDD+ implementation are shown in Figure 2c-1.

# Financial Arrangements

The international rules for the financing of REDD+ actions are yet to be agreed by the UNFCCC COP, though it acknowledged, through Decision 2/CP.17 (paragraph 65), that “results-based finance [for REDD+ actions] provided to developing country Parties that is new, additional and predictable may come from a wide variety of sources, public and private, bilateral and multilateral, including alternative sources”. Nevertheless, prior to the full operationalization of REDD+ under the UNFCCC as part of a post-2020 global climate change agreement, international financial contributions (e.g., FCPF or UN-REDD Programme) and bilateral initiatives will be the primary funding source for Bhutan’s REDD+ readiness phase.

Bhutan’s REDD+ implementation framework in the readiness phase will establish appropriate financial arrangement that will deal with multiple funding sources and ensure that funds are appropriated to intended beneficiaries. The financial arrangements will be designed to address the disbursement of REDD+ benefits to sub-national levels, with particular attention paid to accessibility by local forest-dependent communities and ethnic groups.

Bhutan has a long-standing and very successful trust fund, the Bhutan Trust Fund (BTF).  The BTF was the world’s first environmental trust fund, established in 1992. An endowment of US$20 million was set up as an innovative mechanism to finance conservation programs over the long term in Bhutan. In May 1996, the trust fund was legally incorporated in Bhutan under Royal Charter. Today, it is an effective conservation grant-making organisation autonomous of the government. The trust fund is governed by the Royal Charter of 1996 and a high-level Management Board.  While originally established as a biodiversity conservation fund, the mandate of the BTF has expanded to include economic development issues that have direct impacts on natural environment, such as solid waste management, climate change adaptation strategies, and awareness and education.

One option for management of REDD+ finance would therefore be to establish a REDD+ sub-fund under the BTF.  Alternatively, a new REDD+ fund could be established.  These and other options will be examined during R-PP implementation.

To ensure credibility, transparency, accountability, inclusiveness and efficiency, the REDD+ finance management arrangements will be determined in detail at an early stage during the readiness phase through the TWG on Safeguards, Benefit Distribution and Stakeholder Engagement, in consultation with WMD, the Ministry of Finance and other relevant stakeholders. Further analytical and design work, as well as stakeholder consultations, is required to reach well-informed decision and financial management structure.

# Benefit Sharing Arrangements

Positive incentives from international REDD+ funding sources will have to be shared among eligible stakeholders, with fair and equitable, efficient, effective and transparent benefit sharing system. The benefit sharing system is likely to be complex because of the number of stakeholders involved and the high costs of achieving emission reductions at current carbon value. Payment for Ecosystem Service (PES) at multi-level scheme, international and national scheme, could be beneficial to REDD+ payments and benefit sharing.

Bhutan has some experience with benefit sharing under PES schemes.  A PES Feasibility Study was undertaken by FAO in 2009.  The study identified certain positive conditions for implementation of PES in Bhutan.  For example, there is political will and enabling laws and policies which include specific references to PES as a mechanism for benefit-sharing and more decentralized investment in NRM. Examples of such enabling laws and policies are the Draft Water Act, which specifically identifies the establishment of PES as one of the main sources of revenue for watershed management; the National Forest Policy (2011), which mentions PES as a mean to cover the costs of maintaining and improving watershed services.

The Feasibility Study recommended piloting PES for three different ecosystem services in three locations in the country.  The Wang Watershed was proposed as a pilot of payment for hydropower services; the headwaters of the water system of Mongar were proposed as a pilot of payment for drinking water services, and the Phobjikha valley was proposed as a pilot for ecotourism services.  The drinking water pilot at Mongar began implementation at the beginning of 2011, while arrangements for the ecotourism pilot in the Phobjikha Valley are well advanced.

An analysis of PES practice, community based forest management and other incentive-based conservation programs in Bhutan will be carried out as part of readiness activities and lessons learned from these existing practices will subsequently be incorporated in Bhutan’s National REDD+ Strategy and financial arrangements for REDD+, including benefit distribution. Pilot activities are recommended during the readiness phase to focus on land management practices that affect ecosystem services, in light of unclear rights in ecosystem services and levels of payments for them. Diverse benefit sharing arrangements will be tested during the readiness phase through pilot/demonstration activities.

Eventually a more complex system will be designed and legalized based on experience gained. This will allow for scaling up of REDD+ efforts during the readiness phase and ultimately accommodate a national approach. More importantly, it will ensure that households and communities adopting new practices to implement REDD+ will be able to benefit from technical support and financing to establish the necessary improvements in practices. At the community level, mechanisms to subsidize the development and formalization of associations will be discussed during the readiness phase. Furthermore, other considerations need to be taken into account: appropriate forms of benefits such as direct payments and in-kind contributions; risk minimization and conflict management; and opportunity costs of other land uses as well as assessment of cost effectiveness of different benefit distribution options.

Existing relevant legal framework will be assessed for potential opportunities and bottlenecks, while an enabling legal framework and/or new legal instruments will be drafted during the readiness phase, as an essential prerequisite for successful PES. These processes will be further refined and discussed through extensive stakeholder consultations during the readiness phase by the TWG on Safeguards, Benefit Distribution and Stakeholder Engagement.

# Land tenure and rights to resources related to REDD+

The Forest Act, 1969 had a significant impact on natural resource property rights and provided substantial power to forest officials to protect, manage and control access to the forests. It defined "forest" as "any land under forests in which no person has acquired a permanent, hereditary and transferable right of use and occupancy" and gave the status of reserved forest to all forest land. At the same time it appropriated many areas used as village and community forests as government property.

In 1995, the National Assembly repealed the Forest Act, 1969 replaced it with the "Forest and Nature Conservation Act, 1995".  The revised definition of `forest' under the new act is: "Forest means any land and water body, whether or not under vegetative cover, in which no person has acquired a permanent and transferable right of use and occupancy, whether such land is located inside or outside the forest boundary pillars, and includes land registered in a person's name as tsamdog (grazing land) or sokshing (woodlot for collection of leaf litter)”.

The new act recognizes community forests and deals in detail regarding their creation and management.  Under the community forest rules a group of at least ten households willing to establish, control and manage a forest area as a community forest in accordance with these rules can form a community forest management group (CFMG). The CFMG is authorized under the rules to control the management of the community forest in accordance with the management plan prepared by the CFMG and approved by the dzongkhag administration on the recommendation of the Divisional Forest Officer (DFO). The management plan needs to contain maps of the boundary and various compartments, management objectives, descriptions of forest types and species, an assessment of the forest condition and an inventory of the forest areas. It is often difficult for local people to provide such information for a management plan. Rules provide for no royalty for the bonafide use of forest products from the community forest by the CFMG members. However, if the forest products are sold to outsiders they are then subject to taxation.

The Act of 1995 clearly lays down regulations for the extraction of firewood. An individual has to procure a firewood permit (free of charge) on the basis of the recommendation of the gup and dzongda for procuring firewood either from private or government forest areas. The policy of the government is to encourage the local people to use trees of inferior quality, or ones that are dead or dying, as firewood and this instruction is noted on the permit. A forest official must mark these trees before they can be cut as firewood. The use of unmarked wood/timber is considered an offence and carries penalties. However, with limited staff it is difficult for the forest organization to detect illegal (without permit) harvesting of firewood.

The Land Act of 1978 dealt with tenure rights over agricultural land. It provides for legitimacy for the inheritance of land and protects the tenure rights to property. Registration or recording of land with the government by an individual gives credibility to property rights and acknowledges the rights of the individual farmer over land that he had traditionally cultivated. The same law also changed in-kind tax payments to cash.

The Land Act also provides legal status to grazing land (tshamdo) and forests maintained for leaf manure (sokshing). The Land Act defines tshamdo as land "used for grazing cattle" and "such land can neither be allotted nor sold" but can be requisitioned by the government in time of necessity without paying for it. It defines sokshing as forest used for leaf litter, fodder and manure and the owner has not right over the standing trees and land over which Sokshing has been established. It exempts such types of non-commercial land use from state tax.

# REDD+ Information System and Activity Registry

A key principle of Bhutan’s framework for REDD+ implementation will be transparency. To facilitate adherence to this principle, the DoFPS will establish a REDD+ Information System and Activity Registry. This system will act as the national hub for REDD+ knowledge management and (domestic and international) information sharing. A variety of media will be used to share this information:

- A website that will contain all relevant documentation and latest news on progress with the implementation of REDD+ readiness in Bhutan;

- A web-GIS portal (online mapping tool) that will provide information on the implementation of REDD+ activities in the country, as well as transparently share data on annual deforestation statistics (this will be developed as part of Component 4a);

- A REDD+ Activity Registry will provide information on the location, scope, methods, stakeholders, etc. of all REDD+ activities being implemented in the country.

During the readiness phase, information and knowledge management will ensure accessibility to REDD+ related information to all relevant stakeholders as well as the general public. The Information System and Registry will address critical knowledge gaps through knowledge capitalization and the synthesis of information, as well as facilitate transparency of decision-making and monitoring. The REDD+ Information System will also refine, harmonize and strengthen existing information management related to REDD+ implementation arrangements and efforts in Bhutan as well as the latest information and guidance from the international level (in particular from UNFCCC and IPCC).

# Demonstration Activities

Bhutan’s REDD+ readiness phase will be based on a learning-by-doing approach that will involve the piloting of different methods and approaches and gathering feedback from stakeholders, implementation partners and other relevant organizations and stakeholders. As Bhutan progresses through its readiness phase it will develop systems to manage the implementation and monitoring of REDD+ demonstration activities, including at the subnational level (though it has not yet been determined which scale demonstration activities will be implemented at in Bhutan). A key preparatory activity will be the definition of parameters to select sites for activity piloting and multi-stakeholder consultations to select potential pilot sites; as well as ensuring full awareness and the (voluntary) participation of relevant stakeholders at the local level. Towards the end of the implementation of this RPP, Bhutan will have identified its demonstration sites and initiated local stakeholder engagement activities, and developed preliminary subnational or national (as necessary) forest reference levels and/or forest reference levels (RELs/RLs) for the activities to be implemented.

# Capacity Building

Human resource capacity building and institutional strengthening of relevant government agencies at different levels and other involved stakeholders, including communities, will be a major focus of the implementation of the RPP. A variety of training and capacity building measures to access to data/information, technology transfer, and shared learning will be necessary to meet the needs of all agencies and individuals required to create a comprehensive REDD+ implementation framework. Technical assistance and capacity building proposed at the national and sub-national levels will include:

# National Level

- A series of awareness raising activities to establish a basic understanding of REDD+ as the foundation for specific training activities for government and other institutions;

- The provision of technical information on key REDD+ issues to policy makers as a basis for well-informed decision making (financial and benefit sharing mechanism, RELs/RLs and national forest monitoring system development);

- A series of training events with multi-sectoral stakeholders to create a basic understanding of REDD+ to facilitate 1) cross-sectoral collaboration and 2) the coordination of inputs of different donor initiatives;

- Incorporation of REDD+ and related issues into the tertiary level education curriculum;

- Development of standardized awareness raising materials at different levels.

# Sub-national and Local Level

- A series of sequential awareness raising activities to create basic understanding of REDD+ as a foundation for further specific training measure for local communities;

- A series of technical assistance and capacity building activities on key REDD+ issues to local communities to facilitate REDD+ implementation at local level (e.g. community forest monitoring

It will also be necessary to assess capacities related to REDD+, which will allow a more accurate design of the program for the creation and strengthening of these capacities. Proposed measures and activities related to the different components will be implemented during the readiness phase to establish the outlined REDD+ framework. This will be carried out simultaneously with other actions that also need to be conducted during the readiness phase. The budget summary for the main activities is provided in Table 2c-1.

Implementation criteria to be checked on an ongoing basis for adjustment, as appropriate, will include:

- Adoption of legislation and regulations

  - Assess the extent to which legislation and/or regulations related to REDD+ programs and projects have been adopted.

- Transparent and equitable REDD+ implementation framework

  - Assess whether the implementation framework is operating in a transparent and equitable manner, and whether it defines aspects such as the process for participation in programs, benefit distribution, REDD+ financing mechanism/financial architecture and financing modalities, procedures for official approvals, monitoring systems and grievance mechanism.

- National REDD+ Information System and Activity Registry

  - Assess whether a national geo-referenced REDD+ information system and REDD+ activity registry is operational, comprehensive, transparent and accurate.

| Table 2c: Summary of REDD-plus Implementation Framework Activities and Budget |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Main Activity | Sub-Activity | Estimated Cost (in thousands) |  |  |  |  |
|  |  | 2011 | 2012 | 2013 | 2014 | Total |
|  |  | $ | $ | $ | $ | $ |
|  |  | $ | $ | $ | $ | $ |
|  |  | $ | $ | $ | $ | $ |
|  |  | $ | $ | $ | $ | $ |
|  |  | $ | $ | $ | $ | $ |
|  |  | $ | $ | $ | $ | $ |
| Total |  | $ | $ | $ | $ | $ |
| Government |  | $ | $ | $ | $ | $ |
| FCPF |  | $ | $ | $ | $ | $ |
| UN-REDD Programme (if applicable) |  | $ | $ | $ | $ | $ |
| Other Development Partner 1 (name) |  | $ | $ | $ | $ | $ |
| Other Development Partner 2 (name) |  | $ | $ | $ | $ | $ |
| Other Development Partner 3 (name) |  | $ | $ | $ | $ | $ |

## 2d. Social and Environmental Impacts during Readiness Preparation and REDD-plus Implementation

# Introduction

Activities that reduce emissions from deforestation and forest degradation (REDD) and contribute to conservation, sustainable management of forests and enhancement of forest carbon stocks (REDD+) have the potential to deliver significant social and environmental co-benefits. Strategic environmental and social issues must be considered at the REDD+ readiness stage.  Strategic Environmental and Social Assessment (SESA) is a range of analytical and participatory approaches that aims to integrate environmental and social considerations into policies, plans and programs (PPPs) and evaluate the inter linkages with economic and institutional considerations. The purpose of this component therefore, is to utilize the SESA process to assess the likely impacts of the REDD+ strategy options and implementation framework identified in Sections 2b and 2c or that will be identified in the course of the preparatory work. The objective is that REDD+, starting with the preparation for REDD+ readiness to implementation, should “do no harm‟ and, instead, should “do good‟.

# Social and Environmental Consideration in Bhutan

Article 5 of the Constitution of Bhutan states that at least 60% of the land area of the country must be maintained under forest cover.  Bhutan has an environmental protection act, as well as rules, regulations and guidelines for conducting detailed environmental impact assessments and initial environmental examinations. Bhutan is considering the social and environmental impacts of forest development activities as specified in environmental Protection Act1996 and Environmental protection Regulation 1999. The environmental protection act has special provision for Initial Environmental Examination (IEE) and Environmental Impact Assessment (EIA). Clear felling of forest area, change in species composition, use of forestland in other land use system, introduction of exotic species and implementation of management plan require IEE or EIA.

An initial stakeholder analysis was conducted during the preparation of the R-PP. Possible drivers of deforestation and degradation, and feasible strategic options for addressing those drivers, have also been identified. In addition, specific consultations with stakeholders, including forest-dependent communities and indigenous peoples were also held during the process.

# Social and Environmental Impacts of REDD+

The REDD strategic options proposed in component 2b aim to contribute to reducing GHGs emissions and poverty reduction, and to enhancing economic growth through the sustainable and equitable management of forests while increasing forest carbon stocks. Implementation of these options will involve local forest-dependent communities, ethnic groups, women and youth. Nevertheless, in spite of the positive results expected with regard to efforts against climate change, the launch of REDD+ could have negative impacts on the environment and on local forest-dependent communities. Some examples of possible negative impacts are:

- REDD+ interventions may lead to changes in traditional livelihoods and, in a worst case scenario, make them unviable.

- Many communities located in and around forests depend on forest resources for their economic and social livelihoods without any formal title, leaving open the possibility of abuse of their rights.

- Risks that forest biodiversity may lead to increase in certain wildlife populations and result in damage to agricultural farms.

- Potential conflicts between government agencies and local communities, particularly in resource utilization and land management.

- Centralized REDD+ administration and management may neglect stakeholder participation or imbalance proportion of stakeholders in REDD+ activities.

- Risks of not using local traditional knowledge of communities in REDD+ decision-making process. The need to make sure that REDD+ implementation should not create conflicts with traditional lifestyles and cultural practices.

- Unfair access to financial resources, as some groups may have privileged access to funds, loans and resources for development while others are neglected.

- Inefficient institutional arrangements and policies that may negatively impact on the welfare of the poor to benefit from REDD+.

- Lack of good governance in forest management in the light of corruption and inadequate forest enforcement.

- Reduced emphasis on the importance of biodiversity conservation, as the basis of food security and medicine for local communities, through forest landscape rehabilitation because of over-emphasis on carbon sequestration.

- Reduced emphasis on other ecosystem services in terms of watershed protection, and alleviation of natural disasters

SESA will be conducted to assess the positive and negative impacts that could be generated in the implementation of REDD+ strategic options. SESA will be undertaken through a participatory process involving local forest-dependent communities, marginalized groups, women, and other forest users.

# Institutions that Can Play a Role in SESA and ESMF

Given the multi-sectoral nature of REDD+ mechanism and the varied nature of the causes of deforestation and forest degradation in Bhutan, the SESA process would seek to bring the various perspectives of the ministries and land resource users on potential negative and positive impacts of REDD+. The consultation process during SESA and development of ESMF would involve the following stakeholders at the national and sub-national levels:

- National governments such as Ministries of Agriculture and Forestry, Economic Affairs, Finance, 
Home and Cultural Affairs, and Works and Human Settlement

- Local forest-dependent communities and networks.

- Private sector such as mining, wood processing, agribusiness, etc.

- NGOs

- Research and academia.

# Consultations for SESA

A detailed plan of consultation during the SESA will be developed by the entity that will carry out the study using FCPF framework but also exploring, for example, UN-REDD and CCBA social and environmental standards, principles, criteria and tools for REDD+ where relevant to enhance the process. The main output of the SESA process is the development of a strategic Environmental and Social Management Framework (ESMF).

# Social and Environmental Considerations

The FCPF will be one of the major funding sources for the implementation of R-PP and consideration will be made for fulfilling the World Bank safeguard policies, especially: (i) OP 4.01 on Environmental Evaluation; (ii) OP 4.04 on the Natural Habitats; (iii) OP 4.10 on Indigenous Populations (local forest-dependent communities in case of Bhutan); (iv) OP 4.11 relating to Physical Cultural Resources; (v) OP 4.12 on Involuntary Resettlement; and (vi) OP 4.36 on Forests..

SESA will be carried out during the R-PP implementation which will include stakeholder analysis, description of the initial social and environmental situation of the forest sector and related sectors in Bhutan.

# Foreseeable Tasks to be Conducted during the Readiness Phase

Tasks to be conducted during the Readiness Phase would include scope of assessments and baseline analysis.

SESA will identify the key drivers influencing social and environmental problems. The analysis will take into account past development and the current situation, and the results will explain the future trend of key social and environmental problems if REDD+ is not to be implemented. SESA would identify existing regulations, gaps of institution and competency of personnel in order to avoid undesirable impacts from REDD+ readiness implementation. Other issues are: (i) potential of institutions to facilitate the relationship between REDD+ and social and environmental issues, and (ii) efficiency of mechanisms for integration of social and environmental factors in the forestry sector. This ongoing assessment will be combined with stakeholder consultations.

The initial aim of the SESA is to identify important social and environmental issues and linkage between REDD+ strategic plan, and policies. Preliminary studies combined with SESA consultations, will identify key social and environmental issues relating to REDD+ strategy options, analysis of policy and strategy framework related to REDD+. The review of key social and environmental problems will be linked to prioritization of problems and activities suggested by the REDD+ strategic plan. There will be additional analysis for each identified negative and positive social and environmental impacts. REDD+ strategies and activities will be prioritized in terms of impacts on affected areas by District (Dzongkhag) or Sub-district (Geog). The results and conclusions will be reviewed followed by stakeholder consultation.

# Measures for Impact Mitigation and Efficiency Improvement

The results from SESA analysis will be used to suggest measures for mitigation of negative impact and efficiency improvement for positive impacts in REDD+ strategy options The suggestions may include (i) revision of REDD+ strategic options; (ii) revision of rules and regulations together with institutional management as appropriate, such as revision of policy and strategic plans to ensure the efficiency of REDD+ project implementation; (iii) terms and conditions of REDD+ project implementation; and (iv) stakeholder participation.

# Monitoring Framework

SESA will suggest the monitoring system, reporting pattern and indicators for monitoring of social and environmental impacts from REDD+ strategy implementation.

# Reporting

The results and conclusions from SESA will be summarized in the draft report which will be disseminated to relevant stakeholders.

# Development of Environmental and Social Management Framework

The ESMF is an output of the SESA process. It aims to ensure that REDD+ policy and REDD+ activities “do no harm‟ and, instead, should “do good‟ to all environmental and social aspects. The integration of the Social and Environmental considerations will be handled using the Environment and Social Management Framework tool (ESMF). This tool will be used to guide the process of incorporating the safeguards for identified negative impacts. The tool provides guidance to identify salient environmental and social issues early on, prepare, as needed, remedies and plans to address these issues, and monitor implementation.

# Expertise to be Involved

This assignment requires a multidisciplinary team consisting of experts from various filed of specialization. The proposed expertise may include but not limited to:

- Land use expert

- Lawyer in human rights

- Social and Environmental impacts experts

- Policy Analyst

- Public Participation Expert with long-term experience with organizing public participation and consultation processes related to local forest-dependent communities.

# Criteria to be considered as checklist during implementation for adjustment as appropriate

1. SESA coordination and integration arrangements: Check to see whether the necessary institutional arrangements for coordinating the integration of environmental and social considerations into the REDD+ process are in place?

2. Analysis of safeguard issues: What evidence is there that applicable safeguard issues have been fully identified/analysed via relevant studies or diagnostics?

3. REDD+ strategy design with respect to impacts: How are SESA results and the identification of social and environmental impacts (both positive and negative) used for prioritizing and designing REDD+ strategy options?

4. Environmental and Social Management Framework: What evidence is there that the ESMF is in place and managing environmental and social risks and potential impacts during the REDD+ strategy implementation phase?

The budget summary for the main activities in social and environmental impacts assessment is provided in Table 2d-1.

| Table 2d: Summary of Social and Environmental Impacts during Readiness Preparation and REDD-plus Implementation Activities and Budget |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Main Activity | Sub-Activity | Estimated Cost (in thousands) |  |  |  |  |
|  |  | 2011 | 2012 | 2013 | 2014 | Total |
|  |  | $ | $ | $ | $ | $ |
|  |  | $ | $ | $ | $ | $ |
|  |  | $ | $ | $ | $ | $ |
|  |  | $ | $ | $ | $ | $ |
|  |  | $ | $ | $ | $ | $ |
|  |  | $ | $ | $ | $ | $ |
| Total |  | $ | $ | $ | $ | $ |
| Government |  | $ | $ | $ | $ | $ |
| FCPF |  | $ | $ | $ | $ | $ |
| UN-REDD Programme (if applicable) |  | $ | $ | $ | $ | $ |
| Other Development Partner 1 (name) |  | $ | $ | $ | $ | $ |
| Other Development Partner 2 (name) |  | $ | $ | $ | $ | $ |
| Other Development Partner 3 (name) |  | $ | $ | $ | $ | $ |

# Component 3: Develop a National Forest Reference Emission Level and/or a Forest Reference Level

Rationale: REDD+ is based on a continuous assessment of forest-based greenhouse gas (GHG) emissions. This assessment must be compared against a pre-established benchmark in order to be meaningful. A participating country must determine its Forest Reference Emission Level and/or Forest Reference Level to be eligible to implement REDD+ activities. Standard 3 the R-PP text needs to meet for this component: Develop a National Forest Reference Emission Level and/or a Forest Reference Level Present work plan for how the reference level for deforestation, forest degradation (if desired), conservation, sustainable management of forest, and enhancement of carbon stocks will be developed. Include early ideas on a process for determining which approach and methods to use (e.g. forest cover change and GHG emissions based on historical trends, and/or projections into the future of historical trend data; combination of inventory and/or remote sensing, and/or GIS or modelling), major data requirements and current capacity and capacity requirements. Assess linkages to components 2a (assessment of deforestation drivers), 2b (REDD-plus strategy activities), and 4 (national forest monitoring system design).

# 3.1 Background and Objectives

To date (as of July 2013), the COP of the UNFCCC have published three decisions that provide guidance on forest reference emission levels and forest reference levels (RELs/RLs) for REDD+ activities. The first piece of guidance was published in Decision 4/CP.15, paragraph 7, which states that RELs/RLs should be developed transparently taking into account historic data, and adjust for national circumstances. Decision 1/CP.16 then sets out a ‘national forest reference emission level and/or forest reference level or, if appropriate, as an interim measure, subnational forest reference emission levels and/or forest reference levels’ as one of the four elements that developing countries aiming to undertake REDD+ activities are requested to develop; in accordance with national circumstances and the provisions set out in Decision 4/CP.15. The most substantive guidance on the modalities for RELs/RLs is set out in Decision 12/CP.17 (totalling nine paragraphs and supported by an Annex on ‘Guidelines for submissions of information on forest reference levels’), with some of the key points as follows:

- RELs/RLs should be expressed in tonnes of carbon dioxide equivalent per year and are benchmarks for assessing a country’s performance in implementing REDD+ activities;

- RELs/RLs must be established maintaining consistency with anthropogenic forest-related GHG emissions and removals by sinks as derived from a country’s national forest monitoring system;

- A step-wise approach to RELs/RLs development may be useful to allow countries to improve them by incorporating better data, improved methodologies and, where appropriate, additional forest carbon pools (this modality reflects the phased approach to the implementation of REDD+ activities to allow a learning-by-doing process);

- Subnational RELs/RLs that may cover less than the entire territory of a country may be elaborated as an interim measure while a country transitions to a national REL/RL;

- RELs/RLs should be periodically updated (i.e. revised) to take account of new knowledge, new trends and any modification of scope and methodologies;

- Countries are invited to submit proposed RELs/RLs on a voluntary basis and to make them available on the UNFCCC REDD web platform.

Importantly, Decision 12/CP.17 allows countries the flexibility to exclude non-significant forest carbon pools when developing RELs/RLs and adopt a conservative approach to estimating forest carbon stock changes. The step-wise approach also allows them to develop preliminary RELs/RLs while they continue to collect data and further refine their methodologies.

The objective of this section is to set out how Bhutan will follow UNFCCC guidance and modalities to develop its forest RELs/RLs for REDD+ activities. In doing so, this section will also set out early methodological ideas for RELs/RLs development in Bhutan, identify capacity gaps and requirements and assess linkages to other components of this RPP. This section will have strong links to Section 3 (covering the assessment of drivers of deforestation and forest degradation and the identification and assessment of REDD+ Strategies) and Component 4 (on the design of a national forest monitoring system).

# 3.2 Approach to REL/RL Development in Bhutan

RELs/RLs will be developed in such a way that ensures GHG emissions and removals are directly comparable to the emissions and removals in the national forest monitoring system component, using the same metrics to ensure consistency between RELs/RLs and the national forest monitoring system (see Component 4). Key features of the development of Bhutan’s RELs/RLs will be:

- Methodological consistency: to ensure comparability of all future RELs/RLs;

- Transparency: to ensure that all relevant stakeholders, including those in the international community, have full access to the process and information used in the development of RELs/RLs.

# Implementation arrangements

Step 1: Determination of institutional arrangements for data generation, analysis and sharing. Formal institutional arrangements will ensure transparency and accountability. This is another element of the RELs/RLs component of the RPP that will be intricately linked with the national forest monitoring system component. Only once institutional arrangements have been discussed, consulted upon and agreed by all relevant stakeholders will the government be in a position to proceed with the methodological development of its RELs/RLs.

Step 2: Selection of REDD+ activities (of the five defined under the Cancun Agreements) that the country decides to implement. Each activity may require a distinct national and/or subnational RELs/RLs; the development of which should be consistent with the national forest monitoring system developed through Component 4 – i.e. using the same metrics and ensuring methodological consistency. Nevertheless, because Bhutan will likely need to report on GHG emissions from deforestation regardless of the formal selection of activities (following reporting standards on forest management under the UNFCCC to date), the work on this particular activity’s REL can be initiated immediately.

# Assessment of historical trends

Following UNFCCC guidance, Bhutan will undertake a national assessment of historical trends in land use change using remote sensing data and GIS analysis over a historical period of 20 years, taking four time slices (1990, 2000, 2005, 2010). National land use will be stratified using the land use categories set out by the IPCC (forest land, cropland, grassland, wetlands, settlement and other land), and further stratified according to sub-categories (e.g. for forest land: fmixed conifer, broadleaf, plantation, etc.). These land use categories and sub-categories will be determined by the NFMS Working Group convened under Component 4 of the RPP. The most recent remote sensing data will be used to compile a national forest base map for a set year (e.g. 2013, but to be determined), against which all future land use changes will be measured. This forest base map will be the same one used to monitor REDD+ activities and assess Activity Data under the national forest monitoring system component of the RPP (see Component 4). Emission factors (forest carbon stock change figures), derived from the national forest inventory (NFI), will then be applied to historical land use changes to estimate historical GHG emissions from the land use, land use change and forestry (LULUCF) sector.

# Assessment of National Circumstances

In addition to data on historical forest area change and associated emissions, the development of forest RELs/ RLs requires information on drivers and activities at work and their specific potential contribution(s) to future national emissions. The assessment and reporting of national circumstances is a pre-existing requirement for all UNFCCC parties as part of their National Communication, though there are currently no clear guidelines for their assessment in the context of forestry and REDD+. Another major area of work under this component will therefore be the assessment of national circumstances and a determination of what they mean in the context of adjusting national and/or subnational RELs/RLs (and subject to further guidance from the COP). A first step in this work area will be detailed analysis of the specific drivers of deforestation and forest degradation, which will be carried out under Section 3.

The assessment of expected future developments and changes, in particular those related to forestry, is directly related to specific activities and their underlying causes; assessments should therefore be made separately for each driver of forest carbon stock changes within a country (Herold et al., 2012 ). In cases where assumptions about expected future developments differ from the observed historical trends in forest changes and emissions, these will be fully justified and supported by an explanation of activities and drivers at the national level. Examples of underlying causes of forest cover and quality change include international markets and commodity prices, national population and GDP growth and policies, and local land use trends. Based on existing guidance and pending further guidance from the COP, the assessment of national circumstances could consider the following information (UNFCCC, 2003), inter alia:

- Geographical characteristics (climate, forest area and types, land use, other environmental characteristics);

- Population (growth rates, distribution, density, etc.);

- Economy (GDP, per capita income, income distribution).

# 3.3 Assessment of current data availability and capacities

As part of the preparation of this RPP, a National Forest Monitoring System and RELs/RLs (NFMS/RELs) Technical Working Group will be formed and convened once a month. The NFMS/RELs Working Group will be tasked with identifying and documenting existing data and technical systems; and capacity building gaps and needs. Below are the findings of the assessment of existing data and technical systems.

a)	Remote Sensing and GIS in Relation to Forestry

# Satellite Land Monitoring System

No single government agency in Bhutan has sole responsibility for land monitoring. The following institutions, agencies and organizations have a mandate for producing and managing national RS/GIS data:

- National Land Commission Secretariat (NLCS)

- MoAF: Department of Forests and Park Services (DoFPS)

- MoAF: Department of Agriculture (DoA)

# Remote Sensing and GIS Data

The following datasets are currently available:

- Boundaries (.shp and .img formats)

  - Administrative

  - Parks, sanctuaries and biological corridors

  - FMUs

  - Working schemes

  - Community forests

  - Private forests

  - Road networks and other infrastructure

- Digital elevation model (DEM): ASTER DEM (30m resolution)

- LUPP 1995

- LCMP 2010

- TCC layers – preliminary

- Fire data (based on MODIS (250m resolution) and Landsat (30m resolution) data)

- Digital contours (40m resolution)

- Bhutan’s standard coordinate system (DRUKREF-03)

- Cadastral data: ongoing (NLCS)

- All NFI plot sites

# RS/GIS Human Capacities, Software and Needs

The GIS Section housed in the Forest Resources Management Division (FRMD) currently hires two full-time GIS technicians (headed by a Senior Forestry Officer with an MSc in RS/GIS). The technicians use both licensed (AcrGIS version 9.3) and open-source (Quantum-GIS) software.

Five key areas have been identified as urgent RS/GIS needs by MoAF:

- Establishment of a comprehensive national GIS infrastructure;

- Land cover mapping at regular intervals to monitor changes;

- Web-based GIS data sharing;

- Technical capacity building of staff;

- Increase of RS/GIS staffing levels.

# Current Activities

# Land Use Planning Project (LUPP) 1995

In 1995, the MoAF undertook a national assessment of land cover based on SPOT images from the years 1989 and 1990, with all images being classified manually. The output map is shown in Figure 3-1.

# Figure 3-1. Land cover map produced through the LUPP 1995.

# Bhutan Land Cover Assessment (LCMP) 2010

The LCMP 2010 was carried out to update the national land cover map and figures produced by the 1995 LUPP, using ALOS images (AVNIR-2) with 10m resolution which were subsequently ground-truthed for accuracy. The assessment divides forest land into two sub-classes, conifer and broadleaf, which are further classified into six categories, as per Table 3-1).

# Table 3-1. Forest cover figures based on the LCMP 2010.

| Land Cover Class | Sub-class | Total Area (ha) | Proportion of Total Land Area (%) |
| --- | --- | --- | --- |
| Forest | Fir forest Mixed conifer forest Blue pine forest Chir pine forest Broadleaf forest Broadleaf and conifer forest | 183,208 613,964 80,024 107,667 1,668,956 31,472 | 4.7 16.0 2.1 2.8 44.0 0.8 |
| Shrubs | Shrubs | 4,005 | 10.4 |

The product of this assessment (see Figure 3-2) has produced a sound and accurate land cover baseline to inform future land cover change analyses. Current official land cover figures are based on this assessment.

# Figure 3-2. Land cover map produced through the LCMP 2010.

# Tree Canopy Cover (TCC): 2012-going

TCC is an ongoing initiative to map forest cover in Bhutan, which is being carried out in partnership with the US Forest Service and NASA. Under this programme, extensive training will be delivered on integrating forest mapping and monitoring into the NFI; and assistance will also be delivered to neighbouring countries. The specific objectives of this mapping effort include:

- Adaptation of US Forest Service tree canopy cover mapping model for use in Bhutan;

- Development of tree canopy cover map products;

- Validation of tree canopy cover results;

- Transfer of technical expertise to Bhutanese specialists for Eastern Himalayan regional application.

# Figure 3-3 shows an initial output from the ongoing TCC initiative.

# Figure 3-3. Tree canopy cover map of Bhutan, 2012.

# Monitoring Trends in Burn Severity (MTBS)

To better understand the incidence and impacts of fire, and to improve fire planning and management efforts, a fire occurrence map and individual burned area analyses are being developed for Bhutan. Historical fire occurrence maps are being produced using MODIS and Landsat data; and fires affecting areas greater than 200ha are being mapped individually, using a method adapted from the US Forest Service. The method is adaptable to diverse biophysical settings and characterizes fire effects due to detectable changes in living and non-living biomass, including ash and soil exposure.

b)	Carbon Stock Data

Forest carbon stock data is currently being collected through the NFI. For background on NFI in Bhutan, see Component 4a. For the development of preliminary RELs (for activities to reduce emissions from deforestation and/or forest  degradation (at the subnational or national level, as appropriate to demonstration activities), conservative default emission factors will be applied. These will be discussed and set by the NFMS/RELs Technical Working Group.

# 5.4 Description of Activities

# Output 1: Capacity building and review of methodologies for establishing RELs/RLs

Current knowledge of RELs/RLs is limited in Bhutan. In addition, little guidance currently exists on methodologies to establish national and/or subnational RELs/RLs. Existing guidelines and methodologies, as well as lessons learned from other countries, will be collated and reviewed to determine the best practice approaches Bhutan can/will take when developing its own RELs/RLs. This will involve capacity building/awareness raising events, consultations with national and international organizations and research institutes that are working on diverse approaches to REL/RL development.

Under this output, the following activities will be implemented:

- RELs/RLs capacity building workshop held with stakeholders;

- Study carried out into the context of REL/RL implementation in Bhutan and methodological options available;

- Stakeholder consultation workshop to present findings of the REL/RL methodological study;

- Consultations to determine which methodologies to pilot at demonstration sites.

Expected outputs/results:

- Raised capacities of stakeholders on RELs/RLs;

- Report on RELs/RLs methodologies being used in other countries, including assessment of feasibility of application of these methodologies in Bhutan;

- Methodologies to developed and tested at demonstration sites.

# Output 2: Analyze historical land use change trends at the national scale

This activity will be directly linked to the assessment of activity data as part of the development of the national forest monitoring system (see Component 4a), using remote sensing data and GIS analysis to calculate spatially-explicit historical land use changes. The remote sensing analysis will also be used to stratify land uses and forest types by eco-region, which will feed into the development of RELs/RLs for different forest types and/or for different REDD+ activities. This output will involve training as set out in Component 4.

- See activities under Component 4a Output 2;

- Historical annual emissions calculated using emission factors from national forest monitoring system (Component 4a) (with default values used as an interim measure).

Expected outputs:

- Historical land use (change) analysis for Bhutan completed;

- Emissions factors applied to historical changes to generate assessment of historical emissions from LULUCF.

# Output 3: Review relevant national circumstances and collect data

Evaluating Bhutan’s national circumstances will be based on variables including: (i) analysis of existing and historical social, political and economic data and trends; (ii) existing conservation laws and policies; (iii) analysis of projected future development in Bhutan (iv) vulnerability to climate change and adaptive capacity; and (v) potential forest cover and carbon stock changes through a consultative process. This will also involve: (a) a further assessment of land-use policy, forest policy and governance conducted through the RPP process with appropriate institutional structures and arrangements (under Components 1a, 2c and 2a), and (b) new assessments undertaken as part of the REDD+ Strategy analysis to be conducted during R-PP implementation under Component 2b. A key work area will be an in-depth study of the drivers of deforestation and forest degradation (Component 2a), which will not only inform the development appropriate policies and measures to implement REDD+ activities, but also shed light on specific national circumstances surrounding forestry and the implementation of REDD+ activities in Bhutan.

In combination with historical data, the above aspects will constitute the tool on which to base national decisions for the establishment of RELs/RLs. Collating information on these aspects will provide the opportunity to harmonize REDD+ with Bhutan’s conservation goals, sustainable development priorities, objectives and projects, and circumstances that will have a significant impact on the successful implementation of REDD+ activities within the broader context of national development. It will also create a platform to promote a better understanding of the country‘s vulnerability and adaptive capacity to deal with adverse effects of climate change.

Under this output, the following activities will be implemented:

- Assessment of the drivers of deforestation (see Component 2), including policy and land use governance context;

- Stakeholder consultation workshops and seminars to present findings of the study on national circumstances;

- Development of potential RELs/RLs adjustment factors.

Expected outputs:

- Detailed assessment of the national circumstances of Bhutan in the context of forestry and REDD+, including the drivers of deforestation and forest degradation in Bhutan;

- Potential/pilot RELs/RLs adjustment factors.

# Output 4: Pilot and test national and/or subnational RELs/RLs at demonstration sites

In years 3 and 4 of the REDD+ Readiness RPP implementation process, wide stakeholder consultations will be held to determine concrete proposals for REL/RL formulation, including the REDD+ activities to be piloted (and therefore for which RELs/RLs will be formulated), the locations for implementation and different methodologies to be used/tested. This will involve extensive consultations with technical experts (government and non-government) as well as stakeholders at proposed sites of demonstration activities, and will therefore be closely linked to Component 2b. This activity will lead to the identification of sites for piloting RELs/RLs development at the subnational level and subsequent development and testing of preliminary RELs/RLs to accompany activity piloting.

Under this output, the following activities will be implemented:

- Consultations with stakeholder and technical experts to collate proposals for, and select, pilot sites;

- Develop national and/or subnational RELs/RLs for demonstration activities and submit to the UNFCCC Secretariat for review;

- Pilot selected RELs/RLs methodologies at demonstration sites;

- Gather feedback and lessons learned, and refine methodologies as appropriate.

Expected outputs:

- Proposals for locations of pilot sites where RELs/RLs methodologies will be tested;

- Preliminary national and/or subnational RELs/RLs and feedback on the methodology used from the UNFCCC;

- Lessons learned and feedback from implementation;

- Refined RELs/RLs methodology/ies.

# 5.5 Indicative Work Plan and Budget

| - National Programme Components | Participating donor organization | Implementing Partner | Indicative readiness activities | Estimated cost (in thousand US$) (over 4 years) |
| --- | --- | --- | --- | --- |
| Component 3: Develop and pilot national and/or subnational forest RELs/RLs |  |  |  |  |
| 5.1 Capacity building and review of methodologies for establishing REL/RLs |  | WMD | - REL/RL capacity building workshop held with stakeholders - Study carried out into the context of REL/RL implementation in Bhutan and methodological options available - Stakeholder consultation workshop to present findings of the REL/RL methodological study - Consultations to determine which methodologies to pilot at demonstration sites | 150 |
| 5.2 Analyze historical land use change trends at the national scale |  | DoF | - See activities under Component 4a land use change analysis activities - Historical annual emissions calculated using emission factors from national forest monitoring system (Component 4a) | 20 |
| 5.3 Review relevant national circumstances and collect data |  | WMD | - Assessment of the drivers of deforestation (see Component 2), including policy and land use governance context - Stakeholder consultation workshop to present findings of the study on national circumstances - Development of potential REL/RL adjustment factors | 100 |
| 5.4 Selection of demonstrations sites for piloting and testing of national and/or subnational RELs/RLs |  | WMD / DoF | - Proposals for locations of pilot sites where RELs/RLs methodologies will be tested - Preliminary national and/or subnational RELs/RLs and feedback on the methodology used from the UNFCCC - Lessons learned and feedback from implementation - Refined RELs/RLs methodology/ies | 250 |
| Total |  |  |  | 520 |

# Component 4: Design Systems for National Forest Monitoring and Information on Safeguards

## 4a. National Forest Monitoring System

# 4a.1 Background and Objectives

# UNFCCC COP Decision 4/CP.15 establishes the REDD+ MRV requirement by requesting Parties (paragraph 1(d)) to:

# “…establish, according to national circumstances and capabilities, robust and transparent national forest  monitoring systems and, if appropriate, sub-national systems as part of national monitoring systems that:

- Use a combination of remote sensing and ground-based forest carbon inventory approaches for estimating ... anthropogenic forest-related greenhouse gas emissions by sources and removals by sinks, forest carbon stocks and forest area changes;

- Provide estimates that are transparent, consistent, as far as possible accurate, and that reduce uncertainties, taking into account national capabilities and capacities;

- Are transparent and their results are available and suitable for review as agreed by the Conference of the Parties”.

# Decision 4/CP.15 also specifies that countries must follow the most recent methodological recommendations issued by the IPCC, serving as a basis for estimating the sources of anthropogenic GHG emissions, and their removal by sinks, and for measuring carbon stocks and changes in forest area. In this way, emissions estimates will be based on common (IPCC) methodological approaches. This  methodological guidance indicates that national forest monitoring systems should be used to: 1) estimate emissions and removals from the forest sector (measurement); 2) report this mitigation performance of REDD+ activities to the UNFCCC (reporting); and 3) allow verification of the results by the UNFCCC Secretariat (verification) (subject to further guidance from the COP) – i.e. to fulfil the MRV function for REDD+ activities.

# UNFCCC guidance on this technical element for REDD+ is built upon in Decision 1/CP.16, where developing countries aiming to participate in REDD+ are requested to develop (paragraph 71(c)):

- “A robust and transparent national forest monitoring system for the monitoring and reporting of the [REDD+] activities ..., with, if appropriate, subnational monitoring and reporting as an interim measure, in accordance with national circumstances, and with the provisions contained in decision 4/CP.15”.

# Decisions 4/CP.15 and 1/CP.16 together establish that countries should develop a national forest monitoring system to serve the dual functions of monitoring and MRV, as shown in Figure 4a-1. As the figure indicates, the monitoring function of the national forest monitoring system may include wider elements including community monitoring and traditional forestry monitoring systems. Community monitoring will form an integral part of the monitoring system as communities will provide ground-level information (e.g. tree counts and locations, delimitation of community forest areas), which will feed into the web-GIS interface. Traditional forest monitoring systems are a critical consideration as the national forest monitoring system aims to build on existing systems and be based on national circumstances; these will therefore also be incorporated into the monitoring function for REDD+.

# Figure 4a-1. The dual functions of the national forest monitoring system for REDD+.

# The monitoring function will allow a country to assess whether REDD+ activities are resulting in positive outcomes, according to proxy indicators such as forest cover change; while the MRV function will assess the mitigation performance of REDD+ activities (Figure 4a-2), i.e. by allowing the assessment (following international standards) of whether REDD+ activities are contributing to measureable carbon mitigation.

# Figure 4a-2. The IPCC’s methodological approach to calculate anthropogenic GHG emissions by sources and removals by sinks related to forest land.

# The implementation of the technical components of the national forest monitoring system will be implemented through the three-phased approach. This allows time to build the necessary capacity, learning lessons and improving the systems, as necessary:

- Phase 1: Capacity building on, and design of, technical elements (e.g. Satellite Land Monitoring System, remote sensing, forest inventory); establishment of institutional arrangements; activity planning; design of demonstration (pilot) activities.

- Phase 2: Implementation and monitoring of (and learning from) demonstration activities, and further capacity building on technical elements.

- Phase 3: Satellite Land Monitoring System is upgraded to monitor national performance of REDD+ policies and measures; full MRV in place for assessing GHG emissions and removals in the forestry sector and to report mitigation performance to the UNFCCC Secretariat.

# The objective of this chapter is to set out how Bhutan will follow the above UNFCCC guidance and modalities to develop its national forest monitoring system for REDD+.

4a.2 National Forest Monitoring System Development and Implementation in Bhutan

# Institutional Arrangements

The first step towards the development of Bhutan’s national forest monitoring system will be the determination of transparent and effective institutional arrangements for 1) the production and sharing of land use monitoring and forest carbon stocks data, 2) compilation of the national GHG inventory for the LULUCF sector, and 3) compilation and reporting of the National Communication to the UNFCCC. Transparent and accountable institutional arrangements will be essential to ensure the effective functioning of the system; the Government of Bhutan will therefore aim to formalize these arrangements through a legal act to ensure long-term accountability and sustainability of the national forest monitoring system.

Discussions held during a national NFMS workshop in November 2012 led to the proposal of the institutional arrangements set out in Figure 4a-3. The institutions indicated in the boxes are proposed to act as the lead government agencies/institutions for each of the respective components of the national forest monitoring system; namely: the Department of Forest (DoF) for the Land Satellite Monitoring System; the Forest Resources Management Division (FRMD) of MoAF for the National Forest Inventory; the National Environment Committee (NEC) for the National GHG Inventory for the LULUCF sector; and NEC for the compilation and reporting of the National Communication to the UNFCCC. In and around these arrangements will be integrated specific Quality Control processes (as set out by the IPCC) and an overall Quality Assurance assessment, that should be carried out by an independent third party. Under these arrangements activity data, emission factors and GHG emissions data should be shared between the involved institutions to maximize transparency and openness.

The institutions listed in the figure will act as lead entities for their respective components, though this does not preclude the receipt of additional technical and capacity building support from other national and international agencies and institutions, for example for the collection and analysis of data.

A first step in the implementation of the REDD+ Readiness Roadmap will be to formalize these arrangements among relevant institutions and stakeholders, followed by the publishing of the agreed institutional arrangements proposal in Bhutan’s National Forest Monitoring System Action Plan – see next section.

# Figure 4a-3. Proposed institutional arrangements for Bhutan’s National Forest Monitoring System.

# Capacity Building Planning for the National Forest Monitoring System

In order to specify in detail the steps that Bhutan will take to develop and implement its national forest monitoring system, the Forest Department will lead on the formulation of a National Forest Monitoring System Action Plan (NFMS-AP) document. This document will set out the actions that the country will undertake, in the context of the provision of adequate and predictable support, including financial resources and technical and technological support, to implement its national forest monitoring system for REDD+ activities. The NFMS-AP is likely to include sections on the following:

- Detailed capacity assessment of RS/GIS, forest inventory and GHG inventory, both in government and non-government entities; and support received to date;

- Guidance on the phased implementation of the national forest monitoring system, from concretizing institutional arrangements and capacity building (Phase 1) to demonstration and monitoring (Phase 2) to full national monitoring and MRV for REDD+ activities;

- A timeline for the implementation of activities;

- A budget.

4a.3 Data Availability and Capacity Building Needs

Preliminary ideas on methods to be employed and systems to be developed are outlined below; but will be subject to change based on the results of national and subnational consultations.

- Forest monitoring

# Remote Sensing and GIS

# Details of existing data, capacities and activities on RS/GIS are set out in Component 3.

The Satellite Land Monitoring System (SLMS) will be developed to fulfill two roles. The first is the monitoring of REDD+ activities, which is necessary in order to assess whether activities are being implemented effectively. Consultations will be undertaken to determine the proxies that will be most useful to monitor the activities, depending on which REDD+ activities are selected for implementation and where. To fulfill this role, staff of the DoF will require training on proxy-based forest monitoring, including training on appropriate software. Among others, the application of open-source software such as TerrAmazon, developed by the Government of Brazil, will explored.

The second role of the SLMS will be to produce activity data to feed into the national GHG inventory for the LULUCF sector. This role will require a national analysis of land use change based on the IPCC categories and methodologies. This form of land use change analysis has to date not been completed at the national level in Bhutan. Training will therefore be required for relevant technical staff on IPCC guidance and guidelines, as well as appropriate software and other tools.

# Forest Monitoring Data Sharing

There is currently no national mechanism or tool in place in Bhutan to openly and transparently share forest information. Key features of the national forest monitoring system will be 1) open-access data sharing and 2) ability to feed-back data, information and/or corrections, as necessary, to the centralized system. One method which will be used to share forest monitoring data and information at the national and international level will be a web-GIS portal, through which any internet user will be able to view forest information through an GIS mapping interface, including viewing of forest areas and types, deforestation statistics, forest governance structures, etc. Staff of the DoF will require capacity building on the building, hosting and management of the web-GIS portal, including data uploading and editing processes.

# Other Forest Monitoring Methods and Approaches

While there are legal provisions for community forest management in Bhutan, forest monitoring activities are currently not carried out at the community level. Nevertheless, the community forest management infrastructure in place is likely to facilitate the integration of local-level monitoring activities which will provide critical data and information for Bhutan’s NFMS. Local monitoring information could include tree counts, delineation of forest areas and GPS routes of monitoring/patrolling activities.

Consultations will be held to decide the ways in which non-RS/GIS forms of forest motoring will be incorporated into the NFMS, including the potential role and function of community forest monitoring. Training workshops will then be held for the national- and subnational-level stakeholders who will be participating in this monitoring, including on how to collect data and information and feed it up to the national level.

- National Forest Inventory

# Historical Context

The Department of Forests and Park Services (then referred to as the Department of Forestry) was established in the year 1952. Up until the early 1980s, the department was manned by Indian Foresters on deputation along with Bhutanese counterparts, given the limited national capacity at that point in time. At that point, the extent of forest area and the wealth of the forest resources were not quantified and therefore no definite figures were available. It was however acknowledged that “three fourths of the country was under forests, alpine pastures, exposed rocks and barren slopes” (PIS-North western Vol.I, Preface).  Further, forest resources then did not have much economic value and it was not until the 1960s that the forests were valued economically when the valleys were opened up by roads and economic development began to expand.

As awareness of the importance of forests grew with the realization of its potential to contribute to the economy of the country, the Royal Government of Bhutan began inviting experts from countries including Sweden, Japan and India to measure the forest resources and all experts identified the need for a detailed forest survey.

This need was subsequently pursued as part of the Third Five Year Plan (1971-76), during which time the Pre-Investment Survey (PIS) of Forest Resources of India (now referred to as the Forest Survey of India), under Ministry of Agriculture and Irrigation of Government of India, was requested by the Royal Government of Bhutan to assist Bhutan in surveying its forest resources.

The field work for the PIS began in the 1974 and continued until December 1979, covering a total area of 29,176 km2. The survey was focused more towards “assessing the availability of the raw material for wood based industries”. The PIS generated estimates for number of stems/ha, volume table, volume per hectare, totals growing stock, regeneration status and increment. The report of the PIS proposed the potential availability of wood resources for setting up wood based industries in Bhutan based on the information gathered. Volume equations for 28 major timber species were also determined from the PIS effort along with forest type maps at 1: 50,000 scale for the country.

While PIS was being carried out, the department also pursued technical capacity building of its staff in timber management planning with the assistance of UNDP and FAO. Harry J. McCarty, a Forest Management Consultant was engaged to develop the Forest management inventory designs, and document and build national capacity.

The  PIS was the first NFI in Bhutan which was followed by a number of assessments using remote sensing technologies but no field inventory has been done since then, owing to various reasons including lack of financial and technical capacities. The assessments based on remote sensing data provided forest extent and coverage but lacked the capacity to make quantitative assessments of the forest resources.

# Current Status

Bhutan started the National Forest Inventory field work in 2012 ,based on the methodology developed through series of consultative workshops and meetings with national and international experts and completed.  Out of twenty districts segregated into four regions, namely Western Region, Eastern Region, Central region and Southern region , Department of Forests and Park Services of Bhutan have  by now completed data enumeration from three districts of the Western region comprising of 144 cluster plots or  six percent of the total sample plots to be enumerated. The data enumeration from the Western Region is being supported by Royal Government of Bhutan, Bhutan Trust Fund For Environment Conservation and EU and is expected to be complete by 2014. Bhutan is simultaneously exploring for financial support for the rest of the three regions comprising of 1586 cluster plots covering three fourth of the country.

# Bhutan has 60 dedicated forestry personnel trained as NFI field crew members.

# Methodology

The methodology for Bhutan’s new NFI, which was completed in 2011, was determined through two technical exercises. Exercise I was a remote sensing-based exercise, which classified the land into forest and non-forest using the 1995 Land Cover Map of Bhutan (LUPP 1995 – see Component 3 for more details). The forests were then classified into homogenous forest type categories.

In Exercise II, the data of forest resource inventory plots (approximately 4500 plots of 0.05 ha) from 13 Forest Management Units (FMUs) were analysed to determine the sampling intensity required for achieving a 15% Margin of Error at 90% confidence interval. The sampling intensity was thus used to estimate the total number of cluster plots, which totalled 26,935 cluster plots at 1.2 km systematic spacing. However, in consideration of available human resources and financial limitations, it was decided that a 4km x 4km grid would be used for the NFI sampling framework, following numerous consultations with experts from within the department, Yale University School of Forestry and Environmental Studies, and the US Department of Agriculture-Forest Service. This framework demands one sample location for every 160 ha and comes to 2,424 cluster plots covering all land cover classes, as decided by stakeholders during a Data User Consultation Workshop held in January 2009. This framework will provide reliable estimates at 15% Margin of Error for basal area at 90% confidence interval at the district level and greater precision at the national level.

The data collection parameters were discussed during the Data User Stakeholder Consultation Workshop, through which it was decided that Bhutan’s NFI will collect data and information not limited to timber but also capture wide ranging information on Non-Timber Forest Products (NTFPs), shrubs, herbs, biomass, wildlife, biodiversity, forest health and disturbances. Specifically, the targeted outputs of the NFI are:

- Stems per hectare and total number of stems

- Basal are per hectare and total Basal area

- Volume per hectare and total volume

- Biomass per hectare and total biomass

- Carbon per hectare and total above ground carbon

- Increment and growth

- Regeneration

- Forest stand structure

- Distribution of plant species

- Biological diversity (using indicators like species richness indices, species diversity indices, ecological similarity/dissimilarity indices)

- Coarse wood debris (CWD) per hectare and total CWD

- Cover percent of identified Non-Wood Forest Produce

- Cover percent of bamboos

- Geo referenced  locations of bamboo populations

- Distribution of  wildlife

- Extent  and types of forest disturbance

- Land use information

- Health of forests (pests and diseases)

- A soil map

- Tree Canopy Cover percent Map, Forest Cover Map, Forest Type Map

Each inventory plot consists of a cluster of three circular plots on an L-shaped transect spaced at 50 m apart laid systematically on a 4km x 4km grid. These circular plots will be referred to as Elbow Plot, North Plot and East Plot as shown in the diagram (Figure 4a-4).

NORTH PLOT

ELBOW PLOT

EAST PLOT

12.62m radius

Regeneration plot of 3.57 m

Herb plot of 0.57 m radius

50m

50m

CWD from 50m transect

5m by 5m shrub plot

1m by 1m herb plot

20cm by 20cm soil plot

NFI Cluster Plot

Forest Understorey carbon plot

# Figure 4a-4. Cluster plot as used in Bhutan’s NFI.

Each circular plot will be of 12.62 m radius with an area 0.05 ha for collecting tree data. The Elbow Plot will have an additional circular plot of 3.57 m radius within it, for collecting regeneration data; and a circular plot of 0.57 m (1 m2) radius will be laid in North and East plots for collecting herb data.

For the Forest Understorey Carbon Assessment, plots will be laid 20m south-west from the center of Elbow plot, wherein a 5m x5m plot will be laid for shrubs. All shrubs falling within this plot will be harvested at ground level, then weighed and the samples will be taken to laboratory for carbon analysis. Within the 5m x5m plot, a 1mx1m herb plot will be randomly placed, from where all grasses and herbs will be clipped to ground level and carry the samples/subsamples for analysis.

In the same 1mx1m plot, a 20cmx20cm plot will be randomly constructed for litter and soil sample collection. The organic litter sample will be collected first followed by soil samples from 0-10cm, 10-20cm and 20-30cm depths in the same 20cm x 20cm plot. All the samples will be collected and taken to the laboratory. The soil samples will be analysed for bulk density and carbon content. The methodology employed has been developed with the technical assistance of USDA-Forest Service, Washington University and Yale University.

Assessment of carbon stocks in trees will be done using species-specific allometric equations to be developed using Randomized Branch Sampling technique.

# Capacity Building and Implementation Support Needs

The implementation of Bhutan’s NFI is currently underway, yet some important capacity (building) gaps remain that require filling in order for the first cycle of the new NFI methodology to be completed, and to apply the data for REDD+ MRV. Firstly, there is need for the development of biomass allometric equations for at least 50 key tree species, for which destructive sampling methods will need to be applied. Secondly, additional support is required for assessment of forest understorey (shrubs, herbs, litter) and soil carbon, which requires specialized field and laboratory equipment and capacity building as per the methodology described under 4.3.(b) National Forest Inventory. Thirdly, a NFI database management system is required for the analysis and archiving of NFI data. Work has been initiated with FAO on this work area, but further development, implementation and capacity building is required. Finally, Bhutan requires further support to continue the implementation of the NFI and ensure the continued capacity building of its field staff, as funding of the NFI and associated staff training is currently not guaranteed by the government.

- Forest-Related National GHG Inventory in Bhutan

All country Parties to the UNFCCC are requested to estimate and report on forest-related GHGs by sources and removal by sinks (Decision 4/CP.15, paragraph 1(d) and (d) (i)). Information published in GHG inventories allows the COP to observe progress achieved by the Parties in fulfilling their commitments and achieving the ultimate objective of the Convention.

The quality of a GHG inventory depends not only on the robustness of the results from the measurements made and the credibility of estimates, but also on the manner and method in which the information is collated and presented. Information should be documented coherently following the reporting the guidance of the UNFCCC. Countries should follow the most recent IPCC guidance and guidelines, as adopted or encouraged by the COP, as a basis for estimating anthropogenic forest-related greenhouse gas emissions by sources and removals by sinks, forest carbon stocks and forest area changes in order to comply with the five GHG inventory reporting principles: Transparency, Coherence, Comparability, Completeness and Accuracy.

# National Communication

Parties to the Convention must submit national reports on their progress on implementing the Convention to the UNFCCC COP. The core elements of the national communications are information on emissions and removals of GHGs and details of the activities a Party has undertaken to implement the Convention. National Communications usually contain sections on national circumstances, vulnerability assessment, financial resources and transfer of technology, and education, training and public awareness.

# Central National GHG Inventory Archiving System

An archive system is a critical tool to underpin the sustainability of the National GHG Inventory System by ensuring that GHG estimates can be easily (re-)produced, safeguarding against data and information loss, and allowing replicability of estimates.

# Current Status

The Government of Bhutan submitted its Second National Communication (SNC) to the UNFCCC in November 2011. The report was prepared by then NEC with the support of the Global Environment Facility (GEF) through UNDP, and used 2000 as the inventory year. Default values from the IPCC’s global Emissions Factor Database (EFDB) were used to compile the forestry sector inventory; and the 2006 IPCC Guidelines for National Greenhouse Gas Inventories were followed for the compilation of the inventory report.

# Capacity Building Needs

Capacity building is required for technical officers in MOECAF and MOAI on IPCC guidance and guidelines for GHG inventory compilations, as well as software tools that can be used to support inventory compilation, such as the US Environmental Protection Agency’s (EPA) Agriculture and Land Use (ALU) tool, and database development and management, including QA/QC procedures.

- NFMS-Related Scientific Research

# Potential Research Areas

# Following initial awareness raising and capacity building on REDD+, internal and external consultations and discussions will be undertaken into potential new research areas to support the implementation of REDD+ in Bhutan, and in particular the multipurpose NFI and community forest monitoring. In particular, the development of country-specific allometric equations for 50 key tree species, as identified above, is a central potential area of necessary research for the operationalisation of the NFMS.

# 4a.4 Description of Activities

# Output 1: Capacity Building and NFMS Action Plan Development

# The first step towards the development and implementation of Bhutan’s NFMS will involve general awareness raising on the components of the system as well as in-depth training workshops on the specifics of each of the components, at national and subnational levels. This output will include the hiring of an international Chief Technical Advisor (P3 grade international UN officer), a national officer and a secretary who will together coordinate all activities under components 3 and 4.

# Activity 1.1: Organize NFMS work and capacity building

# Under this activity, the following sub-activities will be implemented:

- Establish a NFMS/RELs Technical Working Group;

- Develop a calendar of meetings to be held over the Roadmap implementation period;

- Collaboratively formulate a TOR for the Working Group;

- Identify the topics to be discussed in each of the meetings and relevant contributors;

- Prepare the minutes of each of the meetings;

- Store and archive all documents and other materials produced during the meetings;

- In collaboration with all relevant stakeholders, contribute to national consultations on the NFMS-AP, national forest definition, satellite land monitoring system and GHG inventory;

- Organize and deliver capacity building events across the country to relevant stakeholders.

# Expected outputs:

- List of the NFMS stakeholders with contact address and associated institution names;

- TOR, work plan and calendar for the Roadmap implementation period;

- Minutes of the meetings;

- Archive of all documents produced;

- Capacity and awareness of relevant built;

- Reports of the national consultations.

# Activity 1.2: Formalize institutional arrangements for the implementation and management of the NFMS

# Under this activity, the following sub-activities will be implemented:

- Propose institutional arrangements for effective and transparent implementation;

- Identify the roles, coordination mechanisms and contact information for those providing relevant data for estimating GHG emissions and removals from the LULUCF sector;

- Provide information on lead agencies, identify inventory management team members, contact information and status of institutional arrangements in a tabular format;

- Identify policy support necessary for institutional arrangement and obtain government approval (e.g. notification on institutional structures, roles and mandate) for effective implementation;

- Identify the strengths, and recommend for potential improvements, in the management structure of National Inventory System.

# Expected outputs:

- Essential information in a tabular format;

- Standardized tasks, to compare and contrast results provided;

- Roles and responsibilities clarified;

- Objective and efficient system for identifying priorities for future improvements provided;

- Concrete institutional arrangements proposed in Bhutan’s NFMS-AP.

# Activity 1.3: Develop Bhutan’s NFMS Action Plan

# The NFMS-AP (as outlined above) will set out institutional arrangements and guidance for implementation in Bhutan. In addition to detailed capacity and needs assessment, it will set out the activities and work plan to implement the NFMS, including details of logistics, procurement, equipment and software needs, etc.

# The NFMS-AP will be consulted upon with relevant stakeholders, re-drafted (as necessary), then be proposed for official government endorsement in order to formalize the institutional arrangements and work plan. In addition to guiding national activities, this document will also be used to seek additional funding for components of the national forest monitoring system not funded through the Roadmap.

# Under this activity, the following sub-activities will be implemented:

- Develop a table of contents (led by NFMS Working Group);

- Gather input through meetings and consultations with relevant ministries, NGOs and private sector stakeholders;

- Develop a first draft of the document and consult widely with stakeholders through a workshop;

- Gather input and re-draft the document;

- Produce final version and hold national a validation workshop.

# Expected outputs:

- Bhutan’s NFMS Action Plan document;

- Report of the proceedings of national consultation workshop;

- Report of the proceedings of national validation workshop.

# Output 2: Satellite Land Monitoring System developed and operationalized

# A SLMS will be designed and implemented to monitor REDD+ activities and (eventually) assess national activity data. Consultations will be undertaken to determine an efficient and cost-effective approach, including consideration of open-source software packages and through support from experienced international organizations and countries. Training will be delivered to technical officers who will then process national data and upload it to the purpose-built web-GIS portal. In addition, a systematic data archive will be built to store national remote sensing data securely and transparently.

# Activity 2.1: Capacity building on geospatial data processing and database management

# Stakeholders will receive training on geospatial data capture, processing, analysis and management. Part of the training will be delivered in collaboration with the Brazilian Institute for Space Research (INPE), who hold a partnership with FAO/UN-REDD to deliver training to government counterparts from partner countries. This activity will also include the hiring of a team of people to coordinate the SLMS work and design, operationalise and manage Bhutan’s SLMS.

# Under this activity, the following sub-activities will be implemented:

- Identification of RS/GIS and database management training needs;

- Develop and deliver training programmes on satellite data geo-rectification, interpretation, classification, field data collection, accuracy assessment and change matrix generation;

- Travel of national officers to Brazil for training at INPE;

- Develop and deliver a training program on RS/GIS database structure and data capture including metadata, editing and retrieval, visualization, analysis, mapping and modelling;

- Provide guidelines and training on RS/GIS data archiving and database management, with preference for open-source database software.

# Expected outputs:

- Capacity enhanced on GIS, RS data handling and data base management;

- Training materials and guidelines on GIS and remote sensing;

- Training materials and guidelines on RS/GIS data archiving and management.

# Activity 2.2: Establish a harmonized classification system for land representation

# This activity involves setting the National Forest Definition and classification for land representation. It is important to have an appropriate national definition of forest and land representation system allowing for effective and sustainable  monitoring tools of forest resources. Under the UNFCCC, forest definitions are provided based on biophysical thresholds. The forest thresholds will need to be within the thresholds identified by the UNFCCC.

# The forest classification systems will need to account for measuring and monitoring REDD+ activities.

# Under this activity, the following sub-activities will be implemented:

- Collect existing land cover and land use maps of Bhutan and identify the different forest and other land use definitions and criteria used to develop the maps;

- Organize consultations on forest classification, including a forest monitoring training workshop;

- Assess the impact of different forest definitions on the feasibility, sustainability and efficiency of methods for forest monitoring;

- Provide recommendations on forest classification and forest stratification;

- Develop a harmonized classification system of land use.

# Expected outputs:

- Harmonized land use classification for mapping;

- Manual of the classification system;

- Minutes of the national consultations.

# Activity 2.3: Satellite image characterization for forest monitoring

# The selection of the types of satellite imagery will depend on their quality, cloud cover, spatial, temporal and spectral resolution, as well as their cost. It is therefore necessary to decide the parameters to be used for collecting remote sensing data to accurately monitor forest cover change and provide information on some of the REDD+ safeguards. It is also important to decide on the use of correct levels of resolution, to accurately monitor forest degradation or enhancement of forest carbon stocks by way of distinguishing forest landscape feature changes or forest area changes.

# Under this activity, the following sub-activities will be implemented:

- Identify and organize all available satellite and/or aerial imageries for the country, e.g. by resolution, date, geographical coverage, etc.;

- Assess the quality of these data in terms of spatial and temporal coverage, cloud cover, spatial and spectral resolution and image registration;

- Analyze the impact of different spatial resolutions in identifying deforestation and forest degradation;

- Provide recommendations for the use of imagery for past and future forest cover assessments, forest stratification and monitoring of REDD+ activities.

# Expected outputs:

- All existing satellite imagery for Bhutan identified;

- Standardised procedure for integrating medium- and high-resolution satellite data;

- Freely available satellite imageries archived and transparently available for the national entities involved in the NFMS;

- Recommendations provided on satellite imagery to be used to monitor  REDD+ activities.

# Activity 2.4: Establish an RS/GIS Forest Information System and web-GIS platform

# Information and monitoring systems for the forest sector have become important tools for forest planning, monitoring and reporting. An RS/GIS Forest Information Systems (FIS) will be developed to support decision makers as well as ensure transparency of forest data, including for REDD+. Development of the system will involve documentation at all levels, including of meta-data, development of a data dictionary and user manuals, and instructions for data storage, manipulation, retrieval and update.

# Under this activity, the following sub-activities will be implemented:

- Review, harmonize and standardize existing statistical and spatial data information related to the forest sector and identify additional information requirements;

- Develop a database structure for the Forest Information System;

- Review capacity building needs for the Forest Information System;

- Develop a design for hosting a web-based GIS platform for database management;

- Standardize existing GIS and RS data and integrate them into the system;

- Develop training manuals for managing and maintaining the system;

- Develop technical documentation and deliver training on the system.

# Expected outputs:

- Operational Forest Information System;

- Documentation of the system design, data flow, storage and retrieval models;

- Web-based GIS platform operational;

- User manual.

# Activity 2.5: Develop and operationalise Bhutan’s satellite land monitoring system

# A satellite land monitoring system (SLMS) will be a crucial element of Bhutan’s NFMS, for the monitoring of REDD+ activities and for the generation of activity data.

# Under this activity, the following sub-activities will be implemented:

- Organize national consultations on SLMS development and identify and validate parameters for forest monitoring;

- Develop Bhutan’s forest base map (forest mask), to use as the basis for forest/REDD+ monitoring;

- Develop an operational methodology for the monitoring forests (including staffing and logistical issues and costs);

- Carry out field tests of the monitoring system for selected demonstration activities;

- Integrate lessons from field demonstration activities into the national system.

# Expected outputs:

- Report of the consultations to identify the forest monitoring parameters and recommendations for Bhutan’s SLMS;

- Nationally appropriate satellite land monitoring system developed and operationalised;

- Results from demonstration sites integrated into the national SLMS.

# Activity 2.6: Develop participatory tools for community forest monitoring

# Given the importance of community monitoring in generating and delivering local data and ground-truthing national monitoring activities, activities will also be designed to support the assessment of integrating community monitoring into the NFMS.

# Under this activity, the following sub-activities will be implemented:

- Research on a) current community forest monitoring practices in Bhutan and b) community monitoring integration in other countries in SE Asia;

- Socio-economic assessment of the potential involvement of forest communities in the NFMS;

- Provide recommendations on the involvement of forest communities in the NFM;

- Stakeholder consultation and validation workshops to select an approach to community forest monitoring for REDD+;

- Selection of demonstration sites based on transparent criteria.

# Expected outputs:

- Diagnostic of the roles, methods and costs of the involvement of the forest communities in the NFMS;

- List of potential demonstration sites.

# Activity 2.7: Forest boundary delineation in the field and GIS boundary generation for demonstration activities

# Some of the risks involved in REDD+ implementation include the displacement of deforestation or forest degradation from the demonstration activities to other forest areas, leading to lower actual net carbon savings by the project. The entire demonstration area should be delineated to assure effective and accurate management and monitoring.

# Under this activity, the following sub-activities will be implemented:

- Collect forest / field maps / cadastral maps of forest boundaries;

- Provide orientation and training for forest land survey using maps and GPS;

- Execute a forest land survey with the coordination with multiple ministries and local stakeholders;

- Develop a boundary demarcation plan by state (along with a budget);

- Identify the potential organisations involved in GIS database building for forest boundary digitization and contract for GIS data generation;

- Provide guidelines for GIS boundary generation.

# Expected outputs:

- Forest boundary defined and mapped;

- Training materials developed and delivered for forest delineation.

# Output 3: Multipurpose NFI implementation completed and data management strengthened

# This output will result in the full national implementation of Bhutan’s new NFI and ensure the continued training of field staff. It will also support the development of country-specific allometric equations, which will underpin the country’s efforts towards reporting its GHG inventory to the UNFCCC at Tier 3 level (through the development and use of country-specific emission factors).

# Activity 3.1: Ongoing training provided to field crews and data analysts

# This activity will ensure that NFI field crews and data analysts receive regular and updated training and that training manuals are regularly reviewed, updated and published.

# Under this activity, the following sub-activities will be implemented:

- Deliver training program on forest inventory (data collection, compilation, analysis etc.) to field crews on periodic basis;

- Regularly review, update and publish NFI training manuals;

- Produce training manuals on data processing, data management and statistical analysis and deliver training to relevant officers.

# Expected outputs:

- Details of trained staff (field crews and data analysts);

- Regularly updated field training manuals;

- Training manuals on NFI data processing, data management and statistical analysis.

# Activity 3.2: Harmonize existing inventory data and develop robust tree species and NFI databases

# In order to ensure the comparability of data collected and to improve the estimates of forest biomass and carbon stocks, existing data should be stored in a central tree species and forestry database and used to support the design of the new multipurpose NFI. An NFI database will be designed, according to the parameters to be measured, to facilitate storage, analysis and archiving of the data to be collected using the new methodology.

# Under this activity, the following sub-activities will be implemented:

- Consultations held with the relevant stakeholders involved in forest inventory and measurement and collate all existing forest inventory data;

- Tree species and forestry database developed based on open-source software;

- All available existing inventory data and land cover maps collected and reviewed;

- Robust geo-referenced database developed, preferably based on open-source software;

- Populate the database with existing inventory data (including allometric equations, wood density and conversion factors, soil and litter carbon stock assessment, etc.);

- Variability of the biomass and carbon stocks in the various forest types assessed;

- NFI database for inputting, analysing and archiving NFI data developed, preferably based on open-source software.

# Expected outputs:

- List of the stakeholders involved in forest inventory and measurement activities;

- Central database containing the available and harmonized tree species and forestry data;

- Statistical method for data harmonization and accuracy assessment;

- Database for new multipurpose NFI.

# Activity 3.3: Allometric equations developed using destructive sampling for 50 key species

# A current major gap in Bhutan’s NFI work is the lack of country-specific allometric equations, which allow the estimation of forest carbon stocks. This activity will address this gap by providing training to technical WMD staff on allometric equations and destructive sampling methodologies, as well as funding the field data collection work.

# Under this activity, the following sub-activities will be implemented:

- Review of allometric equations developed in the South Asian region;

- Development of destructive sampling methodology for Bhutan, including formulation of field manuals;

- Training workshop on allometric equation development, including field demonstration of destructive sampling methodologies;

- Field data collection for 50 key tree species using Bhutan’s destructive sampling methodology.

# Expected outputs:

- Report of allometric equations developed for South Asia;

- Training materials and list of trained personnel on allometric equation development;

- Field manual for Bhutan’s destructive sampling methodology;

- Country-specific allometric equations for 50 key species.

# Activity 3.4: First cycle of new NFI completed in Bhutan

# Bhutan has developed a new NFI methodology, including a calendar for implementation, though there is a funding shortfall for full national implementation of the NFI. This activity will fund field data collection for the completion of a full cycle of the NFI over a period of three years, including for the purchase and maintenance of necessary equipment (data collection and data recording devices).

# Under this activity, the following sub-activities will be implemented:

- Purchase of necessary data collection and recording equipment;

- NFI field data collection completed for the country by trained field crews;

- Equipment checks and maintenance.

# Expected outputs:

- Field crews equipped with all necessary data collection and recording equipment;

- NFI equipment maintained to full working order;

- Full NFI completed for Bhutan and data entered in the purpose-built database (Activity 3.2).

# Output 4: National capacity built for compiling the GHG Inventory for the LULUCF sector

# Activity data and emission factors estimated through the SLMS and NFI will be compiled, following international guidance, to produce Bhutan’s GHG inventory for the LULUCF sector. Figure 4a-5 summarizes the sequence of generic activities to develop and implement Bhutan’s national GHG inventory for the LULUCF sector.

# Activity 4.1: Technical capacity building for the GHG inventory for the LULUCF sector

# Bhutan has limited experience in developing national GHG inventories for the LULUCF sector. The objective of this activity is to provide preliminary training and identify the future training needs in order to prepare the inventory plan for data compilation and reporting with the aim of promoting the establishment of the national system.

# Under this activity, the following sub-activities will be implemented:

- Training delivered on GHG inventory implementation for the LULUCF sector;

- Training needs identified for inventory planning, data collection, data compilation, Quality Assurance/Quality Control (QA/QC) procedures, reporting, uncertainty estimation;

- Bhutan-specific training manuals developed and training programme delivered, as necessary;

- Technical support provided for use of GHG inventory software tools for data compilation and reporting;

- QA/QC plans developed for data collection and compilation;

- Reporting manual designed.

# Expected outputs:

- Government working group on GHG inventory for the LULUCF sector and associated reports/documentation from meetings;

- Government personnel trained in GHG inventory for LULUCF and able to undertake inventory activities independently;

- Manuals, plans, designs of data collection, compilation and QA/QC procedures developed.

# Activity 4.2: Develop a central GHG database and archiving system

An archiving system is essential for the preparation of the national inventory reports. No common archive system currently exists for GHG data management in Bhutan. A common archiving procedure will be developed in order to secure the REDD+ data related to monitoring and MRV as well as information on some of the REDD+ safeguards. The archiving system will be used by the relevant institutions and the documents and data will be shared in order to ensure that the activities are implemented in a timely manner. The archiving system will host a central database whose structure will allow effective, efficient and transparent QA/QC procedures.

# Under this activity, the following sub-activities will be implemented:

- Assess existing database management, archiving and sharing mechanisms in place;

- Develop design of a specialized database structure;

- Standardize existing data and integrate in a specialized data structure;

- Design a web-based platform for sharing the data;

- Procure necessary equipment to establish servers;

- Establish servers;

- Identify training needs and deliver training programmes for the operation and maintenance of the archiving system;

- Develop necessary training manuals;

- Provide training to operationalize the system.

# Expected outputs:

- Report on the assessment of the existing data and needs for GHG inventory server;

- List of the necessary equipment for the relevant entities;

- Web-based data sharing and archiving system for data sharing;

- Technical staff trained to operazionalize the system;

- Transparency of national system ensured.

Figure 4a-5. Indicative activities marking progress towards the generating of the Bhutan’s national GHG inventory for the LULUCF sector.

# Output 5: NFMS-related research supported

# Following initial awareness raising and capacity building on REDD+, internal and external consultations and discussions will be undertaken by the Forest Department and FRI into potential new research areas to support the implementation of REDD+ in Bhutan, and in particular the multipurpose NFI.

# Activity 5.1: Support NFMS-related research and dissemination of findings

# The assessment of forest resources needs to be carried out together in conjunction with research on local knowledge and uses of forest land as these two elements will be crucial to define policies for sustainable forest management.

# Under this activity, the following sub-activities will be implemented:

- Gathering of existing research activities and findings related to REDD+/NFMS;

- Implementation of studies on forest and tree characterisation;

- Publishing of study reports and scientific papers based on findings;

- Provision of internships for university students to support specific studies on forest and tree characterisation;

- Organization of technical and scientific workshops/seminars in Bhutan involving national and international researchers and university students.

# Expected outputs:

- Report on the scope of potential studies to support NFMS development in Bhutan;

- NFMS-related studies completed;

- Results disseminated through published reports and articles in peer-reviewed journals;

- Minutes of workshops/seminars on NFMS-related research;

- Trained university interns.

# 4a.5 Work Plan and Budget for Component 4a

| - National Programme Components | Participating donor organization | Implementing Partner | Indicative readiness activities | Estimated cost (in thousand US$) (over 4 years) |
| --- | --- | --- | --- | --- |
| Component 6: Development of a national forest monitoring system |  |  |  |  |
| 6.1 Capacity building and NFMS Action Plan development |  | WMD | - Organize NFMS work and capacity building - Formalize institutional arrangements for the implementation and management of the NFMS - Develop Bhutan’s NFMS Action Plan | 250 |
| 6.2 Satellite Land Monitoring System developed and operationalized |  | DoF | - Capacity building on geospatial data processing and database management - Establish a harmonized classification system for land representation - Satellite image characterization for forest monitoring - Establish a Forest Management Information System and web-GIS platform - Develop and operationalise Bhutan’s satellite land monitoring system - Develop participatory tools for community forest monitoring - Forest boundary delineation in the field and GIS boundary generation for demonstration activities | 750 |
| 6.3 Multipurpose NFI implementation completed and data management strengthened |  | WMD | - Ongoing training provided to field crews and data analysts - Harmonize existing inventory data and develop robust tree species and NFI databases - Allometric equations developed using destructive sampling for 50 key species - First cycle of new NFI completed in Bhutan | 1,500 |
| 6.4 National capacity built for compiling the GHG inventory for the LULUCF sector |  | NEC | - Technical capacity building for the GHG inventory for the LULUCF sector - Develop a central GHG database and archiving system | 250 |
| 6.5 NFMS-related research supported |  | WMD | - Support NFMS-related research and dissemination of findings | 200 |
| Total |  |  |  | 3,000 |

## 4b. Designing an Information System for Multiple Benefits, Other Impacts, Governance, and Safeguards

# Introduction

This sub-component proposes a process for the development of a component of the national forest monitoring system referred to in Component 4a for monitoring benefits from REDD+ interventions other than reductions in net greenhouse gas emissions, that includes biodiversity, soil and water conservation and social and environmental impacts and the effectiveness of the planned safeguards and governance. A preliminary outline of the proposed integrated monitoring system is shown in Figure ??.

# Existing Arrangements for Monitoring Co-benefits

Multiple benefits are critical to ensuring that the right people get the right incentives to implement REDD+ activities. Socio-economic benefits, that could include diversification of livelihoods; increased productivity; employment, increased income, food security and reduction of poverty are important tangible incentives. However, REDD+ can also help secure benefits such as ownership of land resources and services, participation in decision making, improvement of governance in the forest sector, and cross-sector coordination to address emissions resulting from land use change.

The single unifying idea that guides the nation’s long term development is the uniquely Bhutanese concept of maximizing Gross National Happiness. The spirit and intent of this concept as articulated in the Bhutan Vision 2020 document is to “Maximise the happiness of all Bhutanese and to enable them to achieve their full and innate potential as human beings.” Reflecting the importance of the concept, the promotion of enabling conditions for GNH has also been enshrined as an important principle of state policy under Article 9 of the Constitution.

Incorporating the notion of happiness and the emotional and spiritual well-being needs of humans into the development equation represented a paradigm shift. It sought to go beyond the conventional income-based measures of development and attempted to address the ends of development rather than just the means. The GNH concept does not in any way exclude or deny the importance of economic growth but strongly advocates achieving a harmonious balance between the material and non-material dimensions of development.

In order to translate the multidimensional concept of GNH into core objectives for a more focused direction for the country’s long term development, four priority strategic areas were initially defined. These four foundation pillars of GNH were the goals of sustainable and equitable socio-economic development; environmental conservation; preservation and promotion of culture; and good governance. They constituted the broad strategic framework through which national development processes were to be actualized for the maximization of GNH.

The GNHC is the agency responsible for ensuring that Gross National Happiness(GNH) is mainstreamed into the planning, policy making and implementation process and promoting effective and good governance.

In keeping with the spirit of the results based planning approach ofthe Tenth Plan, efforts were undertaken to develop an appropriate development measure that will capture the essence of GNH and help in tracking national progress towards meeting this overall long-term development objective. The GNH Index (GNHI) is that critical evaluation tool for the results based planning framework of the Tenth Plan and future plans to ensure that development truly contributes to the achievement of GNH.

The GNH indicators considered were those indicators that are designed to be measures of the specific dimensions which make up the GNH model. For instance, demographic indicators constitute an important set of indicators to allow an analysis of the distribution of GNH dimensions across different social and demographic groups in the country. This includes various age and gender groups, occupational and employment clusters, educational backgrounds, types of households, language groupings and geographical areas. The causal indicators that were considered were those factors affecting the performance of GNH status indicators. For instance, the general ratings of central government performance were broken down into more specific components to allow a more detailed analysis of factors affecting general governance performance ratings.As such these indicators are being broadly classified into various domains relating to the areas of psychological well being, cultural diversity and resilience, education, health, time use, good governance, community vitality, ecological diversity and resilience and economic living standards. These areas and their various indicators/indices were determined based on a pilot survey and a National GNH Survey conducted in 2006 and 2008.

The composite GNH index is to be aggregated from these indices and indicators from among the nine domains with appropriate weighting. These indices and indicators – include a wide range of factors with

a significant bearing on individual and collective happiness and include the mental health index, family relationship index, financial security indicator, healthy days per month indicator, body mass index, education level indicator, local air and water pollution indicators, house ownership indicator, human rights indicator and government performance index.

Given the nature of human happiness and well being, the evolution of GNH policies and strategies and the index must necessarily follow a dynamic, inclusive and open ended process that takes into consideration the relative importance of different variables and factors of happiness and well being that may or may not be relevant to Bhutanese society at a particular point of time

# Biodiversity

Monitoring initiatives and tools developed within the framework of the Biodiversity Action Plan include: the publication of the first-ever Field Guide to the Mammals of Bhutan, which provides brief accounts of the physical characteristics, social behavior, habitat and conservation threats of some 200 mammal species found in the country; field studies on the white-bellied heron (Ardeainsignis) initiated in 2005 by the Royal Society for the Protection of Nature (RSPN), as well as research and monitoring of the black-necked crane (Grusnigricollis) as a part of their conservation management program in the Phobjikha Valley; and the first Bhutan Snow Leopard Information Management System (SLIMS), with training and field surveys conducted in Thimphu and Jigme Dorji National Park by the Nature Conservation Division (NCD), in collaboration with the WWF Bhutan Program and the International Snow Leopard Trust. As for floral resources, Bhutan has published three volumes of the “Flora of Bhutan”; work on ferns and their allies is ongoing and the Red Book of Bhutan’s flowering plants is in preparation. The National Information Sharing Mechanism (NISM) is also in place and constitutes a valuable tool for the transparent and effective monitoring of the implementation of the Global Action Plan for Plant Genetic Resources for Food and Agriculture (PGRFA).

Biodiversity surveys have been conducted in all operational Protected Areas with the exception ofRMNP where the present situation does not permit much survey work. Surveys in TNP, JSWNPand BWS were preliminary biodiversity surveys, with survey results being used to prepare therespective management plans.

# Poverty

The Poverty Analysis Report 2007 estimated that 23.2 percent of the population was poor. In absolute numbers this translates to 146,100 individuals. Poverty in rural areas is significantly higher than in urban areas and poverty in Bhutan can be clearly characterized as a rural phenomenon. Around 98% of all the poor live in rural areas with most of the poor primarily engaged in subsistence farming as their primary occupation.  The distribution of poverty is illustrated in Figure 4b-1

# Figure 4b-1: Poverty Incidence in Bhutan (2007)

Tracking this for the years that the data are available, income poverty incidence has declined to present levels of 23.2% in 2007 from 36.3% in 2000 and 31.7% in 2003. However, subsistence or food poverty has risen from 3.8% in 2003 to 5.9% in 2007. In addition to headcount ratios, measuring poverty gap and severity ratios provide a useful perspective on the depth and severity of poverty. Available data for 2003 and 2007 reflect significant reductions in the national and rural poverty gap ratios that declined from 8.6% to 6.1% and from 10.5% to 8.1% respectively. The poverty severity ratios at both the national level and in rural areas also respectively declined from 3.1% to 2.3% and from 3.8% to 3%.

Policies to address poverty in Bhutan are also viewed from a broader and multi-dimensional context than just an income perspective. This takes into account several other aspects of human deprivation such as access to improved drinking water and sanitation, educational and health attainment levels and access to basic infrastructure such as roads and electricity. While significant progress has been made to reduce human poverty levels, more effort needs to be addressed to enhance access to rural roads and electricity, particularly in rural areas. Such infrastructural investments in rural areas have not only been strongly identified by rural communities as a top priority but do have highly beneficial benefits to alleviate conditions of human deprivation and improve the quality of rural life.

# Governance and Other Impacts

The existing legal and regulatory framework relating to the forest and other sectors that provides the basis for governance of REDD+ is described in Component 2a. As discussed above, responsibility for implementing and monitoring these laws and regulations lies primarily with the GNHC through its mandate to promote effective and good governance, and its role of being the central government body for coordinating and spearheading policy formulation.

The functions of the GNHC that are relevant to this Component include:

- Preparing a Strategy for GNH (SGNH), a twenty year perspective that provides long term development framework for the five year plans and programmes till the year 2028.

- Developing mechanisms for effective enforcement of policies and resolving all issues arising from the implementation of policies and plans.

- Ensuring efficient and judicious allocation of and utilization of scarce resources to bring about regionally balanced development and growth with stability, equity and social justice.

- Establishing coherence of policies to promote performance and growth, through a regular process of policy review and commissioning of policy research/studies/surveys by expert groups.

- Monitoring the implementation of development activities by instituting an effective monitoring and reporting system.

- Commissioning impact assessments and evaluations of policies, programmes and activities to assess the progress towards the achievement of national goals and targets that are articulated in the SGNH.

Transparency of and access to information, and the provision of information in a timely manner, are important to ensure effective participation. The need for sufficient capacity to implement genuine multi-stakeholder processes is vital.

# Multiple Benefits to be Included in the Monitoring System

The main direct benefits, other than reductions in GHG emissions, from forest protection, management and restoration will be from strengthened conservation of biodiversity, improved seasonal distribution of water and improved water quality through maintaining forest cover and reducing the risk of soil erosion. Substantial indirect benefits will be obtained through improved governance especially relating to land tenure and improved livelihoods for rural communities. Infrastructure development will generally have large economic benefits, but these must take into account the environmental cost from any reduction in benefits from biodiversity and soil and water conservation that may result from disturbance to any forest and where possible development plans modified to ensure that these benefits are maximized.

# Monitoring Governance

Improved governance will contribute to overall benefits from implementation of REDD+ especially through addressing the issue of land-tenure, which will both help to resolve the question of ownership of the carbon, and provide the basis for a concerted effort to improve livelihoods of rural communities, which will contribute to the broad aims of REDD+. Given some capacity constraints, public resources are managed reasonably well in Bhutan, though significant issues need to be addressed. Ensuring the maximum development impact of expenditures from the increasing revenues from hydropower exports will require enhanced fiscal discipline. Moreover, the ongoing process of political and administrative decentralization has led to a paradigm shift in the planning and implementation of development activities, heightening the need for greater transparency and accountability, as well as increased capacity at the dzongkha and geog levels. The royal government needs to improve accuracy and consistency of macroeconomic forecasting to help underpin sound revenue projections and inform policymaking.

# System for Developing a Co-benefit Monitoring System

At the beginning of the Readiness phase a workshop with all relevant agencies identified above and invited specialists concerned with monitoring the co-benefits indicated above will be convened. This workshop will aim to record in detail the precise parameters being measured by each agency, together with important statistical characteristics including the frequency and intensity of sampling and locations for site-specific sampling such as river flow. The indicators to be used for monitoring the various benefits will be identified and any gaps that may exist in current monitoring arrangements using any guidelines produced by UNFCCC. Information on the format in which the data is recorded will be assembled together with the quantity of data generated annually for each of the indicators identified. In view of the number of agencies that will need to be involved and the extent and complexity of the current monitoring arrangements more than one workshop is likely to be required, but the aim will be to complete the first step within sixmonths. The results of the workshop(s) will be publicized for further stakeholder inputs.

Having assembled information on the parameters monitored and the quantity, quality and format of the data the TWG on REL and national forest monitoring systemdevelopment will assessand recommend on how the data will be integrated into an Information System compatible with the national forest monitoring systemthat can be readily and easily accessed for monitoring purposes. It is expected that this step will be completed in the early stage of Readiness phase. This will be followed by consultations with relevant agencies that will be required to monitor aspects of implementation as outlined above and agree responsibilities and procedures for sharing data. At the same time investigations will be proceeding to select sites for pilot studies under Component 2b, and as these are identified and agreed with participating stakeholders arrangements for relevant stakeholders to contribute to the monitoring will be discussed, agreed and approved. It is expected that it will require around a year to identify pilot sites and conduct consultations with participating stakeholders and that the co-benefit monitoring system will be ready to pilot as the pilot REDD+ activitiesare implemented. The monitoring of co-benefits will be an integral part of the monitoring system set up and piloted at the selected pilot sites as shown in Figure 4-1 under Component 4a. After an appropriate period, monitoring results from the pilot sites will be evaluated and the national co-benefit monitoring system refined and approved.

# The role of Stakeholders in the Monitoring System

The roles of local communities, NGOs, various government agencies or institutes, and the private sector will need to be determined in detail during the design stage of each of the pilot activities. Voluntary participation will be welcomed, especially where the stakeholder already has the capacity, hardware and software to contribute.

The scope for community monitoring of carbon stocks is referred to under Component 4a and trials will also be extended to include community monitoring of biodiversity and water quality. Successful low cost community monitoring of stream flow and water quality has been developed in the Philippines (Deutsch et al., 1998) and of biodiversity in Australia (NPA, 2001) and similar methods based in international experience will be piloted in Bhutan. There is at present some experience involving communities in biodiversity monitoring in Bhutan.

The cooperation and participation of the government agencies referred to above that have a mandate to monitor relevant social and environmental parameters will be sought and their role and responsibilities agreed.

Some private sector companies already have various initiatives, as described in Component 2a (page 46) and discussions will be held with them regarding their current arrangements and experience with monitoring the performance of their initiatives. Consultations will be held with as many private sector companies as possible to assess their interest in supporting the monitoring of co-benefits and the resources and capacity that they are willing and able to contribute.

# Monitoring Systems and Indicators

The overall aim is to have a unified monitoring system that covers changes in forest composition and carbon stocks as well as co-benefits and social and environmental impacts to ensure compliance with safeguards. A REDD+ monitoring system will be created to incorporate the NFMS described under Component 4a and a Co-benefit Monitoring System. This latter will include biodiversity data and relevant  socio-economic data compiled by the GNHC. Changes and improvements to livelihoods and other co-benefits resulting from REDD+ interventions will be collected by relevant government agencies and, where appropriate and feasible, local communities and the private sector. The information submitted will be checked by the REDD+ Office to ensure consistency between sources, and re-assessment will be requested where data appears anomalous. Once evaluated, results will be posted on anweb-GIS forest monitoring portal to facilitate accessibility and sharing of data both nationally and internationally. The workshop among relevant stakeholders on identifying potential indicators to be used for monitoring co-benefits will be carried out during the Readiness phase. Preliminary potential indicators that may be considered to identify to use and assess REDD+ co-benefits are listed in Table 4b-1.

# Table 4b-1. Potential indicators to assess REDD+ co-benefits and safeguards

| Topics for monitoring | Examples of indicators |
| --- | --- |
| Policy and governance | - Development of relevant policies, regulations, guidelines, rules, acts, strategy documents, and procedures for REDD+ - Implementation of 5-year plans for MOAF “on track” (compliance and budgetary monitoring using the PLaMS on-line) - Number of resource management plans approved by Minister of MOAF - Number of management units established - Number of conflicts over use of resources - Number of corrupt practices reported to ACC for the forest sector - Number of forest offences reported - Percentage of reported offences settled - Number of incidences of non-respect for FPIC - Number of forest-related plans, policies etc. that are “referred for further development” by GNHC |
| Biodiversity JIGME TO FIND OUT!!! | - Endemic species – lost or gained - Degraded areas rehabilitated including mangrove vegetation - Identify key species (flora and fauna) that characterize the health of different ecosystems, and assess changes - Protected areas established and encroachment of the existing |
| Poverty alleviation Indicators are defined in 10th 5YP NSB Living standards survey 2012 | - Food security - Employment: creation or loss due to REDD+ - Income: gains or losses - Enterprises: diversification and migration - Technologies made available and accessibility - Access to education and health - Value of NWFPs harvested |
| Cultural diversity | - Number of complaints related to changes resulting from REDD+ interventions |
| Gender equality | - Percentage of land registration documents under a woman’s (and men’s) name - Percentage of men (and women) participating in planning - Percentage of women participating in decision making in forest-margin communities - Percentage of women receiving positive incentives for REDD+ interventions - Average value of positive incentives received by women and men |
| Environmental quality | - Water quality - Water quantity - Incidence of landslides |

Main interventions to be considered:

- Preparation of web-GIS portal (as a component of the national forest monitoring system)

- A national forest cover and land use map will be developed, based on recent satellite data, for use as the base map of the web-GIS platform of the NFMS will be produced for all the areas identified for sub-national level (landscape-level corridor).

- Analyze existing data collection and compilation platforms and establish a mechanism for complementarities of processes and information sharing.

- Establish a system for regular updates of information.

Development of methodologies and establishment of systems for assessing performance related to REDD+ co-benefits

- Refine indicators and establish mechanisms of assessing REDD+ co-benefits performance ;

- Establish reference levels for co-benefits;

- Establish participatory monitoring processes and train land users in data collection methodologies.

# Monitoring Capacity and Future Capacities Required

Discussions and negotiations will take place with the various government agencies identified above to evaluate the existing facilities and capacity for monitoring co-benefits during the implementation of REDD+ demonstration activities. The roles and responsibilities of participating departments and national institutions, for the selection/design of indicators, and to ensure compliance with social and environmental safeguards, will be negotiated during the first year of the Readiness phase. The need for capacity building, training, and additional hardware and software will be assessed and a plan drawn up for implementation of the identified actions.

# Sub-National Level Monitoring

Monitoring of co-benefits maybe conducted at the sub-national level(e.g., a dzhongka or a geog), as deemed appropriate through stakeholder consultations,  as part of the NFMS and the monitoring of co-benefits will be included in the studies proposed in Component 4a.

# Social and Environmental Safeguards

The Cancun Agreements encourage all Parties to find effective ways to reduce the human pressure on forests that results in GHG emissions, including actions to address drivers of deforestation. The Decision also affirms that the implementation of REDD+ activities should be carried out in accordance with annex I to the decision, which provides guidance and safeguards for the implementation of REDD+ activities. In addition, in Bhutan (see Component 2a and 2d) there are a number of laws, environmental policies, procedures (EIA) and measures that are used to mitigate and protect social and environmental impacts relating to programs/projects. These sets of policies and procedures, including the World Bank’s Safeguard Policies, will be used during the Readiness phase as a safeguard tool. In order to ensure that the implementation of REDD+ activities in Bhutan is consistent with the Cancun Agreements and that safeguards being addressed and respected, a Safeguards Information System (SIS) will be designed. The system will be developed and tested at the demonstration sites, subject to available financial support. The design will be based on a participatory approach. The related activities and budget is outlined in Component 2d.

Table 4b-2 shows activities and budget for designing systems for the integration of monitoring co-benefits into the national forest monitoring system. Criteria to be considered during implementation are:

# 1) Identification of non-carbon aspects

- Identify priority non-carbon aspects of REDD+ implementation

# 2) Transparent information sharing

- Design and develop a transparent system for sharing consistent information on non-carbon aspects/safeguards.

- Make the following information available: key quantitative and qualitative variables on the impacts of REDD+ activities on rural livelihoods, conservation of biodiversity and natural forests, ecosystem services provision, key governance factors directly pertinent to REDD+ implementation, and the implementation of safeguards, paying attention to the specific provisions included in the ESMF

# 3) Institutional arrangements and capacities

- Clearly define and assign mandates to perform tasks related to non-carbon aspects/safeguards.

- Identify and estimate resource needs (e.g., human, financial and technical capacities and training requirements)

| Table 4b-2: Summary of Monitoring Activities and Budget |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Main Activity | Sub-Activity | Estimated Cost (in thousands) |  |  |  |  |
|  |  | 2011 | 2012 | 2013 | 2014 | Total |
|  |  | $ | $ | $ | $ | $ |
|  |  | $ | $ | $ | $ | $ |
|  |  | $ | $ | $ | $ | $ |
|  |  | $ | $ | $ | $ | $ |
|  |  | $ | $ | $ | $ | $ |
|  |  | $ | $ | $ | $ | $ |
| Total |  | $ | $ | $ | $ | $ |
| Government |  | $ | $ | $ | $ | $ |
| FCPF |  | $ | $ | $ | $ | $ |
| UN-REDD Programme (if applicable) |  | $ | $ | $ | $ | $ |
| Other Development Partner 1 (name) |  | $ | $ | $ | $ | $ |
| Other Development Partner 2 (name) |  | $ | $ | $ | $ | $ |
| Other Development Partner 3 (name) |  | $ | $ | $ | $ | $ |

Overview Of Forest Policy Reviews In Bhutan. D.B. Dhital. Proceedings of the Forest PolicyWorkshop Kuala Lumpur, Malaysia 22-24 January, 2002, http://www.fao.org/docrep/003/AB576E/AB576E00.HTM

Proceedings of the National Workshop on REDD+ Strategy Development of Bhutan, April 2012, Thimphu

Feasibility of REDD+ in Bhutan: A scoping study.  Hans van Noord (SNV); Watershed Management Division, Department of Forests and Park Services, Ministry of Agriculture and Forests, December 2010

Feasibility of REDD+ in Bhutan: A scoping study.  Hans van Noord (SNV); Watershed Management Division, Department of Forests and Park Services, Ministry of Agriculture and Forests, December 2010

Forest fire is normally a driver of degradation, but in some circumstances can cause deforestation

Gaps and weaknesses were identified in the WWF Management Effectiveness Assessment (assets.panda.org/downloads/bhutancasestudyfinal.pdf‎)

First two gaps/weaknesses identified in BHUTAN FORESTRY OUTLOOK STUDY, byDhan B. Dhital, FAO (www.fao.org/docrep/014/am249e/am249e00.pdf)

Gap/weakness identified in: Community Forestry in Bhutan: Experiences andthe Way Forward. Chado Tshering, Head, Social Forestry Division, Department of Forests, Bhutan (lib.icimod.org/record/20708/files/c_attachment_17_25.pdf)

Designing a National PES Approach in Bhutan: Feasibility Assessment and Proposal. FAO/WMD, 2009.

Or the equivalent safeguard policies of the Delivery Partner

NEC, 2011. Kingdom of Bhutan’s Second National Communication to the United Nations Framework Convention on Climate Change. National Environment Commission, Thimphu.

Or the Safeguard Policies of the Delivery Partner