**Priority Activities for the rest of 2013**

|  |  |
| --- | --- |
| **Outputs** | **Priority Activities** |
| ***Outcome 1: Effective National Management of the REDD+ Readiness process and stakeholder engagement in accordance with the Roadmap principles***  |
| Output 1.1 National REDD+ Readiness Coordination Mechanism established  | * Building Capacity of the REDD+ Taskforce (Visit to Vietnam in October)
* Regular meetings of the Cambodia REDD+ Taskforce
* Develop and Approved TOR of the REDD+ Taskforce
 |
| Output 1.2 Support to National REDD+ Readiness process  | * Coordinate different REDD+ Readiness support project/programme in Cambodia (UN-REDD, Cam-REDD, FCPF REDD+ Readiness project)
* Development of consolidated UNREDD – JICA TA team work plan on MRV
 |
| Output 1.3 Stakeholders are engaged in the REDD+ Readiness process  | * IP selection process in the remain 8 provinces
* Building Capacity of Consultation Group
* Form Consultation Group
* Building Capacity of Consultation Group
* Develop consultation plan and implement
 |
| Output 1.4 Stakeholders provided with information on REDD+ and the National REDD+ Readiness process | * Assess and review the existing REDD+ Communication material
* Provide training on REDD+ to different stakeholders at national and subnational
 |
| ***Outcome 2: Development of the National REDD+ Strategy and Implementation Framework.*** |
| Output 2.1 Development of individual REDD+ strategies and implementation modalities | * Monitor and Document:
	+ **FA project** (Building the Awareness and Support of REDD+ Among the Forest-Dependent Communities in Siem Reap province)
	+ **FiA project** (Conservation and reforestation of Flooded Forest and Mangrove to involve in Carbon emission prevention and Carbon stock)
	+ **GDANCP project** (Support to the development of the National Protected Areas Strategic Management Plan)
 |
| Output 2.2 Evaluation of co-benefits | * Recruit International and National consultants
* Field study and document
* Meeting workshop to share and validate the findings
 |
| Output 2.3Establishing REDD+ Fund mechanisms and Revenue sharing  | * Establishment of Benefit-Sharing Technical Team
* Recruit International and National consultants
* Field study and document
* Meeting/workshop to share and validate the findings
 |
| Output 2.4: Establishing REDD+ Fund mechanisms | * Concept note and TOR are developed but implementation considered through the FCPF program in 2014.
 |
| Output 2.5 Policy and legal development for the National REDD+ implementation framework | * Not priority and implementation considered through the FCPF program in 2014.
 |
| Output 2.6Safeguards and monitoring of co-benefits | * Establishment of Safeguards Technical Team
* National consultants
* Field study and document
* Meeting/workshop to share and validate safeguards
 |
| **Outcome 3: Improved capacity to manage REDD+ at subnational levels** |
| Output 3.1 Development of National REDD+ project guidelines and approval of funding for demonstration sites | * Establishment of Demonstration Technical Team
* Development of guidelines
* Ongoing monitoring of implementation by the Technical Team
 |
| Output 3.2 Pilot project activities | * Release grant
* Collect pilot project reports
 |
| ***Outcome 4: Design of a Monitoring System and REL framework and capacity for implementation.*** |
| Output 4.1 Establishment National MRV/REL Technical Team and build appropriate national capacity | * Establishment of MRV/REL Technical Team
* Assessment of the capacities for GDNACP, FiA and FA on MRV
* Identification of adequate roles and functions for each entity or institution in the MRV system;
* Identification of institutional arrangements to support MRV activities and data sharing
 |
| Output 4.2 Develop Cambodia Monitoring system plan | * Review of National Forest definition scenarios
* Determine National Forest definition
* Determine forest cover classification (workshop land classification)
* Preparation of draft zero-forest map
* Technical session to discuss carbon pools and reference period discussed with leading government institutions
 |
| Output 4.3 Review of the forest cover assessments to provide REDD+ activity data and design the satellite forest monitoring system | * Establishment of achieve containing index maps, satellite and aerial imageries for Cambodia; plan developed for integration into Cambodian REDD+ website.
* Development of forest monitoring system processing chain scenario
* Test monitoring system web platform development
* One national consultation workshop on forest monitoring systems
* Preparation of maps of forest cover change for discussion
 |
| Output 4.4 Design of a National Forest Inventory to develop emission and removal factors for REDD+ related activities | * Design of Multi-purpose National Forest Inventory design
* Creation of archive of existing forest inventory data accessible to MRV team
* Assessment of carbon stock and emission factors based existing data; list of identified missing emission factors;
* Creation of database for GHG inventory with existing assessment data
* Preparation of recommendations and costing for establishing new emission factors
 |
| Output 4.5 Support the development of a REDD+ related GHG Reporting System | * Not a priority for implementation, will be implemented in 2014
 |
| Output 4.6 Support the development of Cambodia RL/REL framework | * Assessing the sources of and contribution of wood fuel use to current and projected future emissions
* Quantitative assessment of drivers of forest degradation
* Collate data on drivers of deforestation
* Revision and finalization of REDD+ Roadmap land-use, forest policy and governance report
* Assessment of national circumstances (preferably government institution contracted to prepare assessment of national circumstances )
 |