**Priority Activities for the rest of 2013**

|  |  |
| --- | --- |
| **Outputs** | **Priority Activities** |
| ***Outcome 1: Effective National Management of the REDD+ Readiness process and stakeholder engagement in accordance with the Roadmap principles*** | |
| Output 1.1  National REDD+ Readiness Coordination Mechanism established | * Building Capacity of the REDD+ Taskforce (Visit to Vietnam in October) * Regular meetings of the Cambodia REDD+ Taskforce * Develop and Approved TOR of the REDD+ Taskforce |
| Output 1.2  Support to National REDD+ Readiness process | * Coordinate different REDD+ Readiness support project/programme in Cambodia (UN-REDD, Cam-REDD, FCPF REDD+ Readiness project) * Development of consolidated UNREDD – JICA TA team work plan on MRV |
| Output 1.3  Stakeholders are engaged in the REDD+ Readiness process | * IP selection process in the remain 8 provinces * Building Capacity of Consultation Group * Form Consultation Group * Building Capacity of Consultation Group * Develop consultation plan and implement |
| Output 1.4  Stakeholders provided with information on REDD+ and the National REDD+ Readiness process | * Assess and review the existing REDD+ Communication material * Provide training on REDD+ to different stakeholders at national and subnational |
| ***Outcome 2: Development of the National REDD+ Strategy and Implementation Framework.*** | |
| Output 2.1  Development of individual REDD+ strategies and implementation modalities | * Monitor and Document:   + **FA project** (Building the Awareness and Support of REDD+ Among the Forest-Dependent Communities in Siem Reap province)   + **FiA project** (Conservation and reforestation of Flooded Forest and Mangrove to involve in Carbon emission prevention and Carbon stock)   + **GDANCP project** (Support to the development of the National Protected Areas Strategic Management Plan) |
| Output 2.2  Evaluation of co-benefits | * Recruit International and National consultants * Field study and document * Meeting workshop to share and validate the findings |
| Output 2.3  Establishing REDD+ Fund mechanisms and Revenue sharing | * Establishment of Benefit-Sharing Technical Team * Recruit International and National consultants * Field study and document * Meeting/workshop to share and validate the findings |
| Output 2.4:  Establishing REDD+ Fund mechanisms | * Concept note and TOR are developed but implementation considered through the FCPF program in 2014. |
| Output 2.5  Policy and legal development for the National REDD+ implementation framework | * Not priority and implementation considered through the FCPF program in 2014. |
| Output 2.6  Safeguards and monitoring of co-benefits | * Establishment of Safeguards Technical Team * National consultants * Field study and document * Meeting/workshop to share and validate safeguards |
| **Outcome 3: Improved capacity to manage REDD+ at subnational levels** | |
| Output 3.1  Development of National REDD+ project guidelines and approval of funding for demonstration sites | * Establishment of Demonstration Technical Team * Development of guidelines * Ongoing monitoring of implementation by the Technical Team |
| Output 3.2  Pilot project activities | * Release grant * Collect pilot project reports |
| ***Outcome 4: Design of a Monitoring System and REL framework and capacity for implementation.*** | |
| Output 4.1  Establishment National MRV/REL Technical Team and build appropriate national capacity | * Establishment of MRV/REL Technical Team * Assessment of the capacities for GDNACP, FiA and FA on MRV * Identification of adequate roles and functions for each entity or institution in the MRV system; * Identification of institutional arrangements to support MRV activities and data sharing |
| Output 4.2  Develop Cambodia Monitoring system plan | * Review of National Forest definition scenarios * Determine National Forest definition * Determine forest cover classification (workshop land classification) * Preparation of draft zero-forest map * Technical session to discuss carbon pools and reference period discussed with leading government institutions |
| Output 4.3  Review of the forest cover assessments to provide REDD+ activity data and design the satellite forest monitoring system | * Establishment of achieve containing index maps, satellite and aerial imageries for Cambodia; plan developed for integration into Cambodian REDD+ website. * Development of forest monitoring system processing chain scenario * Test monitoring system web platform development * One national consultation workshop on forest monitoring systems * Preparation of maps of forest cover change for discussion |
| Output 4.4  Design of a National Forest Inventory to develop emission and removal factors for REDD+ related activities | * Design of Multi-purpose National Forest Inventory design * Creation of archive of existing forest inventory data accessible to MRV team * Assessment of carbon stock and emission factors based existing data; list of identified missing emission factors; * Creation of database for GHG inventory with existing assessment data * Preparation of recommendations and costing for establishing new emission factors |
| Output 4.5  Support the development of a REDD+ related GHG Reporting System | * Not a priority for implementation, will be implemented in 2014 |
| Output 4.6  Support the development of Cambodia RL/REL framework | * Assessing the sources of and contribution of wood fuel use to current and projected future emissions * Quantitative assessment of drivers of forest degradation * Collate data on drivers of deforestation * Revision and finalization of REDD+ Roadmap land-use, forest policy and governance report * Assessment of national circumstances (preferably government institution contracted to prepare assessment of national circumstances ) |