**Work plan for the PGA in Vietnam January-June 2014;**

**towards a PGA report launch by the end of June**

|  |  |  |  |
| --- | --- | --- | --- |
| Activity | Date | Place | Responsible |
| January* Review process to date and agree on way forward; discuss main governance issues and new PGA organizational structure (introducing an Expert Group)
 | 7/1 | Lam Dong | Provincial Working Group (PWG)Facilitated by the PGA Coordinator |
| February* Consult Provincial Working Group (PWG) on the proposed new set of governance issues
 | 21/01 10/02 |  | Provincial Working Group individual (PWG) |
| * Discuss and finalize selection on governance issues based on PWG inputs
 | 14/02 | Hanoi | Expert Group (EG) meeting (Skype)Facilitated by the PGA coordinator |
| * Draft an indicator set based on agreed governance issues
 | Available by 18/02 |  | UN-REDD/ FAO supports the EG technically (RECOFTC is recruited to do this task)PGA Coordinator facilitates |
| * PWG consulted on the draft indicator set (deadline for comments is 22/2)
 | By 22/02 |  | PWG individual |
| * Conclude on indicator set
* Discuss and conclude on data collection methods, data collection instrument (detailed ToR for data collectors) and whom should be conducting the data collection
* Conclusions/decisions to be communicated to the PWG for their information
 | 25/02 | Hanoi | Expert Group meeting(with three representatives from PWG)Technical contributions from UN-REDD PGA Coordinator facilitates |
| March * Develop material for training for data collectors
 | Available 7/03 |  | UN-REDD/ FAO supports |
| * Consulting Provincial Working Group and Expert Group on the training material
 | 11/03 |  | EG individualPWG individual |
| * Finalizing training material for data collection (deadline to respond is 12/03)
 | 12/03 | Hanoi | EG/PWG meeting  |
| * Training workshop for data collection team
 | 15-17/03  | Lam Dong | FAO supports/facilitate |
| April* Collection of data and data entry
 | 20/04 – 15/05 | Lam Dong | • Data collection team (Consultant and provincial working group)•FAO supports to review data collected/methods |
| * Recruiting an editorial team to analyse findings and draft the report
* Drafting of report with main findings and “red flags”
 | by mid-April15/05-20/05 |  | PGA CoordinatorEditorial team with participation/ overall coordination from the PGA Coordinator |
| * Present the early draft to Expert Group
* New draft based on inputs from
 | By 24/05 |  | Editorial teamWith inputs from EG members  |
| May* Discuss findings agree on key recommendations for the draft report
 | 28/05 | Hanoi | EG meeting |
| * Updating the first draft
 | By 02/06 |  | Editorial team |
| * Validation workshop
* Agree on next steps, additional sources if information is lacking, and major edits for the final report
 | 10/06 | Lam Dong | Expert Group and Provincial Working Group members participateFacilitated by PGA coordinator and with technical contributions from UN-REDD |
| * Revise report according to input from validation workshop
* Provide a response matrix and circulate to stakeholders
 | By 16/06 |  | Editorial team with involvement from the PGA Coordinator |
| * Final approval of the report by Expert Panel
 | By 20/06 |  | Expert Group - Individual basis  |
| JuneOfficial launch(es) of the PGA report in Vietnam (Lam Dong and Hanoi)* Expert Group to discuss and agree on further road map for the PGA in Vietnam
* Communication of road map to stakeholders in Lam Dong
 | 24-30/06 |  | Facilitated by the PGA Coordinator in close collaboration with Expert Group membersExpert Group members join the meeting – alongside a representative delegation of the PWG |