**UN-REDD Social & Environmental Principles & Criteria: Internal Work Plan**

**Aug 2011 – Mar 2012**

| Actions | 2011 | 2012 |
| --- | --- | --- |
| LEAD | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar |
| *Tracking progress* |
| 1. Review of work plan | All | 12 |  |  |  |  |  |  |  |
| *Responding to comments and further development of P&C* |
| 2a. Prepare new version of P&C in light of comments : 1. input 3 sets of responses & discuss differences
2. Redraft P&C themselves
3. Revise purpose statement;
4. Annex(es) on process to date and relationship with other documents/standards
5. Discuss

b. sign off by UN-REDD agencies | a. (i) WCMC (LM/VK), UNDP (EH), (ii) UNEP (VK, LJM, JCG, WPS), UNDP (EH)(iii) WCMC (LJM), 1. UNDP (EH)
2. All;

b. WPS, TC | 19Drafts ii-iv 24v. 26 | a. 4, b. 2 |  |  |  |  |  |  |
| 3. Submit next draft of P&C to PB 7 (including translation by Sect) | JCG (to check possibility of reviewing translations)  |  | 5, docs posted 26 |  |  |  |  |  |  |
| 4. Consideration of P&C by PB 7 : request approval for further piloting by countries preparing NPs for submission at PB8 | RP, TC |  |  | 13-14 |  |  |  |  |  |
| 5. Public consultation period : both tool and P&C Using available events | JG to track Durban opportunities |  | (CBD consultation 21)Part’shp safeguard event 30? |  |  | Durban Forest day18 |  |  |  |
| 6. Simultaneous circulation to PB members and observers, IAG and other independent reviewersb. Coordinate agreement on list of independent reviewers (between UNDP/UNEP/FAO) | a. TC via Secretariat, b. LM/ED |  |  |  |  |  |  |  |  |
| 7. Facilitated consultation & testing round 2, with specific countries (preparing new NPs) | Likely to be Sri Lanka, Rep Congo, Guatemala + others? |  |  |  |  |  |  |  |  |
| 8. Revision following testing & consultations, including Cambridge? Meeting in Jan |  |  |  |  |  |  | ?17-18  | ?5 |  |
| 9. Present to PB 8 for approval (alongside tool) |  |  |  |  |  |  |  |  |  |
| *Tool development and piloting* |
| 1. Agreement on common format inc guidance | LM, UNDP |  | 5 |  |  |  |  |  |  |
| 2. a. Develop content with input from regional and national teams | LM, UNDP (AK) |  |  |  |  |  |  |  |  |
| 3. Prepare introduction and supporting material | LM, EH |  |  |  |  |  |  |  |  |
| 4. Consolidate and check for consistency | JCG |  |  |  |  |  |  |  |  |
| 5. Version 1 to review & testing (along with P&C) |  |  |  |  |  | 18 |  |  |  |
| 6. Revision (as for P&C) |  |  |  |  |  |  |  | ?5 |  |
| 7. Present to PB 8 (alongside P&C) |  |  |  |  |  |  |  |  |  |